## SCHEDULE OF VALUE WORKSHEET
GENESIS CAPITAL
CLIENT: | FCM Investments
DATE: | 08.05.2025
PROJECT: | 12750 Moorpark Street
| DESCRIPTION OF WORK | REHAB BUDGET | Cost Spent | Go-Forward
1 | Architect | 50000 | 0 | 50000
2 | Surveying | 25000 | 0 | 25000
3 | Soil Engineer | 30000 | 0 | 30000
4 | Plan Check Fees | 30000 | 0 | 30000
5 | Permit Fees | 275000 |  | 275000
6 | Utility Setup Fees | 75000 | 0 | 75000
7 | Deputy Inspections | 35 | 0 | 35
8 | Admin & Legal | 25000 | 0 | 25000
9 | Structural Engineer | 10000 | 0 | 10000
10 | Civil Engineer | 10000 | 0 | 10000
11 | Property Tax (2 year estimate) | 100000 |  | 100000
12 | Landscape Architect | 10000 | 0 | 10000
13 | MEP Engineer | 20000 | 0 | 20000
14 | Quimby Fee | 382500 | 0 | 382500
15 | Tenant Buyouts | 0 | 0 | 0
16 | Impact Fees | 0 | 0 | 0
17 | Insurance (builders risk) | 50000 | 0 | 50000
18 | Development Fee | 7000 | 0 | 7000
19 | General Conditions - Manpower (Allowance) | 592020.54 | 0 | 592020.54
20 | Demolition | 79500 | 0 | 79500
21 | Land Surveyor-Allowance | 11000 | 0 | 11000
22 | Structural Concrete | 327470 | 0 | 327470
23 | Spoils removal-Allowance | 5000 | 0 | 5000
24 | Lightweight Concrete | 60042 | 0 | 60042
25 | Concrete Masonry Unit (CMU) | 143700 | 0 | 143700
26 | Stone Facing - Brick Veneer | 13055 | 0 | 13055
27 | Structural Steel Fabricator Contractor | 33988.02 | 0 | 33988.02
28 | Elevator Steel - Allowance | 10000 | 0 | 10000
29 | Decorative Metals-Allowance | 75000 | 0 | 75000
30 | Glass Railing-Allowance | 35000 | 0 | 35000
31 | Rough Carpentry - Material & Labor | 970000 | 0 | 970000
32 | EBM System-Allowance | 10000 | 0 | 10000
33 | Below Grade Water Proofing | 7600 | 0 | 7600
34 | Above Grade Water Proofing | 46600 | 0 | 46600
35 | Thermal Insulation | 58250 | 0 | 58250
36 | Roofing | 74200 | 0 | 74200
37 | Sheet Metal Contractor-Allowance | 70000 | 0 | 70000
38 | Firestopping-Allowance | 3000 | 0 | 3000
39 | Joint Sealants-Allowance | 5000 | 0 | 5000
40 | Doors and Frames | 182256 | 0 | 182256
41 | Windows - Material | 81726.81 | 0 | 81726.81
42 | Windows - Installation | 25900 | 0 | 25900
43 | Entrances, Storefronts, and Curtain Walls | 8755 | 0 | 8755
44 | Drywall and metal stud framing | 437990 | 0 | 437990
45 | Painting and Coating | 130000 | 0 | 130000
46 | Flooring | 118463 | 0 | 118463
47 | Cement Plastering - Stucco-Allowance | 275000 | 0 | 275000
48 | Scaffolding-Allowance | 0 | 0 | 0
49 | Signages | 11972.11 | 0 | 11972.11
50 | Bathroom Accesories | 13056 | 0 | 13056
51 | Mirrors | 10840 | 0 | 10840
52 | Fire extinguishers-allowance | 3000 | 0 | 3000
53 | Mailboxes | 14136 | 0 | 14136
54 | Appliances - Material & Installation | 129875.28 | 0 | 129875.28
55 | Countertops-AIIowance | 50000 | 0 | 50000
56 | Cabinetry-Allowance | 103000 | 0 | 103000
57 | Elevators | 150000 | 0 | 150000
58 | Trash Chutes | 37409 | 0 | 37409
59 | Fire Sprinklers | 187300 | 0 | 187300
60 | Plumbing- Rough-Allowance | 800000 | 0 | 800000
61 | Plumbing - Finish | 100000 |  | 100000
62 | Water Submeter-aIIowanee | 5000 | 0 | 5000
63 | HVAC equipment & Ducting | 394800 | 0 | 394800
64 | Electrical rough and finish-Allowance | 575000 | 0 | 575000
65 | Electrical - Finish | 75000 |  | 75000
66 | Low Voltage- Structured Cabling | 32000 | 0 | 32000
67 | 2-way communication system (AOR) | 19000 | 0 | 19000
68 | ERRCS / DAS system | 51000 | 0 | 51000
69 | Access Control/Main Telephone Entry/Door Chimes-Allowance | 5000 | 0 | 5000
70 | Fire Detection and Alarm | 47250 | 0 | 47250
71 | Excavation and Fill | 57350 | 0 | 57350
72 | Fine Grading-Allowance | 10000 | 0 | 10000
73 | Site concrete, Site walkways Site Stairs | 10500 | 0 | 10500
74 | Offsite Concrete-Allowance | 10000 | 0 | 10000
75 | Striping-Allowance | 5000 | 0 | 5000
76 | Permeable Pavers | 28619.55 | 0 | 28619.55
77 | Irrigation system-Allowance | 50000 | 0 | 50000
78 | Planting - Landscaping-Allowance | 0 | 0 | 0
79 | Fiberglass Planters-Allowance | 0 | 0 | 0
80 | CSl-33 (Utilities) | 0 | 0 | 0
81 | Sanitary Sewerage-Allowance | 50000 | 0 | 50000
82 | Stormwater Utilities-Allowance | 0 | 0 | 0
83 | Electrical Utilities-Allowance | 0 | 0 | 0
84 | GC Fee | 806320.04 | 0 | 806320.04
85 | Contractor's Contingency | 689162.43 | 0 | 689162.43
| TOTAL | 9521641.78 | 0 | 9521641.78

## Draw #1
GENESIS CAPITAL DRAW REQUEST FORM
| CLIENT: | FCM Investments |  |  |  |  | TOTAL COMPLETED TO DATE: | 0
| PROJECT: | 12750 Moorpark Street |  |  |  |  | REMAINING $ IN BUDGET: | #REF!
| DATE: | 2025-08-19 |  |  |  |  | ORIGINAL SCHEDULE OF VALUES: | #REF!
| DRAW REQUEST: | 0 |  |  |  |  | CHANGE ORDERS: | 0
[7 empty] | REVISED SCHEDULE OF VALUES: | #REF!
| DESCRIPTION OF WORK |  | SCHEDULED VALUES | + / - CHANGES | REVISED VALUES | REMAINING | DRAW | COMPLETED AND
[6 empty] | $ PER BUDGET | 1 | STORED TO DATE
1 | Architect |  | 50000 | 0 | 50000 | 50000 | 0 | 0
2 | Surveying |  | 25000 | 0 | 25000 | 25000 | 0 | 0
3 | Soil Engineer |  | 30000 | 0 | 30000 | 30000 | 0 | 0
4 | Plan Check Fees |  | 30000 | 0 | 30000 | 30000 | 0 | 0
6 | Utility Setup Fees |  | 75000 | 0 | 75000 | 75000 | 0 | 0
7 | Deputy Inspections |  | 35 | 0 | 35 | 35 | 0 | 0
8 | Admin & Legal |  | 25000 | 0 | 25000 | 25000 | 0 | 0
9 | Structural Engineer |  | 10000 | 0 | 10000 | 10000 | 0 | 0
10 | Civil Engineer |  | 10000 | 0 | 10000 | 10000 | 0 | 0
12 | Landscape Architect |  | 10000 | 0 | 10000 | 10000 | 0 | 0
13 | MEP Engineer |  | 20000 | 0 | 20000 | 20000 | 0 | 0
14 | Quimby Fee |  | 382500 | 0 | 382500 | 382500 | 0 | 0
15 | Tenant Buyouts |  | 0 | 0 | 0 | 0 | 0 | 0
16 | Impact Fees |  | 0 | 0 | 0 | 0 | 0 | 0
17 | Insurance (builders risk) |  | 50000 | 0 | 50000 | 50000 | 0 | 0
18 | Development Fee |  | 7000 | 0 | 7000 | 7000 | 0 | 0
19 | General Conditions - Manpower (Allowance) |  | 592020.54 | 0 | 592020.54 | 592020.54 | 0 | 0
20 | Demolition |  | 79500 | 0 | 79500 | 79500 | 0 | 0
21 | Land Surveyor-Allowance |  | 11000 | 0 | 11000 | 11000 | 0 | 0
22 | Structural Concrete |  | 327470 | 0 | 327470 | 327470 | 0 | 0
23 | Spoils removal-Allowance |  | 5000 | 0 | 5000 | 5000 | 0 | 0
24 | Lightweight Concrete |  | 60042 | 0 | 60042 | 60042 | 0 | 0
25 | Concrete Masonry Unit (CMU) |  | 143700 | 0 | 143700 | 143700 | 0 | 0
26 | Stone Facing - Brick Veneer |  | 13055 | 0 | 13055 | 13055 | 0 | 0
27 | Structural Steel Fabricator Contractor |  | 33988.02 | 0 | 33988.02 | 33988.02 | 0 | 0
28 | Elevator Steel - Allowance |  | 10000 | 0 | 10000 | 10000 | 0 | 0
29 | Decorative Metals-Allowance |  | 75000 | 0 | 75000 | 75000 | 0 | 0
30 | Glass Railing-Allowance |  | 35000 | 0 | 35000 | 35000 | 0 | 0
31 | Rough Carpentry - Material & Labor |  | 970000 | 0 | 970000 | 970000 | 0 | 0
32 | EBM System-Allowance |  | 10000 | 0 | 10000 | 10000 | 0 | 0
33 | Below Grade Water Proofing |  | 7600 | 0 | 7600 | 7600 | 0 | 0
34 | Above Grade Water Proofing |  | 46600 | 0 | 46600 | 46600 | 0 | 0
35 | Thermal Insulation |  | 58250 | 0 | 58250 | 58250 | 0 | 0
36 | Roofing |  | 74200 | 0 | 74200 | 74200 | 0 | 0
37 | Sheet Metal Contractor-Allowance |  | 70000 | 0 | 70000 | 70000 | 0 | 0
38 | Firestopping-Allowance |  | 3000 | 0 | 3000 | 3000 | 0 | 0
39 | Joint Sealants-Allowance |  | 5000 | 0 | 5000 | 5000 | 0 | 0
40 | Doors and Frames |  | 182256 | 0 | 182256 | 182256 | 0 | 0
41 | Windows - Material |  | 81726.81 | 0 | 81726.81 | 81726.81 | 0 | 0
42 | Windows - Installation |  | 25900 | 0 | 25900 | 25900 | 0 | 0
43 | Entrances, Storefronts, and Curtain Walls |  | 8755 | 0 | 8755 | 8755 | 0 | 0
44 | Drywall and metal stud framing |  | 437990 | 0 | 437990 | 437990 | 0 | 0
45 | Painting and Coating |  | 130000 | 0 | 130000 | 130000 | 0 | 0
46 | Flooring |  | 118463 | 0 | 118463 | 118463 | 0 | 0
47 | Cement Plastering - Stucco-Allowance |  | 275000 | 0 | 275000 | 275000 | 0 | 0
48 | Scaffolding-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0
49 | Signages |  | 11972.11 | 0 | 11972.11 | 11972.11 | 0 | 0
50 | Bathroom Accesories |  | 13056 | 0 | 13056 | 13056 | 0 | 0
51 | Fire extinguishers-allowance |  | 10840 | 0 | 10840 | 10840 | 0 | 0
52 | #REF! |  | 3000 | 0 | 3000 | 3000 | 0 | 0
53 | Mailboxes |  | 14136 | 0 | 14136 | 14136 | 0 | 0
54 | Appliances - Material & Installation |  | 129875.28 | 0 | 129875.28 | 129875.28 | 0 | 0
55 | Countertops-AIIowance |  | 50000 | 0 | 50000 | 50000 | 0 | 0
56 | Cabinetry-Allowance |  | 103000 | 0 | 103000 | 103000 | 0 | 0
57 | Elevators |  | 150000 | 0 | 150000 | 150000 | 0 | 0
58 | Trash Chutes |  | 37409 | 0 | 37409 | 37409 | 0 | 0
59 | Fire Sprinklers |  | 187300 | 0 | 187300 | 187300 | 0 | 0
60 | Plumbing- Rough-Allowance |  | 800000 | 0 | 800000 | 800000 | 0 | 0
62 | Water Submeter-aIIowanee |  | 5000 | 0 | 5000 | 5000 | 0 | 0
63 | HVAC equipment & Ducting |  | 394800 | 0 | 394800 | 394800 | 0 | 0
64 | Electrical rough and finish-Allowance |  | 575000 | 0 | 575000 | 575000 | 0 | 0
66 | Low Voltage- Structured Cabling |  | 32000 | 0 | 32000 | 32000 | 0 | 0
67 | 2-way communication system (AOR) |  | 19000 | 0 | 19000 | 19000 | 0 | 0
68 | ERRCS / DAS system |  | 51000 | 0 | 51000 | 51000 | 0 | 0
69 | Access Control/Main Telephone Entry/Door Chimes-Allowance |  | 5000 | 0 | 5000 | 5000 | 0 | 0
70 | Fire Detection and Alarm |  | 47250 | 0 | 47250 | 47250 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | 0
71 | Excavation and Fill |  | 57350 | 0 | 57350 | 57350 | 0 | 0
72 | Fine Grading-Allowance |  | 10000 | 0 | 10000 | 10000 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | 0
73 | Site concrete, Site walkways Site Stairs |  | 10500 | 0 | 10500 | 10500 | 0 | 0
74 | Offsite Concrete-Allowance |  | 10000 | 0 | 10000 | 10000 | 0 | 0
75 | Striping-Allowance |  | 5000 | 0 | 5000 | 5000 | 0 | 0
76 | Permeable Pavers |  | 28619.55 | 0 | 28619.55 | 28619.55 | 0 | 0
77 | Irrigation system-Allowance |  | 50000 | 0 | 50000 | 50000 | 0 | 0
78 | Planting - Landscaping-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0
79 | Fiberglass Planters-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0
80 | CSl-33 (Utilities) |  | 0 | 0 | 0 | 0 | 0 | 0
81 | Sanitary Sewerage-Allowance |  | 50000 | 0 | 50000 | 50000 | 0 | 0
82 | Stormwater Utilities-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0
83 | Electrical Utilities-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0
84 | GC Fee |  | 806320.04 | 0 | 806320.04 | 806320.04 | 0 | 0
85 | Contractor's Contingency |  | 689162.43 | 0 | 689162.43 | 689162.43 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | 0
| TOTAL |  | #REF! | 0 | #REF! | #REF! | 0 | 0

## Draw #2
GENESIS CAPITAL DRAW FORM
| CLIENT: | FCM Investments | [5 empty] | TOTAL COMPLETED TO DATE: | 0 | #REF!
| DATE: | 2025-08-19 | [5 empty] | REMAINING $ IN BUDGET: | #REF!
| PROJECT: | 12750 Moorpark Street | [5 empty] | ORIGINAL SCHEDULE OF VALUES: | #REF!
| DRAW REQUEST: | 0 | [5 empty] | CHANGE ORDERS: | 0
[8 empty] | REVISED SCHEDULE OF VALUES: | #REF!
| DESCRIPTION OF WORK |  | SCHEDULED VALUES | PREVIOUS | + / - CHANGES | REVISED VALUES | REMAINING | DRAW | COMPLETED AND
|  |  |  | CHANGES |  |  | BUDGET | 2 | STORED TO DATE
1 | Architect |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
2 | Surveying |  | 25000 | 0 | 0 | 25000 | 25000 | 0 | 0
3 | Soil Engineer |  | 30000 | 0 | 0 | 30000 | 30000 | 0 | 0
4 | Plan Check Fees |  | 30000 | 0 | 0 | 30000 | 30000 | 0 | 0
6 | Utility Setup Fees |  | 75000 | 0 | 0 | 75000 | 75000 | 0 | 0
7 | Deputy Inspections |  | 35 | 0 | 0 | 35 | 35 | 0 | 0
8 | Admin & Legal |  | 25000 | 0 | 0 | 25000 | 25000 | 0 | 0
9 | Structural Engineer |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
10 | Civil Engineer |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
12 | Landscape Architect |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
13 | MEP Engineer |  | 20000 | 0 | 0 | 20000 | 20000 | 0 | 0
14 | Quimby Fee |  | 382500 | 0 | 0 | 382500 | 382500 | 0 | 0
15 | Tenant Buyouts |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Impact Fees |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Insurance (builders risk) |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
18 | Development Fee |  | 7000 | 0 | 0 | 7000 | 7000 | 0 | 0
19 | General Conditions - Manpower (Allowance) |  | 592020.54 | 0 | 0 | 592020.54 | 592020.54 | 0 | 0
20 | Demolition |  | 79500 | 0 | 0 | 79500 | 79500 | 0 | 0
21 | Land Surveyor-Allowance |  | 11000 | 0 | 0 | 11000 | 11000 | 0 | 0
22 | Structural Concrete |  | 327470 | 0 | 0 | 327470 | 327470 | 0 | 0
23 | Spoils removal-Allowance |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
24 | Lightweight Concrete |  | 60042 | 0 | 0 | 60042 | 60042 | 0 | 0
25 | Concrete Masonry Unit (CMU) |  | 143700 | 0 | 0 | 143700 | 143700 | 0 | 0
26 | Stone Facing - Brick Veneer |  | 13055 | 0 | 0 | 13055 | 13055 | 0 | 0
27 | Structural Steel Fabricator Contractor |  | 33988.02 | 0 | 0 | 33988.02 | 33988.02 | 0 | 0
28 | Elevator Steel - Allowance |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
29 | Decorative Metals-Allowance |  | 75000 | 0 | 0 | 75000 | 75000 | 0 | 0
30 | Glass Railing-Allowance |  | 35000 | 0 | 0 | 35000 | 35000 | 0 | 0
31 | Rough Carpentry - Material & Labor |  | 970000 | 0 | 0 | 970000 | 970000 | 0 | 0
32 | EBM System-Allowance |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
33 | Below Grade Water Proofing |  | 7600 | 0 | 0 | 7600 | 7600 | 0 | 0
34 | Above Grade Water Proofing |  | 46600 | 0 | 0 | 46600 | 46600 | 0 | 0
35 | Thermal Insulation |  | 58250 | 0 | 0 | 58250 | 58250 | 0 | 0
36 | Roofing |  | 74200 | 0 | 0 | 74200 | 74200 | 0 | 0
37 | Sheet Metal Contractor-Allowance |  | 70000 | 0 | 0 | 70000 | 70000 | 0 | 0
38 | Firestopping-Allowance |  | 3000 | 0 | 0 | 3000 | 3000 | 0 | 0
39 | Joint Sealants-Allowance |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
40 | Doors and Frames |  | 182256 | 0 | 0 | 182256 | 182256 | 0 | 0
41 | Windows - Material |  | 81726.81 | 0 | 0 | 81726.81 | 81726.81 | 0 | 0
42 | Windows - Installation |  | 25900 | 0 | 0 | 25900 | 25900 | 0 | 0
43 | Entrances, Storefronts, and Curtain Walls |  | 8755 | 0 | 0 | 8755 | 8755 | 0 | 0
44 | Drywall and metal stud framing |  | 437990 | 0 | 0 | 437990 | 437990 | 0 | 0
45 | Painting and Coating |  | 130000 | 0 | 0 | 130000 | 130000 | 0 | 0
46 | Flooring |  | 118463 | 0 | 0 | 118463 | 118463 | 0 | 0
47 | Cement Plastering - Stucco-Allowance |  | 275000 | 0 | 0 | 275000 | 275000 | 0 | 0
48 | Scaffolding-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | Signages |  | 11972.11 | 0 | 0 | 11972.11 | 11972.11 | 0 | 0
50 | Bathroom Accesories |  | 13056 | 0 | 0 | 13056 | 13056 | 0 | 0
51 | Fire extinguishers-allowance |  | 10840 | 0 | 0 | 10840 | 10840 | 0 | 0
52 | #REF! |  | 3000 | 0 | 0 | 3000 | 3000 | 0 | 0
53 | Mailboxes |  | 14136 | 0 | 0 | 14136 | 14136 | 0 | 0
54 | Appliances - Material & Installation |  | 129875.28 | 0 | 0 | 129875.28 | 129875.28 | 0 | 0
55 | Countertops-AIIowance |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
56 | Cabinetry-Allowance |  | 103000 | 0 | 0 | 103000 | 103000 | 0 | 0
57 | Elevators |  | 150000 | 0 | 0 | 150000 | 150000 | 0 | 0
58 | Trash Chutes |  | 37409 | 0 | 0 | 37409 | 37409 | 0 | 0
59 | Fire Sprinklers |  | 187300 | 0 | 0 | 187300 | 187300 | 0 | 0
60 | Plumbing- Rough-Allowance |  | 800000 | 0 | 0 | 800000 | 800000 | 0 | 0
62 | Water Submeter-aIIowanee |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
63 | HVAC equipment & Ducting |  | 394800 | 0 | 0 | 394800 | 394800 | 0 | 0
64 | Electrical rough and finish-Allowance |  | 575000 | 0 | 0 | 575000 | 575000 | 0 | 0
66 | Low Voltage- Structured Cabling |  | 32000 | 0 | 0 | 32000 | 32000 | 0 | 0
67 | 2-way communication system (AOR) |  | 19000 | 0 | 0 | 19000 | 19000 | 0 | 0
68 | ERRCS / DAS system |  | 51000 | 0 | 0 | 51000 | 51000 | 0 | 0
69 | Access Control/Main Telephone Entry/Door Chimes-Allowance |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
70 | Fire Detection and Alarm |  | 47250 | 0 | 0 | 47250 | 47250 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
71 | Excavation and Fill |  | 57350 | 0 | 0 | 57350 | 57350 | 0 | 0
72 | Fine Grading-Allowance |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
73 | Site concrete, Site walkways Site Stairs |  | 10500 | 0 | 0 | 10500 | 10500 | 0 | 0
74 | Offsite Concrete-Allowance |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
75 | Striping-Allowance |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
76 | Permeable Pavers |  | 28619.55 | 0 | 0 | 28619.55 | 28619.55 | 0 | 0
77 | Irrigation system-Allowance |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
78 | Planting - Landscaping-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
79 | Fiberglass Planters-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 | CSl-33 (Utilities) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
81 | Sanitary Sewerage-Allowance |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
82 | Stormwater Utilities-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
83 | Electrical Utilities-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
84 | GC Fee |  | 806320.04 | 0 | 0 | 806320.04 | 806320.04 | 0 | 0
85 | Contractor's Contingency |  | 689162.43 | 0 | 0 | 689162.43 | 689162.43 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
| TOTAL |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0

## Draw #3
GENESIS CAPITAL DRAW FORM
| CLIENT: | FCM Investments | [5 empty] | TOTAL COMPLETED TO DATE: | 0 | #REF!
| DATE: | 2025-08-19 | [5 empty] | REMAINING $ IN BUDGET: | #REF!
| PROJECT: | 12750 Moorpark Street | [5 empty] | ORIGINAL SCHEDULE OF VALUES: | #REF!
| DRAW REQUEST: | 0 | [5 empty] | CHANGE ORDERS: | 0
[8 empty] | REVISED SCHEDULE OF VALUES: | #REF!
| DESCRIPTION OF WORK |  | SCHEDULED VALUES | PREVIOUS | + / - CHANGES | REVISED VALUES | REMAINING | DRAW | COMPLETED AND
|  |  |  | CHANGES |  |  | BUDGET | 3 | STORED TO DATE
1 | Architect |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
2 | Surveying |  | 25000 | 0 | 0 | 25000 | 25000 | 0 | 0
3 | Soil Engineer |  | 30000 | 0 | 0 | 30000 | 30000 | 0 | 0
4 | Plan Check Fees |  | 30000 | 0 | 0 | 30000 | 30000 | 0 | 0
6 | Utility Setup Fees |  | 75000 | 0 | 0 | 75000 | 75000 | 0 | 0
7 | Deputy Inspections |  | 35 | 0 | 0 | 35 | 35 | 0 | 0
8 | Admin & Legal |  | 25000 | 0 | 0 | 25000 | 25000 | 0 | 0
9 | Structural Engineer |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
10 | Civil Engineer |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
12 | Landscape Architect |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
13 | MEP Engineer |  | 20000 | 0 | 0 | 20000 | 20000 | 0 | 0
14 | Quimby Fee |  | 382500 | 0 | 0 | 382500 | 382500 | 0 | 0
15 | Tenant Buyouts |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Impact Fees |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Insurance (builders risk) |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
18 | Development Fee |  | 7000 | 0 | 0 | 7000 | 7000 | 0 | 0
19 | General Conditions - Manpower (Allowance) |  | 592020.54 | 0 | 0 | 592020.54 | 592020.54 | 0 | 0
20 | Demolition |  | 79500 | 0 | 0 | 79500 | 79500 | 0 | 0
21 | Land Surveyor-Allowance |  | 11000 | 0 | 0 | 11000 | 11000 | 0 | 0
22 | Structural Concrete |  | 327470 | 0 | 0 | 327470 | 327470 | 0 | 0
23 | Spoils removal-Allowance |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
24 | Lightweight Concrete |  | 60042 | 0 | 0 | 60042 | 60042 | 0 | 0
25 | Concrete Masonry Unit (CMU) |  | 143700 | 0 | 0 | 143700 | 143700 | 0 | 0
26 | Stone Facing - Brick Veneer |  | 13055 | 0 | 0 | 13055 | 13055 | 0 | 0
27 | Structural Steel Fabricator Contractor |  | 33988.02 | 0 | 0 | 33988.02 | 33988.02 | 0 | 0
28 | Elevator Steel - Allowance |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
29 | Decorative Metals-Allowance |  | 75000 | 0 | 0 | 75000 | 75000 | 0 | 0
30 | Glass Railing-Allowance |  | 35000 | 0 | 0 | 35000 | 35000 | 0 | 0
31 | Rough Carpentry - Material & Labor |  | 970000 | 0 | 0 | 970000 | 970000 | 0 | 0
32 | EBM System-Allowance |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
33 | Below Grade Water Proofing |  | 7600 | 0 | 0 | 7600 | 7600 | 0 | 0
34 | Above Grade Water Proofing |  | 46600 | 0 | 0 | 46600 | 46600 | 0 | 0
35 | Thermal Insulation |  | 58250 | 0 | 0 | 58250 | 58250 | 0 | 0
36 | Roofing |  | 74200 | 0 | 0 | 74200 | 74200 | 0 | 0
37 | Sheet Metal Contractor-Allowance |  | 70000 | 0 | 0 | 70000 | 70000 | 0 | 0
38 | Firestopping-Allowance |  | 3000 | 0 | 0 | 3000 | 3000 | 0 | 0
39 | Joint Sealants-Allowance |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
40 | Doors and Frames |  | 182256 | 0 | 0 | 182256 | 182256 | 0 | 0
41 | Windows - Material |  | 81726.81 | 0 | 0 | 81726.81 | 81726.81 | 0 | 0
42 | Windows - Installation |  | 25900 | 0 | 0 | 25900 | 25900 | 0 | 0
43 | Entrances, Storefronts, and Curtain Walls |  | 8755 | 0 | 0 | 8755 | 8755 | 0 | 0
44 | Drywall and metal stud framing |  | 437990 | 0 | 0 | 437990 | 437990 | 0 | 0
45 | Painting and Coating |  | 130000 | 0 | 0 | 130000 | 130000 | 0 | 0
46 | Flooring |  | 118463 | 0 | 0 | 118463 | 118463 | 0 | 0
47 | Cement Plastering - Stucco-Allowance |  | 275000 | 0 | 0 | 275000 | 275000 | 0 | 0
48 | Scaffolding-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | Signages |  | 11972.11 | 0 | 0 | 11972.11 | 11972.11 | 0 | 0
50 | Bathroom Accesories |  | 13056 | 0 | 0 | 13056 | 13056 | 0 | 0
51 | Fire extinguishers-allowance |  | 10840 | 0 | 0 | 10840 | 10840 | 0 | 0
52 | #REF! |  | 3000 | 0 | 0 | 3000 | 3000 | 0 | 0
53 | Mailboxes |  | 14136 | 0 | 0 | 14136 | 14136 | 0 | 0
54 | Appliances - Material & Installation |  | 129875.28 | 0 | 0 | 129875.28 | 129875.28 | 0 | 0
55 | Countertops-AIIowance |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
56 | Cabinetry-Allowance |  | 103000 | 0 | 0 | 103000 | 103000 | 0 | 0
57 | Elevators |  | 150000 | 0 | 0 | 150000 | 150000 | 0 | 0
58 | Trash Chutes |  | 37409 | 0 | 0 | 37409 | 37409 | 0 | 0
59 | Fire Sprinklers |  | 187300 | 0 | 0 | 187300 | 187300 | 0 | 0
60 | Plumbing- Rough-Allowance |  | 800000 | 0 | 0 | 800000 | 800000 | 0 | 0
62 | Water Submeter-aIIowanee |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
63 | HVAC equipment & Ducting |  | 394800 | 0 | 0 | 394800 | 394800 | 0 | 0
64 | Electrical rough and finish-Allowance |  | 575000 | 0 | 0 | 575000 | 575000 | 0 | 0
66 | Low Voltage- Structured Cabling |  | 32000 | 0 | 0 | 32000 | 32000 | 0 | 0
67 | 2-way communication system (AOR) |  | 19000 | 0 | 0 | 19000 | 19000 | 0 | 0
68 | ERRCS / DAS system |  | 51000 | 0 | 0 | 51000 | 51000 | 0 | 0
69 | Access Control/Main Telephone Entry/Door Chimes-Allowance |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
70 | Fire Detection and Alarm |  | 47250 | 0 | 0 | 47250 | 47250 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
71 | Excavation and Fill |  | 57350 | 0 | 0 | 57350 | 57350 | 0 | 0
72 | Fine Grading-Allowance |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
73 | Site concrete, Site walkways Site Stairs |  | 10500 | 0 | 0 | 10500 | 10500 | 0 | 0
74 | Offsite Concrete-Allowance |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
75 | Striping-Allowance |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
76 | Permeable Pavers |  | 28619.55 | 0 | 0 | 28619.55 | 28619.55 | 0 | 0
77 | Irrigation system-Allowance |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
78 | Planting - Landscaping-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
79 | Fiberglass Planters-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 | CSl-33 (Utilities) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
81 | Sanitary Sewerage-Allowance |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
82 | Stormwater Utilities-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
83 | Electrical Utilities-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
84 | GC Fee |  | 806320.04 | 0 | 0 | 806320.04 | 806320.04 | 0 | 0
85 | Contractor's Contingency |  | 689162.43 | 0 | 0 | 689162.43 | 689162.43 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
| TOTAL |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0

## Draw #4
GENESIS CAPITAL DRAW FORM
| CLIENT: | FCM Investments | [5 empty] | TOTAL COMPLETED TO DATE: | 0 | #REF!
| DATE: | 2025-08-19 | [5 empty] | REMAINING $ IN BUDGET: | #REF!
| PROJECT: | 12750 Moorpark Street | [5 empty] | ORIGINAL SCHEDULE OF VALUES: | #REF!
| DRAW REQUEST: | 0 | [5 empty] | CHANGE ORDERS: | 0
[8 empty] | REVISED SCHEDULE OF VALUES: | #REF!
| DESCRIPTION OF WORK |  | SCHEDULED VALUES | PREVIOUS | + / - CHANGES | REVISED VALUES | REMAINING | DRAW | COMPLETED AND
|  |  |  | CHANGES |  |  | BUDGET | 4 | STORED TO DATE
1 | Architect |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
2 | Surveying |  | 25000 | 0 | 0 | 25000 | 25000 | 0 | 0
3 | Soil Engineer |  | 30000 | 0 | 0 | 30000 | 30000 | 0 | 0
4 | Plan Check Fees |  | 30000 | 0 | 0 | 30000 | 30000 | 0 | 0
6 | Utility Setup Fees |  | 75000 | 0 | 0 | 75000 | 75000 | 0 | 0
7 | Deputy Inspections |  | 35 | 0 | 0 | 35 | 35 | 0 | 0
8 | Admin & Legal |  | 25000 | 0 | 0 | 25000 | 25000 | 0 | 0
9 | Structural Engineer |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
10 | Civil Engineer |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
12 | Landscape Architect |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
13 | MEP Engineer |  | 20000 | 0 | 0 | 20000 | 20000 | 0 | 0
14 | Quimby Fee |  | 382500 | 0 | 0 | 382500 | 382500 | 0 | 0
15 | Tenant Buyouts |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Impact Fees |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Insurance (builders risk) |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
18 | Development Fee |  | 7000 | 0 | 0 | 7000 | 7000 | 0 | 0
19 | General Conditions - Manpower (Allowance) |  | 592020.54 | 0 | 0 | 592020.54 | 592020.54 | 0 | 0
20 | Demolition |  | 79500 | 0 | 0 | 79500 | 79500 | 0 | 0
21 | Land Surveyor-Allowance |  | 11000 | 0 | 0 | 11000 | 11000 | 0 | 0
22 | Structural Concrete |  | 327470 | 0 | 0 | 327470 | 327470 | 0 | 0
23 | Spoils removal-Allowance |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
24 | Lightweight Concrete |  | 60042 | 0 | 0 | 60042 | 60042 | 0 | 0
25 | Concrete Masonry Unit (CMU) |  | 143700 | 0 | 0 | 143700 | 143700 | 0 | 0
26 | Stone Facing - Brick Veneer |  | 13055 | 0 | 0 | 13055 | 13055 | 0 | 0
27 | Structural Steel Fabricator Contractor |  | 33988.02 | 0 | 0 | 33988.02 | 33988.02 | 0 | 0
28 | Elevator Steel - Allowance |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
29 | Decorative Metals-Allowance |  | 75000 | 0 | 0 | 75000 | 75000 | 0 | 0
30 | Glass Railing-Allowance |  | 35000 | 0 | 0 | 35000 | 35000 | 0 | 0
31 | Rough Carpentry - Material & Labor |  | 970000 | 0 | 0 | 970000 | 970000 | 0 | 0
32 | EBM System-Allowance |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
33 | Below Grade Water Proofing |  | 7600 | 0 | 0 | 7600 | 7600 | 0 | 0
34 | Above Grade Water Proofing |  | 46600 | 0 | 0 | 46600 | 46600 | 0 | 0
35 | Thermal Insulation |  | 58250 | 0 | 0 | 58250 | 58250 | 0 | 0
36 | Roofing |  | 74200 | 0 | 0 | 74200 | 74200 | 0 | 0
37 | Sheet Metal Contractor-Allowance |  | 70000 | 0 | 0 | 70000 | 70000 | 0 | 0
38 | Firestopping-Allowance |  | 3000 | 0 | 0 | 3000 | 3000 | 0 | 0
39 | Joint Sealants-Allowance |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
40 | Doors and Frames |  | 182256 | 0 | 0 | 182256 | 182256 | 0 | 0
41 | Windows - Material |  | 81726.81 | 0 | 0 | 81726.81 | 81726.81 | 0 | 0
42 | Windows - Installation |  | 25900 | 0 | 0 | 25900 | 25900 | 0 | 0
43 | Entrances, Storefronts, and Curtain Walls |  | 8755 | 0 | 0 | 8755 | 8755 | 0 | 0
44 | Drywall and metal stud framing |  | 437990 | 0 | 0 | 437990 | 437990 | 0 | 0
45 | Painting and Coating |  | 130000 | 0 | 0 | 130000 | 130000 | 0 | 0
46 | Flooring |  | 118463 | 0 | 0 | 118463 | 118463 | 0 | 0
47 | Cement Plastering - Stucco-Allowance |  | 275000 | 0 | 0 | 275000 | 275000 | 0 | 0
48 | Scaffolding-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | Signages |  | 11972.11 | 0 | 0 | 11972.11 | 11972.11 | 0 | 0
50 | Bathroom Accesories |  | 13056 | 0 | 0 | 13056 | 13056 | 0 | 0
51 | Fire extinguishers-allowance |  | 10840 | 0 | 0 | 10840 | 10840 | 0 | 0
52 | #REF! |  | 3000 | 0 | 0 | 3000 | 3000 | 0 | 0
53 | Mailboxes |  | 14136 | 0 | 0 | 14136 | 14136 | 0 | 0
54 | Appliances - Material & Installation |  | 129875.28 | 0 | 0 | 129875.28 | 129875.28 | 0 | 0
55 | Countertops-AIIowance |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
56 | Cabinetry-Allowance |  | 103000 | 0 | 0 | 103000 | 103000 | 0 | 0
57 | Elevators |  | 150000 | 0 | 0 | 150000 | 150000 | 0 | 0
58 | Trash Chutes |  | 37409 | 0 | 0 | 37409 | 37409 | 0 | 0
59 | Fire Sprinklers |  | 187300 | 0 | 0 | 187300 | 187300 | 0 | 0
60 | Plumbing- Rough-Allowance |  | 800000 | 0 | 0 | 800000 | 800000 | 0 | 0
62 | Water Submeter-aIIowanee |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
63 | HVAC equipment & Ducting |  | 394800 | 0 | 0 | 394800 | 394800 | 0 | 0
64 | Electrical rough and finish-Allowance |  | 575000 | 0 | 0 | 575000 | 575000 | 0 | 0
66 | Low Voltage- Structured Cabling |  | 32000 | 0 | 0 | 32000 | 32000 | 0 | 0
67 | 2-way communication system (AOR) |  | 19000 | 0 | 0 | 19000 | 19000 | 0 | 0
68 | ERRCS / DAS system |  | 51000 | 0 | 0 | 51000 | 51000 | 0 | 0
69 | Access Control/Main Telephone Entry/Door Chimes-Allowance |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
70 | Fire Detection and Alarm |  | 47250 | 0 | 0 | 47250 | 47250 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
71 | Excavation and Fill |  | 57350 | 0 | 0 | 57350 | 57350 | 0 | 0
72 | Fine Grading-Allowance |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
73 | Site concrete, Site walkways Site Stairs |  | 10500 | 0 | 0 | 10500 | 10500 | 0 | 0
74 | Offsite Concrete-Allowance |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
75 | Striping-Allowance |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
76 | Permeable Pavers |  | 28619.55 | 0 | 0 | 28619.55 | 28619.55 | 0 | 0
77 | Irrigation system-Allowance |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
78 | Planting - Landscaping-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
79 | Fiberglass Planters-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 | CSl-33 (Utilities) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
81 | Sanitary Sewerage-Allowance |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
82 | Stormwater Utilities-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
83 | Electrical Utilities-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
84 | GC Fee |  | 806320.04 | 0 | 0 | 806320.04 | 806320.04 | 0 | 0
85 | Contractor's Contingency |  | 689162.43 | 0 | 0 | 689162.43 | 689162.43 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
| TOTAL |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0

## Draw #5
GENESIS CAPITAL DRAW FORM
| CLIENT: | FCM Investments | [5 empty] | TOTAL COMPLETED TO DATE: | 0 | #REF!
| DATE: | 2025-08-19 | [5 empty] | REMAINING $ IN BUDGET: | #REF!
| PROJECT: | 12750 Moorpark Street | [5 empty] | ORIGINAL SCHEDULE OF VALUES: | #REF!
| DRAW REQUEST: | 0 | [5 empty] | CHANGE ORDERS: | 0
[8 empty] | REVISED SCHEDULE OF VALUES: | #REF!
| DESCRIPTION OF WORK |  | SCHEDULED VALUES | PREVIOUS | + / - CHANGES | REVISED VALUES | REMAINING | DRAW | COMPLETED AND
|  |  |  | CHANGES |  |  | BUDGET | 5 | STORED TO DATE
1 | Architect |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
2 | Surveying |  | 25000 | 0 | 0 | 25000 | 25000 | 0 | 0
3 | Soil Engineer |  | 30000 | 0 | 0 | 30000 | 30000 | 0 | 0
4 | Plan Check Fees |  | 30000 | 0 | 0 | 30000 | 30000 | 0 | 0
6 | Utility Setup Fees |  | 75000 | 0 | 0 | 75000 | 75000 | 0 | 0
7 | Deputy Inspections |  | 35 | 0 | 0 | 35 | 35 | 0 | 0
8 | Admin & Legal |  | 25000 | 0 | 0 | 25000 | 25000 | 0 | 0
9 | Structural Engineer |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
10 | Civil Engineer |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
12 | Landscape Architect |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
13 | MEP Engineer |  | 20000 | 0 | 0 | 20000 | 20000 | 0 | 0
14 | Quimby Fee |  | 382500 | 0 | 0 | 382500 | 382500 | 0 | 0
15 | Tenant Buyouts |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Impact Fees |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Insurance (builders risk) |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
18 | Development Fee |  | 7000 | 0 | 0 | 7000 | 7000 | 0 | 0
19 | General Conditions - Manpower (Allowance) |  | 592020.54 | 0 | 0 | 592020.54 | 592020.54 | 0 | 0
20 | Demolition |  | 79500 | 0 | 0 | 79500 | 79500 | 0 | 0
21 | Land Surveyor-Allowance |  | 11000 | 0 | 0 | 11000 | 11000 | 0 | 0
22 | Structural Concrete |  | 327470 | 0 | 0 | 327470 | 327470 | 0 | 0
23 | Spoils removal-Allowance |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
24 | Lightweight Concrete |  | 60042 | 0 | 0 | 60042 | 60042 | 0 | 0
25 | Concrete Masonry Unit (CMU) |  | 143700 | 0 | 0 | 143700 | 143700 | 0 | 0
26 | Stone Facing - Brick Veneer |  | 13055 | 0 | 0 | 13055 | 13055 | 0 | 0
27 | Structural Steel Fabricator Contractor |  | 33988.02 | 0 | 0 | 33988.02 | 33988.02 | 0 | 0
28 | Elevator Steel - Allowance |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
29 | Decorative Metals-Allowance |  | 75000 | 0 | 0 | 75000 | 75000 | 0 | 0
30 | Glass Railing-Allowance |  | 35000 | 0 | 0 | 35000 | 35000 | 0 | 0
31 | Rough Carpentry - Material & Labor |  | 970000 | 0 | 0 | 970000 | 970000 | 0 | 0
32 | EBM System-Allowance |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
33 | Below Grade Water Proofing |  | 7600 | 0 | 0 | 7600 | 7600 | 0 | 0
34 | Above Grade Water Proofing |  | 46600 | 0 | 0 | 46600 | 46600 | 0 | 0
35 | Thermal Insulation |  | 58250 | 0 | 0 | 58250 | 58250 | 0 | 0
36 | Roofing |  | 74200 | 0 | 0 | 74200 | 74200 | 0 | 0
37 | Sheet Metal Contractor-Allowance |  | 70000 | 0 | 0 | 70000 | 70000 | 0 | 0
38 | Firestopping-Allowance |  | 3000 | 0 | 0 | 3000 | 3000 | 0 | 0
39 | Joint Sealants-Allowance |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
40 | Doors and Frames |  | 182256 | 0 | 0 | 182256 | 182256 | 0 | 0
41 | Windows - Material |  | 81726.81 | 0 | 0 | 81726.81 | 81726.81 | 0 | 0
42 | Windows - Installation |  | 25900 | 0 | 0 | 25900 | 25900 | 0 | 0
43 | Entrances, Storefronts, and Curtain Walls |  | 8755 | 0 | 0 | 8755 | 8755 | 0 | 0
44 | Drywall and metal stud framing |  | 437990 | 0 | 0 | 437990 | 437990 | 0 | 0
45 | Painting and Coating |  | 130000 | 0 | 0 | 130000 | 130000 | 0 | 0
46 | Flooring |  | 118463 | 0 | 0 | 118463 | 118463 | 0 | 0
47 | Cement Plastering - Stucco-Allowance |  | 275000 | 0 | 0 | 275000 | 275000 | 0 | 0
48 | Scaffolding-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | Signages |  | 11972.11 | 0 | 0 | 11972.11 | 11972.11 | 0 | 0
50 | Bathroom Accesories |  | 13056 | 0 | 0 | 13056 | 13056 | 0 | 0
51 | Fire extinguishers-allowance |  | 10840 | 0 | 0 | 10840 | 10840 | 0 | 0
52 | #REF! |  | 3000 | 0 | 0 | 3000 | 3000 | 0 | 0
53 | Mailboxes |  | 14136 | 0 | 0 | 14136 | 14136 | 0 | 0
54 | Appliances - Material & Installation |  | 129875.28 | 0 | 0 | 129875.28 | 129875.28 | 0 | 0
55 | Countertops-AIIowance |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
56 | Cabinetry-Allowance |  | 103000 | 0 | 0 | 103000 | 103000 | 0 | 0
57 | Elevators |  | 150000 | 0 | 0 | 150000 | 150000 | 0 | 0
58 | Trash Chutes |  | 37409 | 0 | 0 | 37409 | 37409 | 0 | 0
59 | Fire Sprinklers |  | 187300 | 0 | 0 | 187300 | 187300 | 0 | 0
60 | Plumbing- Rough-Allowance |  | 800000 | 0 | 0 | 800000 | 800000 | 0 | 0
62 | Water Submeter-aIIowanee |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
63 | HVAC equipment & Ducting |  | 394800 | 0 | 0 | 394800 | 394800 | 0 | 0
64 | Electrical rough and finish-Allowance |  | 575000 | 0 | 0 | 575000 | 575000 | 0 | 0
66 | Low Voltage- Structured Cabling |  | 32000 | 0 | 0 | 32000 | 32000 | 0 | 0
67 | 2-way communication system (AOR) |  | 19000 | 0 | 0 | 19000 | 19000 | 0 | 0
68 | ERRCS / DAS system |  | 51000 | 0 | 0 | 51000 | 51000 | 0 | 0
69 | Access Control/Main Telephone Entry/Door Chimes-Allowance |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
70 | Fire Detection and Alarm |  | 47250 | 0 | 0 | 47250 | 47250 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
71 | Excavation and Fill |  | 57350 | 0 | 0 | 57350 | 57350 | 0 | 0
72 | Fine Grading-Allowance |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
73 | Site concrete, Site walkways Site Stairs |  | 10500 | 0 | 0 | 10500 | 10500 | 0 | 0
74 | Offsite Concrete-Allowance |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
75 | Striping-Allowance |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
76 | Permeable Pavers |  | 28619.55 | 0 | 0 | 28619.55 | 28619.55 | 0 | 0
77 | Irrigation system-Allowance |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
78 | Planting - Landscaping-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
79 | Fiberglass Planters-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 | CSl-33 (Utilities) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
81 | Sanitary Sewerage-Allowance |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
82 | Stormwater Utilities-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
83 | Electrical Utilities-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
84 | GC Fee |  | 806320.04 | 0 | 0 | 806320.04 | 806320.04 | 0 | 0
85 | Contractor's Contingency |  | 689162.43 | 0 | 0 | 689162.43 | 689162.43 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
| TOTAL |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0

## Draw #6
GENESIS CAPITAL DRAW FORM
| CLIENT: | FCM Investments | [5 empty] | TOTAL COMPLETED TO DATE: | 0 | #REF!
| DATE: | 2025-08-19 | [5 empty] | REMAINING $ IN BUDGET: | #REF!
| PROJECT: | 12750 Moorpark Street | [5 empty] | ORIGINAL SCHEDULE OF VALUES: | #REF!
| DRAW REQUEST: | 0 | [5 empty] | CHANGE ORDERS: | 0
[8 empty] | REVISED SCHEDULE OF VALUES: | #REF!
| DESCRIPTION OF WORK |  | SCHEDULED VALUES | PREVIOUS | + / - CHANGES | REVISED VALUES | REMAINING | DRAW | COMPLETED AND
|  |  |  | CHANGES |  |  | BUDGET | 6 | STORED TO DATE
1 | Architect |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
2 | Surveying |  | 25000 | 0 | 0 | 25000 | 25000 | 0 | 0
3 | Soil Engineer |  | 30000 | 0 | 0 | 30000 | 30000 | 0 | 0
4 | Plan Check Fees |  | 30000 | 0 | 0 | 30000 | 30000 | 0 | 0
6 | Utility Setup Fees |  | 75000 | 0 | 0 | 75000 | 75000 | 0 | 0
7 | Deputy Inspections |  | 35 | 0 | 0 | 35 | 35 | 0 | 0
8 | Admin & Legal |  | 25000 | 0 | 0 | 25000 | 25000 | 0 | 0
9 | Structural Engineer |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
10 | Civil Engineer |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
12 | Landscape Architect |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
13 | MEP Engineer |  | 20000 | 0 | 0 | 20000 | 20000 | 0 | 0
14 | Quimby Fee |  | 382500 | 0 | 0 | 382500 | 382500 | 0 | 0
15 | Tenant Buyouts |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Impact Fees |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Insurance (builders risk) |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
18 | Development Fee |  | 7000 | 0 | 0 | 7000 | 7000 | 0 | 0
19 | General Conditions - Manpower (Allowance) |  | 592020.54 | 0 | 0 | 592020.54 | 592020.54 | 0 | 0
20 | Demolition |  | 79500 | 0 | 0 | 79500 | 79500 | 0 | 0
21 | Land Surveyor-Allowance |  | 11000 | 0 | 0 | 11000 | 11000 | 0 | 0
22 | Structural Concrete |  | 327470 | 0 | 0 | 327470 | 327470 | 0 | 0
23 | Spoils removal-Allowance |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
24 | Lightweight Concrete |  | 60042 | 0 | 0 | 60042 | 60042 | 0 | 0
25 | Concrete Masonry Unit (CMU) |  | 143700 | 0 | 0 | 143700 | 143700 | 0 | 0
26 | Stone Facing - Brick Veneer |  | 13055 | 0 | 0 | 13055 | 13055 | 0 | 0
27 | Structural Steel Fabricator Contractor |  | 33988.02 | 0 | 0 | 33988.02 | 33988.02 | 0 | 0
28 | Elevator Steel - Allowance |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
29 | Decorative Metals-Allowance |  | 75000 | 0 | 0 | 75000 | 75000 | 0 | 0
30 | Glass Railing-Allowance |  | 35000 | 0 | 0 | 35000 | 35000 | 0 | 0
31 | Rough Carpentry - Material & Labor |  | 970000 | 0 | 0 | 970000 | 970000 | 0 | 0
32 | EBM System-Allowance |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
33 | Below Grade Water Proofing |  | 7600 | 0 | 0 | 7600 | 7600 | 0 | 0
34 | Above Grade Water Proofing |  | 46600 | 0 | 0 | 46600 | 46600 | 0 | 0
35 | Thermal Insulation |  | 58250 | 0 | 0 | 58250 | 58250 | 0 | 0
36 | Roofing |  | 74200 | 0 | 0 | 74200 | 74200 | 0 | 0
37 | Sheet Metal Contractor-Allowance |  | 70000 | 0 | 0 | 70000 | 70000 | 0 | 0
38 | Firestopping-Allowance |  | 3000 | 0 | 0 | 3000 | 3000 | 0 | 0
39 | Joint Sealants-Allowance |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
40 | Doors and Frames |  | 182256 | 0 | 0 | 182256 | 182256 | 0 | 0
41 | Windows - Material |  | 81726.81 | 0 | 0 | 81726.81 | 81726.81 | 0 | 0
42 | Windows - Installation |  | 25900 | 0 | 0 | 25900 | 25900 | 0 | 0
43 | Entrances, Storefronts, and Curtain Walls |  | 8755 | 0 | 0 | 8755 | 8755 | 0 | 0
44 | Drywall and metal stud framing |  | 437990 | 0 | 0 | 437990 | 437990 | 0 | 0
45 | Painting and Coating |  | 130000 | 0 | 0 | 130000 | 130000 | 0 | 0
46 | Flooring |  | 118463 | 0 | 0 | 118463 | 118463 | 0 | 0
47 | Cement Plastering - Stucco-Allowance |  | 275000 | 0 | 0 | 275000 | 275000 | 0 | 0
48 | Scaffolding-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | Signages |  | 11972.11 | 0 | 0 | 11972.11 | 11972.11 | 0 | 0
50 | Bathroom Accesories |  | 13056 | 0 | 0 | 13056 | 13056 | 0 | 0
51 | Fire extinguishers-allowance |  | 10840 | 0 | 0 | 10840 | 10840 | 0 | 0
52 | #REF! |  | 3000 | 0 | 0 | 3000 | 3000 | 0 | 0
53 | Mailboxes |  | 14136 | 0 | 0 | 14136 | 14136 | 0 | 0
54 | Appliances - Material & Installation |  | 129875.28 | 0 | 0 | 129875.28 | 129875.28 | 0 | 0
55 | Countertops-AIIowance |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
56 | Cabinetry-Allowance |  | 103000 | 0 | 0 | 103000 | 103000 | 0 | 0
57 | Elevators |  | 150000 | 0 | 0 | 150000 | 150000 | 0 | 0
58 | Trash Chutes |  | 37409 | 0 | 0 | 37409 | 37409 | 0 | 0
59 | Fire Sprinklers |  | 187300 | 0 | 0 | 187300 | 187300 | 0 | 0
60 | Plumbing- Rough-Allowance |  | 800000 | 0 | 0 | 800000 | 800000 | 0 | 0
62 | Water Submeter-aIIowanee |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
63 | HVAC equipment & Ducting |  | 394800 | 0 | 0 | 394800 | 394800 | 0 | 0
64 | Electrical rough and finish-Allowance |  | 575000 | 0 | 0 | 575000 | 575000 | 0 | 0
66 | Low Voltage- Structured Cabling |  | 32000 | 0 | 0 | 32000 | 32000 | 0 | 0
67 | 2-way communication system (AOR) |  | 19000 | 0 | 0 | 19000 | 19000 | 0 | 0
68 | ERRCS / DAS system |  | 51000 | 0 | 0 | 51000 | 51000 | 0 | 0
69 | Access Control/Main Telephone Entry/Door Chimes-Allowance |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
70 | Fire Detection and Alarm |  | 47250 | 0 | 0 | 47250 | 47250 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
71 | Excavation and Fill |  | 57350 | 0 | 0 | 57350 | 57350 | 0 | 0
72 | Fine Grading-Allowance |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
73 | Site concrete, Site walkways Site Stairs |  | 10500 | 0 | 0 | 10500 | 10500 | 0 | 0
74 | Offsite Concrete-Allowance |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
75 | Striping-Allowance |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
76 | Permeable Pavers |  | 28619.55 | 0 | 0 | 28619.55 | 28619.55 | 0 | 0
77 | Irrigation system-Allowance |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
78 | Planting - Landscaping-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
79 | Fiberglass Planters-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 | CSl-33 (Utilities) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
81 | Sanitary Sewerage-Allowance |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
82 | Stormwater Utilities-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
83 | Electrical Utilities-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
84 | GC Fee |  | 806320.04 | 0 | 0 | 806320.04 | 806320.04 | 0 | 0
85 | Contractor's Contingency |  | 689162.43 | 0 | 0 | 689162.43 | 689162.43 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
| TOTAL |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0

## Draw #7
GENESIS CAPITAL DRAW FORM
| CLIENT: | FCM Investments | [5 empty] | TOTAL COMPLETED TO DATE: | 0 | #REF!
| DATE: | 2025-08-19 | [5 empty] | REMAINING $ IN BUDGET: | #REF!
| PROJECT: | 12750 Moorpark Street | [5 empty] | ORIGINAL SCHEDULE OF VALUES: | #REF!
| DRAW REQUEST: | 0 | [5 empty] | CHANGE ORDERS: | 0
[8 empty] | REVISED SCHEDULE OF VALUES: | #REF!
| DESCRIPTION OF WORK |  | SCHEDULED VALUES | PREVIOUS | + / - CHANGES | REVISED VALUES | REMAINING | DRAW | COMPLETED AND
|  |  |  | CHANGES |  |  | BUDGET | 7 | STORED TO DATE
1 | Architect |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
2 | Surveying |  | 25000 | 0 | 0 | 25000 | 25000 | 0 | 0
3 | Soil Engineer |  | 30000 | 0 | 0 | 30000 | 30000 | 0 | 0
4 | Plan Check Fees |  | 30000 | 0 | 0 | 30000 | 30000 | 0 | 0
6 | Utility Setup Fees |  | 75000 | 0 | 0 | 75000 | 75000 | 0 | 0
7 | Deputy Inspections |  | 35 | 0 | 0 | 35 | 35 | 0 | 0
8 | Admin & Legal |  | 25000 | 0 | 0 | 25000 | 25000 | 0 | 0
9 | Structural Engineer |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
10 | Civil Engineer |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
12 | Landscape Architect |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
13 | MEP Engineer |  | 20000 | 0 | 0 | 20000 | 20000 | 0 | 0
14 | Quimby Fee |  | 382500 | 0 | 0 | 382500 | 382500 | 0 | 0
15 | Tenant Buyouts |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Impact Fees |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Insurance (builders risk) |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
18 | Development Fee |  | 7000 | 0 | 0 | 7000 | 7000 | 0 | 0
19 | General Conditions - Manpower (Allowance) |  | 592020.54 | 0 | 0 | 592020.54 | 592020.54 | 0 | 0
20 | Demolition |  | 79500 | 0 | 0 | 79500 | 79500 | 0 | 0
21 | Land Surveyor-Allowance |  | 11000 | 0 | 0 | 11000 | 11000 | 0 | 0
22 | Structural Concrete |  | 327470 | 0 | 0 | 327470 | 327470 | 0 | 0
23 | Spoils removal-Allowance |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
24 | Lightweight Concrete |  | 60042 | 0 | 0 | 60042 | 60042 | 0 | 0
25 | Concrete Masonry Unit (CMU) |  | 143700 | 0 | 0 | 143700 | 143700 | 0 | 0
26 | Stone Facing - Brick Veneer |  | 13055 | 0 | 0 | 13055 | 13055 | 0 | 0
27 | Structural Steel Fabricator Contractor |  | 33988.02 | 0 | 0 | 33988.02 | 33988.02 | 0 | 0
28 | Elevator Steel - Allowance |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
29 | Decorative Metals-Allowance |  | 75000 | 0 | 0 | 75000 | 75000 | 0 | 0
30 | Glass Railing-Allowance |  | 35000 | 0 | 0 | 35000 | 35000 | 0 | 0
31 | Rough Carpentry - Material & Labor |  | 970000 | 0 | 0 | 970000 | 970000 | 0 | 0
32 | EBM System-Allowance |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
33 | Below Grade Water Proofing |  | 7600 | 0 | 0 | 7600 | 7600 | 0 | 0
34 | Above Grade Water Proofing |  | 46600 | 0 | 0 | 46600 | 46600 | 0 | 0
35 | Thermal Insulation |  | 58250 | 0 | 0 | 58250 | 58250 | 0 | 0
36 | Roofing |  | 74200 | 0 | 0 | 74200 | 74200 | 0 | 0
37 | Sheet Metal Contractor-Allowance |  | 70000 | 0 | 0 | 70000 | 70000 | 0 | 0
38 | Firestopping-Allowance |  | 3000 | 0 | 0 | 3000 | 3000 | 0 | 0
39 | Joint Sealants-Allowance |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
40 | Doors and Frames |  | 182256 | 0 | 0 | 182256 | 182256 | 0 | 0
41 | Windows - Material |  | 81726.81 | 0 | 0 | 81726.81 | 81726.81 | 0 | 0
42 | Windows - Installation |  | 25900 | 0 | 0 | 25900 | 25900 | 0 | 0
43 | Entrances, Storefronts, and Curtain Walls |  | 8755 | 0 | 0 | 8755 | 8755 | 0 | 0
44 | Drywall and metal stud framing |  | 437990 | 0 | 0 | 437990 | 437990 | 0 | 0
45 | Painting and Coating |  | 130000 | 0 | 0 | 130000 | 130000 | 0 | 0
46 | Flooring |  | 118463 | 0 | 0 | 118463 | 118463 | 0 | 0
47 | Cement Plastering - Stucco-Allowance |  | 275000 | 0 | 0 | 275000 | 275000 | 0 | 0
48 | Scaffolding-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | Signages |  | 11972.11 | 0 | 0 | 11972.11 | 11972.11 | 0 | 0
50 | Bathroom Accesories |  | 13056 | 0 | 0 | 13056 | 13056 | 0 | 0
51 | Fire extinguishers-allowance |  | 10840 | 0 | 0 | 10840 | 10840 | 0 | 0
52 | #REF! |  | 3000 | 0 | 0 | 3000 | 3000 | 0 | 0
53 | Mailboxes |  | 14136 | 0 | 0 | 14136 | 14136 | 0 | 0
54 | Appliances - Material & Installation |  | 129875.28 | 0 | 0 | 129875.28 | 129875.28 | 0 | 0
55 | Countertops-AIIowance |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
56 | Cabinetry-Allowance |  | 103000 | 0 | 0 | 103000 | 103000 | 0 | 0
57 | Elevators |  | 150000 | 0 | 0 | 150000 | 150000 | 0 | 0
58 | Trash Chutes |  | 37409 | 0 | 0 | 37409 | 37409 | 0 | 0
59 | Fire Sprinklers |  | 187300 | 0 | 0 | 187300 | 187300 | 0 | 0
60 | Plumbing- Rough-Allowance |  | 800000 | 0 | 0 | 800000 | 800000 | 0 | 0
62 | Water Submeter-aIIowanee |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
63 | HVAC equipment & Ducting |  | 394800 | 0 | 0 | 394800 | 394800 | 0 | 0
64 | Electrical rough and finish-Allowance |  | 575000 | 0 | 0 | 575000 | 575000 | 0 | 0
66 | Low Voltage- Structured Cabling |  | 32000 | 0 | 0 | 32000 | 32000 | 0 | 0
67 | 2-way communication system (AOR) |  | 19000 | 0 | 0 | 19000 | 19000 | 0 | 0
68 | ERRCS / DAS system |  | 51000 | 0 | 0 | 51000 | 51000 | 0 | 0
69 | Access Control/Main Telephone Entry/Door Chimes-Allowance |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
70 | Fire Detection and Alarm |  | 47250 | 0 | 0 | 47250 | 47250 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
71 | Excavation and Fill |  | 57350 | 0 | 0 | 57350 | 57350 | 0 | 0
72 | Fine Grading-Allowance |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
73 | Site concrete, Site walkways Site Stairs |  | 10500 | 0 | 0 | 10500 | 10500 | 0 | 0
74 | Offsite Concrete-Allowance |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
75 | Striping-Allowance |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
76 | Permeable Pavers |  | 28619.55 | 0 | 0 | 28619.55 | 28619.55 | 0 | 0
77 | Irrigation system-Allowance |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
78 | Planting - Landscaping-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
79 | Fiberglass Planters-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 | CSl-33 (Utilities) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
81 | Sanitary Sewerage-Allowance |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
82 | Stormwater Utilities-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
83 | Electrical Utilities-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
84 | GC Fee |  | 806320.04 | 0 | 0 | 806320.04 | 806320.04 | 0 | 0
85 | Contractor's Contingency |  | 689162.43 | 0 | 0 | 689162.43 | 689162.43 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
| TOTAL |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0

## Draw #8
GENESIS CAPITAL DRAW FORM
| CLIENT: | FCM Investments | [5 empty] | TOTAL COMPLETED TO DATE: | 0 | #REF!
| DATE: | 2025-08-19 | [5 empty] | REMAINING $ IN BUDGET: | #REF!
| PROJECT: | 12750 Moorpark Street | [5 empty] | ORIGINAL SCHEDULE OF VALUES: | #REF!
| DRAW REQUEST: | 0 | [5 empty] | CHANGE ORDERS: | 0
[8 empty] | REVISED SCHEDULE OF VALUES: | #REF!
| DESCRIPTION OF WORK |  | SCHEDULED VALUES | PREVIOUS | + / - CHANGES | REVISED VALUES | REMAINING | DRAW | COMPLETED AND
|  |  |  | CHANGES |  |  | BUDGET | 8 | STORED TO DATE
1 | Architect |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
2 | Surveying |  | 25000 | 0 | 0 | 25000 | 25000 | 0 | 0
3 | Soil Engineer |  | 30000 | 0 | 0 | 30000 | 30000 | 0 | 0
4 | Plan Check Fees |  | 30000 | 0 | 0 | 30000 | 30000 | 0 | 0
6 | Utility Setup Fees |  | 75000 | 0 | 0 | 75000 | 75000 | 0 | 0
7 | Deputy Inspections |  | 35 | 0 | 0 | 35 | 35 | 0 | 0
8 | Admin & Legal |  | 25000 | 0 | 0 | 25000 | 25000 | 0 | 0
9 | Structural Engineer |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
10 | Civil Engineer |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
12 | Landscape Architect |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
13 | MEP Engineer |  | 20000 | 0 | 0 | 20000 | 20000 | 0 | 0
14 | Quimby Fee |  | 382500 | 0 | 0 | 382500 | 382500 | 0 | 0
15 | Tenant Buyouts |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Impact Fees |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Insurance (builders risk) |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
18 | Development Fee |  | 7000 | 0 | 0 | 7000 | 7000 | 0 | 0
19 | General Conditions - Manpower (Allowance) |  | 592020.54 | 0 | 0 | 592020.54 | 592020.54 | 0 | 0
20 | Demolition |  | 79500 | 0 | 0 | 79500 | 79500 | 0 | 0
21 | Land Surveyor-Allowance |  | 11000 | 0 | 0 | 11000 | 11000 | 0 | 0
22 | Structural Concrete |  | 327470 | 0 | 0 | 327470 | 327470 | 0 | 0
23 | Spoils removal-Allowance |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
24 | Lightweight Concrete |  | 60042 | 0 | 0 | 60042 | 60042 | 0 | 0
25 | Concrete Masonry Unit (CMU) |  | 143700 | 0 | 0 | 143700 | 143700 | 0 | 0
26 | Stone Facing - Brick Veneer |  | 13055 | 0 | 0 | 13055 | 13055 | 0 | 0
27 | Structural Steel Fabricator Contractor |  | 33988.02 | 0 | 0 | 33988.02 | 33988.02 | 0 | 0
28 | Elevator Steel - Allowance |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
29 | Decorative Metals-Allowance |  | 75000 | 0 | 0 | 75000 | 75000 | 0 | 0
30 | Glass Railing-Allowance |  | 35000 | 0 | 0 | 35000 | 35000 | 0 | 0
31 | Rough Carpentry - Material & Labor |  | 970000 | 0 | 0 | 970000 | 970000 | 0 | 0
32 | EBM System-Allowance |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
33 | Below Grade Water Proofing |  | 7600 | 0 | 0 | 7600 | 7600 | 0 | 0
34 | Above Grade Water Proofing |  | 46600 | 0 | 0 | 46600 | 46600 | 0 | 0
35 | Thermal Insulation |  | 58250 | 0 | 0 | 58250 | 58250 | 0 | 0
36 | Roofing |  | 74200 | 0 | 0 | 74200 | 74200 | 0 | 0
37 | Sheet Metal Contractor-Allowance |  | 70000 | 0 | 0 | 70000 | 70000 | 0 | 0
38 | Firestopping-Allowance |  | 3000 | 0 | 0 | 3000 | 3000 | 0 | 0
39 | Joint Sealants-Allowance |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
40 | Doors and Frames |  | 182256 | 0 | 0 | 182256 | 182256 | 0 | 0
41 | Windows - Material |  | 81726.81 | 0 | 0 | 81726.81 | 81726.81 | 0 | 0
42 | Windows - Installation |  | 25900 | 0 | 0 | 25900 | 25900 | 0 | 0
43 | Entrances, Storefronts, and Curtain Walls |  | 8755 | 0 | 0 | 8755 | 8755 | 0 | 0
44 | Drywall and metal stud framing |  | 437990 | 0 | 0 | 437990 | 437990 | 0 | 0
45 | Painting and Coating |  | 130000 | 0 | 0 | 130000 | 130000 | 0 | 0
46 | Flooring |  | 118463 | 0 | 0 | 118463 | 118463 | 0 | 0
47 | Cement Plastering - Stucco-Allowance |  | 275000 | 0 | 0 | 275000 | 275000 | 0 | 0
48 | Scaffolding-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | Signages |  | 11972.11 | 0 | 0 | 11972.11 | 11972.11 | 0 | 0
50 | Bathroom Accesories |  | 13056 | 0 | 0 | 13056 | 13056 | 0 | 0
51 | Fire extinguishers-allowance |  | 10840 | 0 | 0 | 10840 | 10840 | 0 | 0
52 | #REF! |  | 3000 | 0 | 0 | 3000 | 3000 | 0 | 0
53 | Mailboxes |  | 14136 | 0 | 0 | 14136 | 14136 | 0 | 0
54 | Appliances - Material & Installation |  | 129875.28 | 0 | 0 | 129875.28 | 129875.28 | 0 | 0
55 | Countertops-AIIowance |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
56 | Cabinetry-Allowance |  | 103000 | 0 | 0 | 103000 | 103000 | 0 | 0
57 | Elevators |  | 150000 | 0 | 0 | 150000 | 150000 | 0 | 0
58 | Trash Chutes |  | 37409 | 0 | 0 | 37409 | 37409 | 0 | 0
59 | Fire Sprinklers |  | 187300 | 0 | 0 | 187300 | 187300 | 0 | 0
60 | Plumbing- Rough-Allowance |  | 800000 | 0 | 0 | 800000 | 800000 | 0 | 0
62 | Water Submeter-aIIowanee |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
63 | HVAC equipment & Ducting |  | 394800 | 0 | 0 | 394800 | 394800 | 0 | 0
64 | Electrical rough and finish-Allowance |  | 575000 | 0 | 0 | 575000 | 575000 | 0 | 0
66 | Low Voltage- Structured Cabling |  | 32000 | 0 | 0 | 32000 | 32000 | 0 | 0
67 | 2-way communication system (AOR) |  | 19000 | 0 | 0 | 19000 | 19000 | 0 | 0
68 | ERRCS / DAS system |  | 51000 | 0 | 0 | 51000 | 51000 | 0 | 0
69 | Access Control/Main Telephone Entry/Door Chimes-Allowance |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
70 | Fire Detection and Alarm |  | 47250 | 0 | 0 | 47250 | 47250 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
71 | Excavation and Fill |  | 57350 | 0 | 0 | 57350 | 57350 | 0 | 0
72 | Fine Grading-Allowance |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
73 | Site concrete, Site walkways Site Stairs |  | 10500 | 0 | 0 | 10500 | 10500 | 0 | 0
74 | Offsite Concrete-Allowance |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
75 | Striping-Allowance |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
76 | Permeable Pavers |  | 28619.55 | 0 | 0 | 28619.55 | 28619.55 | 0 | 0
77 | Irrigation system-Allowance |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
78 | Planting - Landscaping-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
79 | Fiberglass Planters-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 | CSl-33 (Utilities) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
81 | Sanitary Sewerage-Allowance |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
82 | Stormwater Utilities-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
83 | Electrical Utilities-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
84 | GC Fee |  | 806320.04 | 0 | 0 | 806320.04 | 806320.04 | 0 | 0
85 | Contractor's Contingency |  | 689162.43 | 0 | 0 | 689162.43 | 689162.43 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
| TOTAL |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0

## Draw #9
GENESIS CAPITAL DRAW FORM
| CLIENT: | FCM Investments | [5 empty] | TOTAL COMPLETED TO DATE: | 0 | #REF!
| DATE: | 2025-08-19 | [5 empty] | REMAINING $ IN BUDGET: | #REF!
| PROJECT: | 12750 Moorpark Street | [5 empty] | ORIGINAL SCHEDULE OF VALUES: | #REF!
| DRAW REQUEST: | 0 | [5 empty] | CHANGE ORDERS: | 0
[8 empty] | REVISED SCHEDULE OF VALUES: | #REF!
| DESCRIPTION OF WORK |  | SCHEDULED VALUES | PREVIOUS | + / - CHANGES | REVISED VALUES | REMAINING | DRAW | COMPLETED AND
|  |  |  | CHANGES |  |  | BUDGET | 9 | STORED TO DATE
1 | Architect |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
2 | Surveying |  | 25000 | 0 | 0 | 25000 | 25000 | 0 | 0
3 | Soil Engineer |  | 30000 | 0 | 0 | 30000 | 30000 | 0 | 0
4 | Plan Check Fees |  | 30000 | 0 | 0 | 30000 | 30000 | 0 | 0
6 | Utility Setup Fees |  | 75000 | 0 | 0 | 75000 | 75000 | 0 | 0
7 | Deputy Inspections |  | 35 | 0 | 0 | 35 | 35 | 0 | 0
8 | Admin & Legal |  | 25000 | 0 | 0 | 25000 | 25000 | 0 | 0
9 | Structural Engineer |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
10 | Civil Engineer |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
12 | Landscape Architect |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
13 | MEP Engineer |  | 20000 | 0 | 0 | 20000 | 20000 | 0 | 0
14 | Quimby Fee |  | 382500 | 0 | 0 | 382500 | 382500 | 0 | 0
15 | Tenant Buyouts |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Impact Fees |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Insurance (builders risk) |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
18 | Development Fee |  | 7000 | 0 | 0 | 7000 | 7000 | 0 | 0
19 | General Conditions - Manpower (Allowance) |  | 592020.54 | 0 | 0 | 592020.54 | 592020.54 | 0 | 0
20 | Demolition |  | 79500 | 0 | 0 | 79500 | 79500 | 0 | 0
21 | Land Surveyor-Allowance |  | 11000 | 0 | 0 | 11000 | 11000 | 0 | 0
22 | Structural Concrete |  | 327470 | 0 | 0 | 327470 | 327470 | 0 | 0
23 | Spoils removal-Allowance |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
24 | Lightweight Concrete |  | 60042 | 0 | 0 | 60042 | 60042 | 0 | 0
25 | Concrete Masonry Unit (CMU) |  | 143700 | 0 | 0 | 143700 | 143700 | 0 | 0
26 | Stone Facing - Brick Veneer |  | 13055 | 0 | 0 | 13055 | 13055 | 0 | 0
27 | Structural Steel Fabricator Contractor |  | 33988.02 | 0 | 0 | 33988.02 | 33988.02 | 0 | 0
28 | Elevator Steel - Allowance |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
29 | Decorative Metals-Allowance |  | 75000 | 0 | 0 | 75000 | 75000 | 0 | 0
30 | Glass Railing-Allowance |  | 35000 | 0 | 0 | 35000 | 35000 | 0 | 0
31 | Rough Carpentry - Material & Labor |  | 970000 | 0 | 0 | 970000 | 970000 | 0 | 0
32 | EBM System-Allowance |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
33 | Below Grade Water Proofing |  | 7600 | 0 | 0 | 7600 | 7600 | 0 | 0
34 | Above Grade Water Proofing |  | 46600 | 0 | 0 | 46600 | 46600 | 0 | 0
35 | Thermal Insulation |  | 58250 | 0 | 0 | 58250 | 58250 | 0 | 0
36 | Roofing |  | 74200 | 0 | 0 | 74200 | 74200 | 0 | 0
37 | Sheet Metal Contractor-Allowance |  | 70000 | 0 | 0 | 70000 | 70000 | 0 | 0
38 | Firestopping-Allowance |  | 3000 | 0 | 0 | 3000 | 3000 | 0 | 0
39 | Joint Sealants-Allowance |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
40 | Doors and Frames |  | 182256 | 0 | 0 | 182256 | 182256 | 0 | 0
41 | Windows - Material |  | 81726.81 | 0 | 0 | 81726.81 | 81726.81 | 0 | 0
42 | Windows - Installation |  | 25900 | 0 | 0 | 25900 | 25900 | 0 | 0
43 | Entrances, Storefronts, and Curtain Walls |  | 8755 | 0 | 0 | 8755 | 8755 | 0 | 0
44 | Drywall and metal stud framing |  | 437990 | 0 | 0 | 437990 | 437990 | 0 | 0
45 | Painting and Coating |  | 130000 | 0 | 0 | 130000 | 130000 | 0 | 0
46 | Flooring |  | 118463 | 0 | 0 | 118463 | 118463 | 0 | 0
47 | Cement Plastering - Stucco-Allowance |  | 275000 | 0 | 0 | 275000 | 275000 | 0 | 0
48 | Scaffolding-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | Signages |  | 11972.11 | 0 | 0 | 11972.11 | 11972.11 | 0 | 0
50 | Bathroom Accesories |  | 13056 | 0 | 0 | 13056 | 13056 | 0 | 0
51 | Fire extinguishers-allowance |  | 10840 | 0 | 0 | 10840 | 10840 | 0 | 0
52 | #REF! |  | 3000 | 0 | 0 | 3000 | 3000 | 0 | 0
53 | Mailboxes |  | 14136 | 0 | 0 | 14136 | 14136 | 0 | 0
54 | Appliances - Material & Installation |  | 129875.28 | 0 | 0 | 129875.28 | 129875.28 | 0 | 0
55 | Countertops-AIIowance |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
56 | Cabinetry-Allowance |  | 103000 | 0 | 0 | 103000 | 103000 | 0 | 0
57 | Elevators |  | 150000 | 0 | 0 | 150000 | 150000 | 0 | 0
58 | Trash Chutes |  | 37409 | 0 | 0 | 37409 | 37409 | 0 | 0
59 | Fire Sprinklers |  | 187300 | 0 | 0 | 187300 | 187300 | 0 | 0
60 | Plumbing- Rough-Allowance |  | 800000 | 0 | 0 | 800000 | 800000 | 0 | 0
62 | Water Submeter-aIIowanee |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
63 | HVAC equipment & Ducting |  | 394800 | 0 | 0 | 394800 | 394800 | 0 | 0
64 | Electrical rough and finish-Allowance |  | 575000 | 0 | 0 | 575000 | 575000 | 0 | 0
66 | Low Voltage- Structured Cabling |  | 32000 | 0 | 0 | 32000 | 32000 | 0 | 0
67 | 2-way communication system (AOR) |  | 19000 | 0 | 0 | 19000 | 19000 | 0 | 0
68 | ERRCS / DAS system |  | 51000 | 0 | 0 | 51000 | 51000 | 0 | 0
69 | Access Control/Main Telephone Entry/Door Chimes-Allowance |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
70 | Fire Detection and Alarm |  | 47250 | 0 | 0 | 47250 | 47250 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
71 | Excavation and Fill |  | 57350 | 0 | 0 | 57350 | 57350 | 0 | 0
72 | Fine Grading-Allowance |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
73 | Site concrete, Site walkways Site Stairs |  | 10500 | 0 | 0 | 10500 | 10500 | 0 | 0
74 | Offsite Concrete-Allowance |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
75 | Striping-Allowance |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
76 | Permeable Pavers |  | 28619.55 | 0 | 0 | 28619.55 | 28619.55 | 0 | 0
77 | Irrigation system-Allowance |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
78 | Planting - Landscaping-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
79 | Fiberglass Planters-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 | CSl-33 (Utilities) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
81 | Sanitary Sewerage-Allowance |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
82 | Stormwater Utilities-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
83 | Electrical Utilities-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
84 | GC Fee |  | 806320.04 | 0 | 0 | 806320.04 | 806320.04 | 0 | 0
85 | Contractor's Contingency |  | 689162.43 | 0 | 0 | 689162.43 | 689162.43 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
| TOTAL |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0

## Draw #10
GENESIS CAPITAL DRAW FORM
| CLIENT: | FCM Investments | [5 empty] | TOTAL COMPLETED TO DATE: | 0 | #REF!
| DATE: | 2025-08-19 | [5 empty] | REMAINING $ IN BUDGET: | #REF!
| PROJECT: | 12750 Moorpark Street | [5 empty] | ORIGINAL SCHEDULE OF VALUES: | #REF!
| DRAW REQUEST: | 0 | [5 empty] | CHANGE ORDERS: | 0
[8 empty] | REVISED SCHEDULE OF VALUES: | #REF!
| DESCRIPTION OF WORK |  | SCHEDULED VALUES | PREVIOUS | + / - CHANGES | REVISED VALUES | REMAINING | DRAW | COMPLETED AND
|  |  |  | CHANGES |  |  | BUDGET | 10 | STORED TO DATE
1 | Architect |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
2 | Surveying |  | 25000 | 0 | 0 | 25000 | 25000 | 0 | 0
3 | Soil Engineer |  | 30000 | 0 | 0 | 30000 | 30000 | 0 | 0
4 | Plan Check Fees |  | 30000 | 0 | 0 | 30000 | 30000 | 0 | 0
6 | Utility Setup Fees |  | 75000 | 0 | 0 | 75000 | 75000 | 0 | 0
7 | Deputy Inspections |  | 35 | 0 | 0 | 35 | 35 | 0 | 0
8 | Admin & Legal |  | 25000 | 0 | 0 | 25000 | 25000 | 0 | 0
9 | Structural Engineer |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
10 | Civil Engineer |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
12 | Landscape Architect |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
13 | MEP Engineer |  | 20000 | 0 | 0 | 20000 | 20000 | 0 | 0
14 | Quimby Fee |  | 382500 | 0 | 0 | 382500 | 382500 | 0 | 0
15 | Tenant Buyouts |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Impact Fees |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Insurance (builders risk) |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
18 | Development Fee |  | 7000 | 0 | 0 | 7000 | 7000 | 0 | 0
19 | General Conditions - Manpower (Allowance) |  | 592020.54 | 0 | 0 | 592020.54 | 592020.54 | 0 | 0
20 | Demolition |  | 79500 | 0 | 0 | 79500 | 79500 | 0 | 0
21 | Land Surveyor-Allowance |  | 11000 | 0 | 0 | 11000 | 11000 | 0 | 0
22 | Structural Concrete |  | 327470 | 0 | 0 | 327470 | 327470 | 0 | 0
23 | Spoils removal-Allowance |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
24 | Lightweight Concrete |  | 60042 | 0 | 0 | 60042 | 60042 | 0 | 0
25 | Concrete Masonry Unit (CMU) |  | 143700 | 0 | 0 | 143700 | 143700 | 0 | 0
26 | Stone Facing - Brick Veneer |  | 13055 | 0 | 0 | 13055 | 13055 | 0 | 0
27 | Structural Steel Fabricator Contractor |  | 33988.02 | 0 | 0 | 33988.02 | 33988.02 | 0 | 0
28 | Elevator Steel - Allowance |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
29 | Decorative Metals-Allowance |  | 75000 | 0 | 0 | 75000 | 75000 | 0 | 0
30 | Glass Railing-Allowance |  | 35000 | 0 | 0 | 35000 | 35000 | 0 | 0
31 | Rough Carpentry - Material & Labor |  | 970000 | 0 | 0 | 970000 | 970000 | 0 | 0
32 | EBM System-Allowance |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
33 | Below Grade Water Proofing |  | 7600 | 0 | 0 | 7600 | 7600 | 0 | 0
34 | Above Grade Water Proofing |  | 46600 | 0 | 0 | 46600 | 46600 | 0 | 0
35 | Thermal Insulation |  | 58250 | 0 | 0 | 58250 | 58250 | 0 | 0
36 | Roofing |  | 74200 | 0 | 0 | 74200 | 74200 | 0 | 0
37 | Sheet Metal Contractor-Allowance |  | 70000 | 0 | 0 | 70000 | 70000 | 0 | 0
38 | Firestopping-Allowance |  | 3000 | 0 | 0 | 3000 | 3000 | 0 | 0
39 | Joint Sealants-Allowance |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
40 | Doors and Frames |  | 182256 | 0 | 0 | 182256 | 182256 | 0 | 0
41 | Windows - Material |  | 81726.81 | 0 | 0 | 81726.81 | 81726.81 | 0 | 0
42 | Windows - Installation |  | 25900 | 0 | 0 | 25900 | 25900 | 0 | 0
43 | Entrances, Storefronts, and Curtain Walls |  | 8755 | 0 | 0 | 8755 | 8755 | 0 | 0
44 | Drywall and metal stud framing |  | 437990 | 0 | 0 | 437990 | 437990 | 0 | 0
45 | Painting and Coating |  | 130000 | 0 | 0 | 130000 | 130000 | 0 | 0
46 | Flooring |  | 118463 | 0 | 0 | 118463 | 118463 | 0 | 0
47 | Cement Plastering - Stucco-Allowance |  | 275000 | 0 | 0 | 275000 | 275000 | 0 | 0
48 | Scaffolding-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | Signages |  | 11972.11 | 0 | 0 | 11972.11 | 11972.11 | 0 | 0
50 | Bathroom Accesories |  | 13056 | 0 | 0 | 13056 | 13056 | 0 | 0
51 | Fire extinguishers-allowance |  | 10840 | 0 | 0 | 10840 | 10840 | 0 | 0
52 | #REF! |  | 3000 | 0 | 0 | 3000 | 3000 | 0 | 0
53 | Mailboxes |  | 14136 | 0 | 0 | 14136 | 14136 | 0 | 0
54 | Appliances - Material & Installation |  | 129875.28 | 0 | 0 | 129875.28 | 129875.28 | 0 | 0
55 | Countertops-AIIowance |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
56 | Cabinetry-Allowance |  | 103000 | 0 | 0 | 103000 | 103000 | 0 | 0
57 | Elevators |  | 150000 | 0 | 0 | 150000 | 150000 | 0 | 0
58 | Trash Chutes |  | 37409 | 0 | 0 | 37409 | 37409 | 0 | 0
59 | Fire Sprinklers |  | 187300 | 0 | 0 | 187300 | 187300 | 0 | 0
60 | Plumbing- Rough-Allowance |  | 800000 | 0 | 0 | 800000 | 800000 | 0 | 0
62 | Water Submeter-aIIowanee |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
63 | HVAC equipment & Ducting |  | 394800 | 0 | 0 | 394800 | 394800 | 0 | 0
64 | Electrical rough and finish-Allowance |  | 575000 | 0 | 0 | 575000 | 575000 | 0 | 0
66 | Low Voltage- Structured Cabling |  | 32000 | 0 | 0 | 32000 | 32000 | 0 | 0
67 | 2-way communication system (AOR) |  | 19000 | 0 | 0 | 19000 | 19000 | 0 | 0
68 | ERRCS / DAS system |  | 51000 | 0 | 0 | 51000 | 51000 | 0 | 0
69 | Access Control/Main Telephone Entry/Door Chimes-Allowance |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
70 | Fire Detection and Alarm |  | 47250 | 0 | 0 | 47250 | 47250 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
71 | Excavation and Fill |  | 57350 | 0 | 0 | 57350 | 57350 | 0 | 0
72 | Fine Grading-Allowance |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
73 | Site concrete, Site walkways Site Stairs |  | 10500 | 0 | 0 | 10500 | 10500 | 0 | 0
74 | Offsite Concrete-Allowance |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
75 | Striping-Allowance |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
76 | Permeable Pavers |  | 28619.55 | 0 | 0 | 28619.55 | 28619.55 | 0 | 0
77 | Irrigation system-Allowance |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
78 | Planting - Landscaping-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
79 | Fiberglass Planters-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 | CSl-33 (Utilities) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
81 | Sanitary Sewerage-Allowance |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
82 | Stormwater Utilities-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
83 | Electrical Utilities-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
84 | GC Fee |  | 806320.04 | 0 | 0 | 806320.04 | 806320.04 | 0 | 0
85 | Contractor's Contingency |  | 689162.43 | 0 | 0 | 689162.43 | 689162.43 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
| TOTAL |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0

## Draw #11
GENESIS CAPITAL DRAW FORM
| CLIENT: | FCM Investments | [5 empty] | TOTAL COMPLETED TO DATE: | 0 | #REF!
| DATE: | 2025-08-19 | [5 empty] | REMAINING $ IN BUDGET: | #REF!
| PROJECT: | 12750 Moorpark Street | [5 empty] | ORIGINAL SCHEDULE OF VALUES: | #REF!
| DRAW REQUEST: | 0 | [5 empty] | CHANGE ORDERS: | 0
[8 empty] | REVISED SCHEDULE OF VALUES: | #REF!
| DESCRIPTION OF WORK |  | SCHEDULED VALUES | PREVIOUS | + / - CHANGES | REVISED VALUES | REMAINING | DRAW | COMPLETED AND
|  |  |  | CHANGES |  |  | BUDGET | 11 | STORED TO DATE
1 | Architect |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
2 | Surveying |  | 25000 | 0 | 0 | 25000 | 25000 | 0 | 0
3 | Soil Engineer |  | 30000 | 0 | 0 | 30000 | 30000 | 0 | 0
4 | Plan Check Fees |  | 30000 | 0 | 0 | 30000 | 30000 | 0 | 0
6 | Utility Setup Fees |  | 75000 | 0 | 0 | 75000 | 75000 | 0 | 0
7 | Deputy Inspections |  | 35 | 0 | 0 | 35 | 35 | 0 | 0
8 | Admin & Legal |  | 25000 | 0 | 0 | 25000 | 25000 | 0 | 0
9 | Structural Engineer |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
10 | Civil Engineer |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
12 | Landscape Architect |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
13 | MEP Engineer |  | 20000 | 0 | 0 | 20000 | 20000 | 0 | 0
14 | Quimby Fee |  | 382500 | 0 | 0 | 382500 | 382500 | 0 | 0
15 | Tenant Buyouts |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Impact Fees |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Insurance (builders risk) |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
18 | Development Fee |  | 7000 | 0 | 0 | 7000 | 7000 | 0 | 0
19 | General Conditions - Manpower (Allowance) |  | 592020.54 | 0 | 0 | 592020.54 | 592020.54 | 0 | 0
20 | Demolition |  | 79500 | 0 | 0 | 79500 | 79500 | 0 | 0
21 | Land Surveyor-Allowance |  | 11000 | 0 | 0 | 11000 | 11000 | 0 | 0
22 | Structural Concrete |  | 327470 | 0 | 0 | 327470 | 327470 | 0 | 0
23 | Spoils removal-Allowance |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
24 | Lightweight Concrete |  | 60042 | 0 | 0 | 60042 | 60042 | 0 | 0
25 | Concrete Masonry Unit (CMU) |  | 143700 | 0 | 0 | 143700 | 143700 | 0 | 0
26 | Stone Facing - Brick Veneer |  | 13055 | 0 | 0 | 13055 | 13055 | 0 | 0
27 | Structural Steel Fabricator Contractor |  | 33988.02 | 0 | 0 | 33988.02 | 33988.02 | 0 | 0
28 | Elevator Steel - Allowance |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
29 | Decorative Metals-Allowance |  | 75000 | 0 | 0 | 75000 | 75000 | 0 | 0
30 | Glass Railing-Allowance |  | 35000 | 0 | 0 | 35000 | 35000 | 0 | 0
31 | Rough Carpentry - Material & Labor |  | 970000 | 0 | 0 | 970000 | 970000 | 0 | 0
32 | EBM System-Allowance |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
33 | Below Grade Water Proofing |  | 7600 | 0 | 0 | 7600 | 7600 | 0 | 0
34 | Above Grade Water Proofing |  | 46600 | 0 | 0 | 46600 | 46600 | 0 | 0
35 | Thermal Insulation |  | 58250 | 0 | 0 | 58250 | 58250 | 0 | 0
36 | Roofing |  | 74200 | 0 | 0 | 74200 | 74200 | 0 | 0
37 | Sheet Metal Contractor-Allowance |  | 70000 | 0 | 0 | 70000 | 70000 | 0 | 0
38 | Firestopping-Allowance |  | 3000 | 0 | 0 | 3000 | 3000 | 0 | 0
39 | Joint Sealants-Allowance |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
40 | Doors and Frames |  | 182256 | 0 | 0 | 182256 | 182256 | 0 | 0
41 | Windows - Material |  | 81726.81 | 0 | 0 | 81726.81 | 81726.81 | 0 | 0
42 | Windows - Installation |  | 25900 | 0 | 0 | 25900 | 25900 | 0 | 0
43 | Entrances, Storefronts, and Curtain Walls |  | 8755 | 0 | 0 | 8755 | 8755 | 0 | 0
44 | Drywall and metal stud framing |  | 437990 | 0 | 0 | 437990 | 437990 | 0 | 0
45 | Painting and Coating |  | 130000 | 0 | 0 | 130000 | 130000 | 0 | 0
46 | Flooring |  | 118463 | 0 | 0 | 118463 | 118463 | 0 | 0
47 | Cement Plastering - Stucco-Allowance |  | 275000 | 0 | 0 | 275000 | 275000 | 0 | 0
48 | Scaffolding-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | Signages |  | 11972.11 | 0 | 0 | 11972.11 | 11972.11 | 0 | 0
50 | Bathroom Accesories |  | 13056 | 0 | 0 | 13056 | 13056 | 0 | 0
51 | Fire extinguishers-allowance |  | 10840 | 0 | 0 | 10840 | 10840 | 0 | 0
52 | #REF! |  | 3000 | 0 | 0 | 3000 | 3000 | 0 | 0
53 | Mailboxes |  | 14136 | 0 | 0 | 14136 | 14136 | 0 | 0
54 | Appliances - Material & Installation |  | 129875.28 | 0 | 0 | 129875.28 | 129875.28 | 0 | 0
55 | Countertops-AIIowance |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
56 | Cabinetry-Allowance |  | 103000 | 0 | 0 | 103000 | 103000 | 0 | 0
57 | Elevators |  | 150000 | 0 | 0 | 150000 | 150000 | 0 | 0
58 | Trash Chutes |  | 37409 | 0 | 0 | 37409 | 37409 | 0 | 0
59 | Fire Sprinklers |  | 187300 | 0 | 0 | 187300 | 187300 | 0 | 0
60 | Plumbing- Rough-Allowance |  | 800000 | 0 | 0 | 800000 | 800000 | 0 | 0
62 | Water Submeter-aIIowanee |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
63 | HVAC equipment & Ducting |  | 394800 | 0 | 0 | 394800 | 394800 | 0 | 0
64 | Electrical rough and finish-Allowance |  | 575000 | 0 | 0 | 575000 | 575000 | 0 | 0
66 | Low Voltage- Structured Cabling |  | 32000 | 0 | 0 | 32000 | 32000 | 0 | 0
67 | 2-way communication system (AOR) |  | 19000 | 0 | 0 | 19000 | 19000 | 0 | 0
68 | ERRCS / DAS system |  | 51000 | 0 | 0 | 51000 | 51000 | 0 | 0
69 | Access Control/Main Telephone Entry/Door Chimes-Allowance |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
70 | Fire Detection and Alarm |  | 47250 | 0 | 0 | 47250 | 47250 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
71 | Excavation and Fill |  | 57350 | 0 | 0 | 57350 | 57350 | 0 | 0
72 | Fine Grading-Allowance |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
73 | Site concrete, Site walkways Site Stairs |  | 10500 | 0 | 0 | 10500 | 10500 | 0 | 0
74 | Offsite Concrete-Allowance |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
75 | Striping-Allowance |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
76 | Permeable Pavers |  | 28619.55 | 0 | 0 | 28619.55 | 28619.55 | 0 | 0
77 | Irrigation system-Allowance |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
78 | Planting - Landscaping-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
79 | Fiberglass Planters-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 | CSl-33 (Utilities) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
81 | Sanitary Sewerage-Allowance |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
82 | Stormwater Utilities-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
83 | Electrical Utilities-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
84 | GC Fee |  | 806320.04 | 0 | 0 | 806320.04 | 806320.04 | 0 | 0
85 | Contractor's Contingency |  | 689162.43 | 0 | 0 | 689162.43 | 689162.43 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
| TOTAL |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0

## Draw #12
GENESIS CAPITAL DRAW FORM
| CLIENT: | FCM Investments | [5 empty] | TOTAL COMPLETED TO DATE: | 0 | #REF!
| DATE: | 2025-08-19 | [5 empty] | REMAINING $ IN BUDGET: | #REF!
| PROJECT: | 12750 Moorpark Street | [5 empty] | ORIGINAL SCHEDULE OF VALUES: | #REF!
| DRAW REQUEST: | 0 | [5 empty] | CHANGE ORDERS: | 0
[8 empty] | REVISED SCHEDULE OF VALUES: | #REF!
| DESCRIPTION OF WORK |  | SCHEDULED VALUES | PREVIOUS | + / - CHANGES | REVISED VALUES | REMAINING | DRAW | COMPLETED AND
|  |  |  | CHANGES |  |  | BUDGET | 12 | STORED TO DATE
1 | Architect |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
2 | Surveying |  | 25000 | 0 | 0 | 25000 | 25000 | 0 | 0
3 | Soil Engineer |  | 30000 | 0 | 0 | 30000 | 30000 | 0 | 0
4 | Plan Check Fees |  | 30000 | 0 | 0 | 30000 | 30000 | 0 | 0
6 | Utility Setup Fees |  | 75000 | 0 | 0 | 75000 | 75000 | 0 | 0
7 | Deputy Inspections |  | 35 | 0 | 0 | 35 | 35 | 0 | 0
8 | Admin & Legal |  | 25000 | 0 | 0 | 25000 | 25000 | 0 | 0
9 | Structural Engineer |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
10 | Civil Engineer |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
12 | Landscape Architect |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
13 | MEP Engineer |  | 20000 | 0 | 0 | 20000 | 20000 | 0 | 0
14 | Quimby Fee |  | 382500 | 0 | 0 | 382500 | 382500 | 0 | 0
15 | Tenant Buyouts |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Impact Fees |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Insurance (builders risk) |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
18 | Development Fee |  | 7000 | 0 | 0 | 7000 | 7000 | 0 | 0
19 | General Conditions - Manpower (Allowance) |  | 592020.54 | 0 | 0 | 592020.54 | 592020.54 | 0 | 0
20 | Demolition |  | 79500 | 0 | 0 | 79500 | 79500 | 0 | 0
21 | Land Surveyor-Allowance |  | 11000 | 0 | 0 | 11000 | 11000 | 0 | 0
22 | Structural Concrete |  | 327470 | 0 | 0 | 327470 | 327470 | 0 | 0
23 | Spoils removal-Allowance |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
24 | Lightweight Concrete |  | 60042 | 0 | 0 | 60042 | 60042 | 0 | 0
25 | Concrete Masonry Unit (CMU) |  | 143700 | 0 | 0 | 143700 | 143700 | 0 | 0
26 | Stone Facing - Brick Veneer |  | 13055 | 0 | 0 | 13055 | 13055 | 0 | 0
27 | Structural Steel Fabricator Contractor |  | 33988.02 | 0 | 0 | 33988.02 | 33988.02 | 0 | 0
28 | Elevator Steel - Allowance |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
29 | Decorative Metals-Allowance |  | 75000 | 0 | 0 | 75000 | 75000 | 0 | 0
30 | Glass Railing-Allowance |  | 35000 | 0 | 0 | 35000 | 35000 | 0 | 0
31 | Rough Carpentry - Material & Labor |  | 970000 | 0 | 0 | 970000 | 970000 | 0 | 0
32 | EBM System-Allowance |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
33 | Below Grade Water Proofing |  | 7600 | 0 | 0 | 7600 | 7600 | 0 | 0
34 | Above Grade Water Proofing |  | 46600 | 0 | 0 | 46600 | 46600 | 0 | 0
35 | Thermal Insulation |  | 58250 | 0 | 0 | 58250 | 58250 | 0 | 0
36 | Roofing |  | 74200 | 0 | 0 | 74200 | 74200 | 0 | 0
37 | Sheet Metal Contractor-Allowance |  | 70000 | 0 | 0 | 70000 | 70000 | 0 | 0
38 | Firestopping-Allowance |  | 3000 | 0 | 0 | 3000 | 3000 | 0 | 0
39 | Joint Sealants-Allowance |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
40 | Doors and Frames |  | 182256 | 0 | 0 | 182256 | 182256 | 0 | 0
41 | Windows - Material |  | 81726.81 | 0 | 0 | 81726.81 | 81726.81 | 0 | 0
42 | Windows - Installation |  | 25900 | 0 | 0 | 25900 | 25900 | 0 | 0
43 | Entrances, Storefronts, and Curtain Walls |  | 8755 | 0 | 0 | 8755 | 8755 | 0 | 0
44 | Drywall and metal stud framing |  | 437990 | 0 | 0 | 437990 | 437990 | 0 | 0
45 | Painting and Coating |  | 130000 | 0 | 0 | 130000 | 130000 | 0 | 0
46 | Flooring |  | 118463 | 0 | 0 | 118463 | 118463 | 0 | 0
47 | Cement Plastering - Stucco-Allowance |  | 275000 | 0 | 0 | 275000 | 275000 | 0 | 0
48 | Scaffolding-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | Signages |  | 11972.11 | 0 | 0 | 11972.11 | 11972.11 | 0 | 0
50 | Bathroom Accesories |  | 13056 | 0 | 0 | 13056 | 13056 | 0 | 0
51 | Fire extinguishers-allowance |  | 10840 | 0 | 0 | 10840 | 10840 | 0 | 0
52 | #REF! |  | 3000 | 0 | 0 | 3000 | 3000 | 0 | 0
53 | Mailboxes |  | 14136 | 0 | 0 | 14136 | 14136 | 0 | 0
54 | Appliances - Material & Installation |  | 129875.28 | 0 | 0 | 129875.28 | 129875.28 | 0 | 0
55 | Countertops-AIIowance |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
56 | Cabinetry-Allowance |  | 103000 | 0 | 0 | 103000 | 103000 | 0 | 0
57 | Elevators |  | 150000 | 0 | 0 | 150000 | 150000 | 0 | 0
58 | Trash Chutes |  | 37409 | 0 | 0 | 37409 | 37409 | 0 | 0
59 | Fire Sprinklers |  | 187300 | 0 | 0 | 187300 | 187300 | 0 | 0
60 | Plumbing- Rough-Allowance |  | 800000 | 0 | 0 | 800000 | 800000 | 0 | 0
62 | Water Submeter-aIIowanee |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
63 | HVAC equipment & Ducting |  | 394800 | 0 | 0 | 394800 | 394800 | 0 | 0
64 | Electrical rough and finish-Allowance |  | 575000 | 0 | 0 | 575000 | 575000 | 0 | 0
66 | Low Voltage- Structured Cabling |  | 32000 | 0 | 0 | 32000 | 32000 | 0 | 0
67 | 2-way communication system (AOR) |  | 19000 | 0 | 0 | 19000 | 19000 | 0 | 0
68 | ERRCS / DAS system |  | 51000 | 0 | 0 | 51000 | 51000 | 0 | 0
69 | Access Control/Main Telephone Entry/Door Chimes-Allowance |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
70 | Fire Detection and Alarm |  | 47250 | 0 | 0 | 47250 | 47250 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
71 | Excavation and Fill |  | 57350 | 0 | 0 | 57350 | 57350 | 0 | 0
72 | Fine Grading-Allowance |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
73 | Site concrete, Site walkways Site Stairs |  | 10500 | 0 | 0 | 10500 | 10500 | 0 | 0
74 | Offsite Concrete-Allowance |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
75 | Striping-Allowance |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
76 | Permeable Pavers |  | 28619.55 | 0 | 0 | 28619.55 | 28619.55 | 0 | 0
77 | Irrigation system-Allowance |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
78 | Planting - Landscaping-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
79 | Fiberglass Planters-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 | CSl-33 (Utilities) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
81 | Sanitary Sewerage-Allowance |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
82 | Stormwater Utilities-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
83 | Electrical Utilities-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
84 | GC Fee |  | 806320.04 | 0 | 0 | 806320.04 | 806320.04 | 0 | 0
85 | Contractor's Contingency |  | 689162.43 | 0 | 0 | 689162.43 | 689162.43 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
| TOTAL |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0

## Draw #13
GENESIS CAPITAL DRAW FORM
| CLIENT: | FCM Investments | [5 empty] | TOTAL COMPLETED TO DATE: | 0 | #REF!
| DATE: | 2025-08-19 | [5 empty] | REMAINING $ IN BUDGET: | #REF!
| PROJECT: | 12750 Moorpark Street | [5 empty] | ORIGINAL SCHEDULE OF VALUES: | #REF!
| DRAW REQUEST: | 0 | [5 empty] | CHANGE ORDERS: | 0
[8 empty] | REVISED SCHEDULE OF VALUES: | #REF!
| DESCRIPTION OF WORK |  | SCHEDULED VALUES | PREVIOUS | + / - CHANGES | REVISED VALUES | REMAINING | DRAW | COMPLETED AND
|  |  |  | CHANGES |  |  | BUDGET | 13 | STORED TO DATE
1 | Architect |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
2 | Surveying |  | 25000 | 0 | 0 | 25000 | 25000 | 0 | 0
3 | Soil Engineer |  | 30000 | 0 | 0 | 30000 | 30000 | 0 | 0
4 | Plan Check Fees |  | 30000 | 0 | 0 | 30000 | 30000 | 0 | 0
6 | Utility Setup Fees |  | 75000 | 0 | 0 | 75000 | 75000 | 0 | 0
7 | Deputy Inspections |  | 35 | 0 | 0 | 35 | 35 | 0 | 0
8 | Admin & Legal |  | 25000 | 0 | 0 | 25000 | 25000 | 0 | 0
9 | Structural Engineer |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
10 | Civil Engineer |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
12 | Landscape Architect |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
13 | MEP Engineer |  | 20000 | 0 | 0 | 20000 | 20000 | 0 | 0
14 | Quimby Fee |  | 382500 | 0 | 0 | 382500 | 382500 | 0 | 0
15 | Tenant Buyouts |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Impact Fees |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Insurance (builders risk) |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
18 | Development Fee |  | 7000 | 0 | 0 | 7000 | 7000 | 0 | 0
19 | General Conditions - Manpower (Allowance) |  | 592020.54 | 0 | 0 | 592020.54 | 592020.54 | 0 | 0
20 | Demolition |  | 79500 | 0 | 0 | 79500 | 79500 | 0 | 0
21 | Land Surveyor-Allowance |  | 11000 | 0 | 0 | 11000 | 11000 | 0 | 0
22 | Structural Concrete |  | 327470 | 0 | 0 | 327470 | 327470 | 0 | 0
23 | Spoils removal-Allowance |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
24 | Lightweight Concrete |  | 60042 | 0 | 0 | 60042 | 60042 | 0 | 0
25 | Concrete Masonry Unit (CMU) |  | 143700 | 0 | 0 | 143700 | 143700 | 0 | 0
26 | Stone Facing - Brick Veneer |  | 13055 | 0 | 0 | 13055 | 13055 | 0 | 0
27 | Structural Steel Fabricator Contractor |  | 33988.02 | 0 | 0 | 33988.02 | 33988.02 | 0 | 0
28 | Elevator Steel - Allowance |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
29 | Decorative Metals-Allowance |  | 75000 | 0 | 0 | 75000 | 75000 | 0 | 0
30 | Glass Railing-Allowance |  | 35000 | 0 | 0 | 35000 | 35000 | 0 | 0
31 | Rough Carpentry - Material & Labor |  | 970000 | 0 | 0 | 970000 | 970000 | 0 | 0
32 | EBM System-Allowance |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
33 | Below Grade Water Proofing |  | 7600 | 0 | 0 | 7600 | 7600 | 0 | 0
34 | Above Grade Water Proofing |  | 46600 | 0 | 0 | 46600 | 46600 | 0 | 0
35 | Thermal Insulation |  | 58250 | 0 | 0 | 58250 | 58250 | 0 | 0
36 | Roofing |  | 74200 | 0 | 0 | 74200 | 74200 | 0 | 0
37 | Sheet Metal Contractor-Allowance |  | 70000 | 0 | 0 | 70000 | 70000 | 0 | 0
38 | Firestopping-Allowance |  | 3000 | 0 | 0 | 3000 | 3000 | 0 | 0
39 | Joint Sealants-Allowance |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
40 | Doors and Frames |  | 182256 | 0 | 0 | 182256 | 182256 | 0 | 0
41 | Windows - Material |  | 81726.81 | 0 | 0 | 81726.81 | 81726.81 | 0 | 0
42 | Windows - Installation |  | 25900 | 0 | 0 | 25900 | 25900 | 0 | 0
43 | Entrances, Storefronts, and Curtain Walls |  | 8755 | 0 | 0 | 8755 | 8755 | 0 | 0
44 | Drywall and metal stud framing |  | 437990 | 0 | 0 | 437990 | 437990 | 0 | 0
45 | Painting and Coating |  | 130000 | 0 | 0 | 130000 | 130000 | 0 | 0
46 | Flooring |  | 118463 | 0 | 0 | 118463 | 118463 | 0 | 0
47 | Cement Plastering - Stucco-Allowance |  | 275000 | 0 | 0 | 275000 | 275000 | 0 | 0
48 | Scaffolding-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | Signages |  | 11972.11 | 0 | 0 | 11972.11 | 11972.11 | 0 | 0
50 | Bathroom Accesories |  | 13056 | 0 | 0 | 13056 | 13056 | 0 | 0
51 | Fire extinguishers-allowance |  | 10840 | 0 | 0 | 10840 | 10840 | 0 | 0
52 | #REF! |  | 3000 | 0 | 0 | 3000 | 3000 | 0 | 0
53 | Mailboxes |  | 14136 | 0 | 0 | 14136 | 14136 | 0 | 0
54 | Appliances - Material & Installation |  | 129875.28 | 0 | 0 | 129875.28 | 129875.28 | 0 | 0
55 | Countertops-AIIowance |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
56 | Cabinetry-Allowance |  | 103000 | 0 | 0 | 103000 | 103000 | 0 | 0
57 | Elevators |  | 150000 | 0 | 0 | 150000 | 150000 | 0 | 0
58 | Trash Chutes |  | 37409 | 0 | 0 | 37409 | 37409 | 0 | 0
59 | Fire Sprinklers |  | 187300 | 0 | 0 | 187300 | 187300 | 0 | 0
60 | Plumbing- Rough-Allowance |  | 800000 | 0 | 0 | 800000 | 800000 | 0 | 0
62 | Water Submeter-aIIowanee |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
63 | HVAC equipment & Ducting |  | 394800 | 0 | 0 | 394800 | 394800 | 0 | 0
64 | Electrical rough and finish-Allowance |  | 575000 | 0 | 0 | 575000 | 575000 | 0 | 0
66 | Low Voltage- Structured Cabling |  | 32000 | 0 | 0 | 32000 | 32000 | 0 | 0
67 | 2-way communication system (AOR) |  | 19000 | 0 | 0 | 19000 | 19000 | 0 | 0
68 | ERRCS / DAS system |  | 51000 | 0 | 0 | 51000 | 51000 | 0 | 0
69 | Access Control/Main Telephone Entry/Door Chimes-Allowance |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
70 | Fire Detection and Alarm |  | 47250 | 0 | 0 | 47250 | 47250 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
71 | Excavation and Fill |  | 57350 | 0 | 0 | 57350 | 57350 | 0 | 0
72 | Fine Grading-Allowance |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
73 | Site concrete, Site walkways Site Stairs |  | 10500 | 0 | 0 | 10500 | 10500 | 0 | 0
74 | Offsite Concrete-Allowance |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
75 | Striping-Allowance |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
76 | Permeable Pavers |  | 28619.55 | 0 | 0 | 28619.55 | 28619.55 | 0 | 0
77 | Irrigation system-Allowance |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
78 | Planting - Landscaping-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
79 | Fiberglass Planters-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 | CSl-33 (Utilities) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
81 | Sanitary Sewerage-Allowance |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
82 | Stormwater Utilities-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
83 | Electrical Utilities-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
84 | GC Fee |  | 806320.04 | 0 | 0 | 806320.04 | 806320.04 | 0 | 0
85 | Contractor's Contingency |  | 689162.43 | 0 | 0 | 689162.43 | 689162.43 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
| TOTAL |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0

## Draw #14
GENESIS CAPITAL DRAW FORM
| CLIENT: | FCM Investments | [5 empty] | TOTAL COMPLETED TO DATE: | 0 | #REF!
| DATE: | 2025-08-19 | [5 empty] | REMAINING $ IN BUDGET: | #REF!
| PROJECT: | 12750 Moorpark Street | [5 empty] | ORIGINAL SCHEDULE OF VALUES: | #REF!
| DRAW REQUEST: | 0 | [5 empty] | CHANGE ORDERS: | 0
[8 empty] | REVISED SCHEDULE OF VALUES: | #REF!
| DESCRIPTION OF WORK |  | SCHEDULED VALUES | PREVIOUS | + / - CHANGES | REVISED VALUES | REMAINING | DRAW | COMPLETED AND
|  |  |  | CHANGES |  |  | BUDGET | 14 | STORED TO DATE
1 | Architect |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
2 | Surveying |  | 25000 | 0 | 0 | 25000 | 25000 | 0 | 0
3 | Soil Engineer |  | 30000 | 0 | 0 | 30000 | 30000 | 0 | 0
4 | Plan Check Fees |  | 30000 | 0 | 0 | 30000 | 30000 | 0 | 0
6 | Utility Setup Fees |  | 75000 | 0 | 0 | 75000 | 75000 | 0 | 0
7 | Deputy Inspections |  | 35 | 0 | 0 | 35 | 35 | 0 | 0
8 | Admin & Legal |  | 25000 | 0 | 0 | 25000 | 25000 | 0 | 0
9 | Structural Engineer |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
10 | Civil Engineer |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
12 | Landscape Architect |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
13 | MEP Engineer |  | 20000 | 0 | 0 | 20000 | 20000 | 0 | 0
14 | Quimby Fee |  | 382500 | 0 | 0 | 382500 | 382500 | 0 | 0
15 | Tenant Buyouts |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Impact Fees |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Insurance (builders risk) |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
18 | Development Fee |  | 7000 | 0 | 0 | 7000 | 7000 | 0 | 0
19 | General Conditions - Manpower (Allowance) |  | 592020.54 | 0 | 0 | 592020.54 | 592020.54 | 0 | 0
20 | Demolition |  | 79500 | 0 | 0 | 79500 | 79500 | 0 | 0
21 | Land Surveyor-Allowance |  | 11000 | 0 | 0 | 11000 | 11000 | 0 | 0
22 | Structural Concrete |  | 327470 | 0 | 0 | 327470 | 327470 | 0 | 0
23 | Spoils removal-Allowance |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
24 | Lightweight Concrete |  | 60042 | 0 | 0 | 60042 | 60042 | 0 | 0
25 | Concrete Masonry Unit (CMU) |  | 143700 | 0 | 0 | 143700 | 143700 | 0 | 0
26 | Stone Facing - Brick Veneer |  | 13055 | 0 | 0 | 13055 | 13055 | 0 | 0
27 | Structural Steel Fabricator Contractor |  | 33988.02 | 0 | 0 | 33988.02 | 33988.02 | 0 | 0
28 | Elevator Steel - Allowance |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
29 | Decorative Metals-Allowance |  | 75000 | 0 | 0 | 75000 | 75000 | 0 | 0
30 | Glass Railing-Allowance |  | 35000 | 0 | 0 | 35000 | 35000 | 0 | 0
31 | Rough Carpentry - Material & Labor |  | 970000 | 0 | 0 | 970000 | 970000 | 0 | 0
32 | EBM System-Allowance |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
33 | Below Grade Water Proofing |  | 7600 | 0 | 0 | 7600 | 7600 | 0 | 0
34 | Above Grade Water Proofing |  | 46600 | 0 | 0 | 46600 | 46600 | 0 | 0
35 | Thermal Insulation |  | 58250 | 0 | 0 | 58250 | 58250 | 0 | 0
36 | Roofing |  | 74200 | 0 | 0 | 74200 | 74200 | 0 | 0
37 | Sheet Metal Contractor-Allowance |  | 70000 | 0 | 0 | 70000 | 70000 | 0 | 0
38 | Firestopping-Allowance |  | 3000 | 0 | 0 | 3000 | 3000 | 0 | 0
39 | Joint Sealants-Allowance |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
40 | Doors and Frames |  | 182256 | 0 | 0 | 182256 | 182256 | 0 | 0
41 | Windows - Material |  | 81726.81 | 0 | 0 | 81726.81 | 81726.81 | 0 | 0
42 | Windows - Installation |  | 25900 | 0 | 0 | 25900 | 25900 | 0 | 0
43 | Entrances, Storefronts, and Curtain Walls |  | 8755 | 0 | 0 | 8755 | 8755 | 0 | 0
44 | Drywall and metal stud framing |  | 437990 | 0 | 0 | 437990 | 437990 | 0 | 0
45 | Painting and Coating |  | 130000 | 0 | 0 | 130000 | 130000 | 0 | 0
46 | Flooring |  | 118463 | 0 | 0 | 118463 | 118463 | 0 | 0
47 | Cement Plastering - Stucco-Allowance |  | 275000 | 0 | 0 | 275000 | 275000 | 0 | 0
48 | Scaffolding-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | Signages |  | 11972.11 | 0 | 0 | 11972.11 | 11972.11 | 0 | 0
50 | Bathroom Accesories |  | 13056 | 0 | 0 | 13056 | 13056 | 0 | 0
51 | Fire extinguishers-allowance |  | 10840 | 0 | 0 | 10840 | 10840 | 0 | 0
52 | #REF! |  | 3000 | 0 | 0 | 3000 | 3000 | 0 | 0
53 | Mailboxes |  | 14136 | 0 | 0 | 14136 | 14136 | 0 | 0
54 | Appliances - Material & Installation |  | 129875.28 | 0 | 0 | 129875.28 | 129875.28 | 0 | 0
55 | Countertops-AIIowance |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
56 | Cabinetry-Allowance |  | 103000 | 0 | 0 | 103000 | 103000 | 0 | 0
57 | Elevators |  | 150000 | 0 | 0 | 150000 | 150000 | 0 | 0
58 | Trash Chutes |  | 37409 | 0 | 0 | 37409 | 37409 | 0 | 0
59 | Fire Sprinklers |  | 187300 | 0 | 0 | 187300 | 187300 | 0 | 0
60 | Plumbing- Rough-Allowance |  | 800000 | 0 | 0 | 800000 | 800000 | 0 | 0
62 | Water Submeter-aIIowanee |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
63 | HVAC equipment & Ducting |  | 394800 | 0 | 0 | 394800 | 394800 | 0 | 0
64 | Electrical rough and finish-Allowance |  | 575000 | 0 | 0 | 575000 | 575000 | 0 | 0
66 | Low Voltage- Structured Cabling |  | 32000 | 0 | 0 | 32000 | 32000 | 0 | 0
67 | 2-way communication system (AOR) |  | 19000 | 0 | 0 | 19000 | 19000 | 0 | 0
68 | ERRCS / DAS system |  | 51000 | 0 | 0 | 51000 | 51000 | 0 | 0
69 | Access Control/Main Telephone Entry/Door Chimes-Allowance |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
70 | Fire Detection and Alarm |  | 47250 | 0 | 0 | 47250 | 47250 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
71 | Excavation and Fill |  | 57350 | 0 | 0 | 57350 | 57350 | 0 | 0
72 | Fine Grading-Allowance |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
73 | Site concrete, Site walkways Site Stairs |  | 10500 | 0 | 0 | 10500 | 10500 | 0 | 0
74 | Offsite Concrete-Allowance |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
75 | Striping-Allowance |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
76 | Permeable Pavers |  | 28619.55 | 0 | 0 | 28619.55 | 28619.55 | 0 | 0
77 | Irrigation system-Allowance |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
78 | Planting - Landscaping-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
79 | Fiberglass Planters-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 | CSl-33 (Utilities) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
81 | Sanitary Sewerage-Allowance |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
82 | Stormwater Utilities-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
83 | Electrical Utilities-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
84 | GC Fee |  | 806320.04 | 0 | 0 | 806320.04 | 806320.04 | 0 | 0
85 | Contractor's Contingency |  | 689162.43 | 0 | 0 | 689162.43 | 689162.43 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
| TOTAL |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0

## Draw #15
GENESIS CAPITAL DRAW FORM
| CLIENT: | FCM Investments | [5 empty] | TOTAL COMPLETED TO DATE: | 0 | #REF!
| DATE: | 2025-08-19 | [5 empty] | REMAINING $ IN BUDGET: | #REF!
| PROJECT: | 12750 Moorpark Street | [5 empty] | ORIGINAL SCHEDULE OF VALUES: | #REF!
| DRAW REQUEST: | 0 | [5 empty] | CHANGE ORDERS: | 0
[8 empty] | REVISED SCHEDULE OF VALUES: | #REF!
| DESCRIPTION OF WORK |  | SCHEDULED VALUES | PREVIOUS | + / - CHANGES | REVISED VALUES | REMAINING | DRAW | COMPLETED AND
|  |  |  | CHANGES |  |  | BUDGET | 15 | STORED TO DATE
1 | Architect |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
2 | Surveying |  | 25000 | 0 | 0 | 25000 | 25000 | 0 | 0
3 | Soil Engineer |  | 30000 | 0 | 0 | 30000 | 30000 | 0 | 0
4 | Plan Check Fees |  | 30000 | 0 | 0 | 30000 | 30000 | 0 | 0
6 | Utility Setup Fees |  | 75000 | 0 | 0 | 75000 | 75000 | 0 | 0
7 | Deputy Inspections |  | 35 | 0 | 0 | 35 | 35 | 0 | 0
8 | Admin & Legal |  | 25000 | 0 | 0 | 25000 | 25000 | 0 | 0
9 | Structural Engineer |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
10 | Civil Engineer |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
12 | Landscape Architect |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
13 | MEP Engineer |  | 20000 | 0 | 0 | 20000 | 20000 | 0 | 0
14 | Quimby Fee |  | 382500 | 0 | 0 | 382500 | 382500 | 0 | 0
15 | Tenant Buyouts |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Impact Fees |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Insurance (builders risk) |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
18 | Development Fee |  | 7000 | 0 | 0 | 7000 | 7000 | 0 | 0
19 | General Conditions - Manpower (Allowance) |  | 592020.54 | 0 | 0 | 592020.54 | 592020.54 | 0 | 0
20 | Demolition |  | 79500 | 0 | 0 | 79500 | 79500 | 0 | 0
21 | Land Surveyor-Allowance |  | 11000 | 0 | 0 | 11000 | 11000 | 0 | 0
22 | Structural Concrete |  | 327470 | 0 | 0 | 327470 | 327470 | 0 | 0
23 | Spoils removal-Allowance |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
24 | Lightweight Concrete |  | 60042 | 0 | 0 | 60042 | 60042 | 0 | 0
25 | Concrete Masonry Unit (CMU) |  | 143700 | 0 | 0 | 143700 | 143700 | 0 | 0
26 | Stone Facing - Brick Veneer |  | 13055 | 0 | 0 | 13055 | 13055 | 0 | 0
27 | Structural Steel Fabricator Contractor |  | 33988.02 | 0 | 0 | 33988.02 | 33988.02 | 0 | 0
28 | Elevator Steel - Allowance |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
29 | Decorative Metals-Allowance |  | 75000 | 0 | 0 | 75000 | 75000 | 0 | 0
30 | Glass Railing-Allowance |  | 35000 | 0 | 0 | 35000 | 35000 | 0 | 0
31 | Rough Carpentry - Material & Labor |  | 970000 | 0 | 0 | 970000 | 970000 | 0 | 0
32 | EBM System-Allowance |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
33 | Below Grade Water Proofing |  | 7600 | 0 | 0 | 7600 | 7600 | 0 | 0
34 | Above Grade Water Proofing |  | 46600 | 0 | 0 | 46600 | 46600 | 0 | 0
35 | Thermal Insulation |  | 58250 | 0 | 0 | 58250 | 58250 | 0 | 0
36 | Roofing |  | 74200 | 0 | 0 | 74200 | 74200 | 0 | 0
37 | Sheet Metal Contractor-Allowance |  | 70000 | 0 | 0 | 70000 | 70000 | 0 | 0
38 | Firestopping-Allowance |  | 3000 | 0 | 0 | 3000 | 3000 | 0 | 0
39 | Joint Sealants-Allowance |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
40 | Doors and Frames |  | 182256 | 0 | 0 | 182256 | 182256 | 0 | 0
41 | Windows - Material |  | 81726.81 | 0 | 0 | 81726.81 | 81726.81 | 0 | 0
42 | Windows - Installation |  | 25900 | 0 | 0 | 25900 | 25900 | 0 | 0
43 | Entrances, Storefronts, and Curtain Walls |  | 8755 | 0 | 0 | 8755 | 8755 | 0 | 0
44 | Drywall and metal stud framing |  | 437990 | 0 | 0 | 437990 | 437990 | 0 | 0
45 | Painting and Coating |  | 130000 | 0 | 0 | 130000 | 130000 | 0 | 0
46 | Flooring |  | 118463 | 0 | 0 | 118463 | 118463 | 0 | 0
47 | Cement Plastering - Stucco-Allowance |  | 275000 | 0 | 0 | 275000 | 275000 | 0 | 0
48 | Scaffolding-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | Signages |  | 11972.11 | 0 | 0 | 11972.11 | 11972.11 | 0 | 0
50 | Bathroom Accesories |  | 13056 | 0 | 0 | 13056 | 13056 | 0 | 0
51 | Fire extinguishers-allowance |  | 10840 | 0 | 0 | 10840 | 10840 | 0 | 0
52 | #REF! |  | 3000 | 0 | 0 | 3000 | 3000 | 0 | 0
53 | Mailboxes |  | 14136 | 0 | 0 | 14136 | 14136 | 0 | 0
54 | Appliances - Material & Installation |  | 129875.28 | 0 | 0 | 129875.28 | 129875.28 | 0 | 0
55 | Countertops-AIIowance |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
56 | Cabinetry-Allowance |  | 103000 | 0 | 0 | 103000 | 103000 | 0 | 0
57 | Elevators |  | 150000 | 0 | 0 | 150000 | 150000 | 0 | 0
58 | Trash Chutes |  | 37409 | 0 | 0 | 37409 | 37409 | 0 | 0
59 | Fire Sprinklers |  | 187300 | 0 | 0 | 187300 | 187300 | 0 | 0
60 | Plumbing- Rough-Allowance |  | 800000 | 0 | 0 | 800000 | 800000 | 0 | 0
62 | Water Submeter-aIIowanee |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
63 | HVAC equipment & Ducting |  | 394800 | 0 | 0 | 394800 | 394800 | 0 | 0
64 | Electrical rough and finish-Allowance |  | 575000 | 0 | 0 | 575000 | 575000 | 0 | 0
66 | Low Voltage- Structured Cabling |  | 32000 | 0 | 0 | 32000 | 32000 | 0 | 0
67 | 2-way communication system (AOR) |  | 19000 | 0 | 0 | 19000 | 19000 | 0 | 0
68 | ERRCS / DAS system |  | 51000 | 0 | 0 | 51000 | 51000 | 0 | 0
69 | Access Control/Main Telephone Entry/Door Chimes-Allowance |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
70 | Fire Detection and Alarm |  | 47250 | 0 | 0 | 47250 | 47250 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
71 | Excavation and Fill |  | 57350 | 0 | 0 | 57350 | 57350 | 0 | 0
72 | Fine Grading-Allowance |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
73 | Site concrete, Site walkways Site Stairs |  | 10500 | 0 | 0 | 10500 | 10500 | 0 | 0
74 | Offsite Concrete-Allowance |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
75 | Striping-Allowance |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
76 | Permeable Pavers |  | 28619.55 | 0 | 0 | 28619.55 | 28619.55 | 0 | 0
77 | Irrigation system-Allowance |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
78 | Planting - Landscaping-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
79 | Fiberglass Planters-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 | CSl-33 (Utilities) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
81 | Sanitary Sewerage-Allowance |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
82 | Stormwater Utilities-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
83 | Electrical Utilities-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
84 | GC Fee |  | 806320.04 | 0 | 0 | 806320.04 | 806320.04 | 0 | 0
85 | Contractor's Contingency |  | 689162.43 | 0 | 0 | 689162.43 | 689162.43 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
| TOTAL |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0

## Draw #16
GENESIS CAPITAL DRAW FORM
| CLIENT: | FCM Investments | [5 empty] | TOTAL COMPLETED TO DATE: | 0 | #REF!
| DATE: | 2025-08-19 | [5 empty] | REMAINING $ IN BUDGET: | #REF!
| PROJECT: | 12750 Moorpark Street | [5 empty] | ORIGINAL SCHEDULE OF VALUES: | #REF!
| DRAW REQUEST: | 0 | [5 empty] | CHANGE ORDERS: | 0
[8 empty] | REVISED SCHEDULE OF VALUES: | #REF!
| DESCRIPTION OF WORK |  | SCHEDULED VALUES | PREVIOUS | + / - CHANGES | REVISED VALUES | REMAINING | DRAW | COMPLETED AND
|  |  |  | CHANGES |  |  | BUDGET | 16 | STORED TO DATE
1 | Architect |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
2 | Surveying |  | 25000 | 0 | 0 | 25000 | 25000 | 0 | 0
3 | Soil Engineer |  | 30000 | 0 | 0 | 30000 | 30000 | 0 | 0
4 | Plan Check Fees |  | 30000 | 0 | 0 | 30000 | 30000 | 0 | 0
6 | Utility Setup Fees |  | 75000 | 0 | 0 | 75000 | 75000 | 0 | 0
7 | Deputy Inspections |  | 35 | 0 | 0 | 35 | 35 | 0 | 0
8 | Admin & Legal |  | 25000 | 0 | 0 | 25000 | 25000 | 0 | 0
9 | Structural Engineer |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
10 | Civil Engineer |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
12 | Landscape Architect |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
13 | MEP Engineer |  | 20000 | 0 | 0 | 20000 | 20000 | 0 | 0
14 | Quimby Fee |  | 382500 | 0 | 0 | 382500 | 382500 | 0 | 0
15 | Tenant Buyouts |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Impact Fees |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Insurance (builders risk) |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
18 | Development Fee |  | 7000 | 0 | 0 | 7000 | 7000 | 0 | 0
19 | General Conditions - Manpower (Allowance) |  | 592020.54 | 0 | 0 | 592020.54 | 592020.54 | 0 | 0
20 | Demolition |  | 79500 | 0 | 0 | 79500 | 79500 | 0 | 0
21 | Land Surveyor-Allowance |  | 11000 | 0 | 0 | 11000 | 11000 | 0 | 0
22 | Structural Concrete |  | 327470 | 0 | 0 | 327470 | 327470 | 0 | 0
23 | Spoils removal-Allowance |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
24 | Lightweight Concrete |  | 60042 | 0 | 0 | 60042 | 60042 | 0 | 0
25 | Concrete Masonry Unit (CMU) |  | 143700 | 0 | 0 | 143700 | 143700 | 0 | 0
26 | Stone Facing - Brick Veneer |  | 13055 | 0 | 0 | 13055 | 13055 | 0 | 0
27 | Structural Steel Fabricator Contractor |  | 33988.02 | 0 | 0 | 33988.02 | 33988.02 | 0 | 0
28 | Elevator Steel - Allowance |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
29 | Decorative Metals-Allowance |  | 75000 | 0 | 0 | 75000 | 75000 | 0 | 0
30 | Glass Railing-Allowance |  | 35000 | 0 | 0 | 35000 | 35000 | 0 | 0
31 | Rough Carpentry - Material & Labor |  | 970000 | 0 | 0 | 970000 | 970000 | 0 | 0
32 | EBM System-Allowance |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
33 | Below Grade Water Proofing |  | 7600 | 0 | 0 | 7600 | 7600 | 0 | 0
34 | Above Grade Water Proofing |  | 46600 | 0 | 0 | 46600 | 46600 | 0 | 0
35 | Thermal Insulation |  | 58250 | 0 | 0 | 58250 | 58250 | 0 | 0
36 | Roofing |  | 74200 | 0 | 0 | 74200 | 74200 | 0 | 0
37 | Sheet Metal Contractor-Allowance |  | 70000 | 0 | 0 | 70000 | 70000 | 0 | 0
38 | Firestopping-Allowance |  | 3000 | 0 | 0 | 3000 | 3000 | 0 | 0
39 | Joint Sealants-Allowance |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
40 | Doors and Frames |  | 182256 | 0 | 0 | 182256 | 182256 | 0 | 0
41 | Windows - Material |  | 81726.81 | 0 | 0 | 81726.81 | 81726.81 | 0 | 0
42 | Windows - Installation |  | 25900 | 0 | 0 | 25900 | 25900 | 0 | 0
43 | Entrances, Storefronts, and Curtain Walls |  | 8755 | 0 | 0 | 8755 | 8755 | 0 | 0
44 | Drywall and metal stud framing |  | 437990 | 0 | 0 | 437990 | 437990 | 0 | 0
45 | Painting and Coating |  | 130000 | 0 | 0 | 130000 | 130000 | 0 | 0
46 | Flooring |  | 118463 | 0 | 0 | 118463 | 118463 | 0 | 0
47 | Cement Plastering - Stucco-Allowance |  | 275000 | 0 | 0 | 275000 | 275000 | 0 | 0
48 | Scaffolding-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | Signages |  | 11972.11 | 0 | 0 | 11972.11 | 11972.11 | 0 | 0
50 | Bathroom Accesories |  | 13056 | 0 | 0 | 13056 | 13056 | 0 | 0
51 | Fire extinguishers-allowance |  | 10840 | 0 | 0 | 10840 | 10840 | 0 | 0
52 | #REF! |  | 3000 | 0 | 0 | 3000 | 3000 | 0 | 0
53 | Mailboxes |  | 14136 | 0 | 0 | 14136 | 14136 | 0 | 0
54 | Appliances - Material & Installation |  | 129875.28 | 0 | 0 | 129875.28 | 129875.28 | 0 | 0
55 | Countertops-AIIowance |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
56 | Cabinetry-Allowance |  | 103000 | 0 | 0 | 103000 | 103000 | 0 | 0
57 | Elevators |  | 150000 | 0 | 0 | 150000 | 150000 | 0 | 0
58 | Trash Chutes |  | 37409 | 0 | 0 | 37409 | 37409 | 0 | 0
59 | Fire Sprinklers |  | 187300 | 0 | 0 | 187300 | 187300 | 0 | 0
60 | Plumbing- Rough-Allowance |  | 800000 | 0 | 0 | 800000 | 800000 | 0 | 0
62 | Water Submeter-aIIowanee |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
63 | HVAC equipment & Ducting |  | 394800 | 0 | 0 | 394800 | 394800 | 0 | 0
64 | Electrical rough and finish-Allowance |  | 575000 | 0 | 0 | 575000 | 575000 | 0 | 0
66 | Low Voltage- Structured Cabling |  | 32000 | 0 | 0 | 32000 | 32000 | 0 | 0
67 | 2-way communication system (AOR) |  | 19000 | 0 | 0 | 19000 | 19000 | 0 | 0
68 | ERRCS / DAS system |  | 51000 | 0 | 0 | 51000 | 51000 | 0 | 0
69 | Access Control/Main Telephone Entry/Door Chimes-Allowance |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
70 | Fire Detection and Alarm |  | 47250 | 0 | 0 | 47250 | 47250 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
71 | Excavation and Fill |  | 57350 | 0 | 0 | 57350 | 57350 | 0 | 0
72 | Fine Grading-Allowance |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
73 | Site concrete, Site walkways Site Stairs |  | 10500 | 0 | 0 | 10500 | 10500 | 0 | 0
74 | Offsite Concrete-Allowance |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
75 | Striping-Allowance |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
76 | Permeable Pavers |  | 28619.55 | 0 | 0 | 28619.55 | 28619.55 | 0 | 0
77 | Irrigation system-Allowance |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
78 | Planting - Landscaping-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
79 | Fiberglass Planters-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 | CSl-33 (Utilities) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
81 | Sanitary Sewerage-Allowance |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
82 | Stormwater Utilities-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
83 | Electrical Utilities-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
84 | GC Fee |  | 806320.04 | 0 | 0 | 806320.04 | 806320.04 | 0 | 0
85 | Contractor's Contingency |  | 689162.43 | 0 | 0 | 689162.43 | 689162.43 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
| TOTAL |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0

## Draw #17
GENESIS CAPITAL DRAW FORM
| CLIENT: | FCM Investments | [5 empty] | TOTAL COMPLETED TO DATE: | 0 | #REF!
| DATE: | 2025-08-19 | [5 empty] | REMAINING $ IN BUDGET: | #REF!
| PROJECT: | 12750 Moorpark Street | [5 empty] | ORIGINAL SCHEDULE OF VALUES: | #REF!
| DRAW REQUEST: | 0 | [5 empty] | CHANGE ORDERS: | 0
[8 empty] | REVISED SCHEDULE OF VALUES: | #REF!
| DESCRIPTION OF WORK |  | SCHEDULED VALUES | PREVIOUS | + / - CHANGES | REVISED VALUES | REMAINING | DRAW | COMPLETED AND
|  |  |  | CHANGES |  |  | BUDGET | 17 | STORED TO DATE
1 | Architect |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
2 | Surveying |  | 25000 | 0 | 0 | 25000 | 25000 | 0 | 0
3 | Soil Engineer |  | 30000 | 0 | 0 | 30000 | 30000 | 0 | 0
4 | Plan Check Fees |  | 30000 | 0 | 0 | 30000 | 30000 | 0 | 0
6 | Utility Setup Fees |  | 75000 | 0 | 0 | 75000 | 75000 | 0 | 0
7 | Deputy Inspections |  | 35 | 0 | 0 | 35 | 35 | 0 | 0
8 | Admin & Legal |  | 25000 | 0 | 0 | 25000 | 25000 | 0 | 0
9 | Structural Engineer |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
10 | Civil Engineer |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
12 | Landscape Architect |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
13 | MEP Engineer |  | 20000 | 0 | 0 | 20000 | 20000 | 0 | 0
14 | Quimby Fee |  | 382500 | 0 | 0 | 382500 | 382500 | 0 | 0
15 | Tenant Buyouts |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Impact Fees |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Insurance (builders risk) |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
18 | Development Fee |  | 7000 | 0 | 0 | 7000 | 7000 | 0 | 0
19 | General Conditions - Manpower (Allowance) |  | 592020.54 | 0 | 0 | 592020.54 | 592020.54 | 0 | 0
20 | Demolition |  | 79500 | 0 | 0 | 79500 | 79500 | 0 | 0
21 | Land Surveyor-Allowance |  | 11000 | 0 | 0 | 11000 | 11000 | 0 | 0
22 | Structural Concrete |  | 327470 | 0 | 0 | 327470 | 327470 | 0 | 0
23 | Spoils removal-Allowance |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
24 | Lightweight Concrete |  | 60042 | 0 | 0 | 60042 | 60042 | 0 | 0
25 | Concrete Masonry Unit (CMU) |  | 143700 | 0 | 0 | 143700 | 143700 | 0 | 0
26 | Stone Facing - Brick Veneer |  | 13055 | 0 | 0 | 13055 | 13055 | 0 | 0
27 | Structural Steel Fabricator Contractor |  | 33988.02 | 0 | 0 | 33988.02 | 33988.02 | 0 | 0
28 | Elevator Steel - Allowance |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
29 | Decorative Metals-Allowance |  | 75000 | 0 | 0 | 75000 | 75000 | 0 | 0
30 | Glass Railing-Allowance |  | 35000 | 0 | 0 | 35000 | 35000 | 0 | 0
31 | Rough Carpentry - Material & Labor |  | 970000 | 0 | 0 | 970000 | 970000 | 0 | 0
32 | EBM System-Allowance |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
33 | Below Grade Water Proofing |  | 7600 | 0 | 0 | 7600 | 7600 | 0 | 0
34 | Above Grade Water Proofing |  | 46600 | 0 | 0 | 46600 | 46600 | 0 | 0
35 | Thermal Insulation |  | 58250 | 0 | 0 | 58250 | 58250 | 0 | 0
36 | Roofing |  | 74200 | 0 | 0 | 74200 | 74200 | 0 | 0
37 | Sheet Metal Contractor-Allowance |  | 70000 | 0 | 0 | 70000 | 70000 | 0 | 0
38 | Firestopping-Allowance |  | 3000 | 0 | 0 | 3000 | 3000 | 0 | 0
39 | Joint Sealants-Allowance |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
40 | Doors and Frames |  | 182256 | 0 | 0 | 182256 | 182256 | 0 | 0
41 | Windows - Material |  | 81726.81 | 0 | 0 | 81726.81 | 81726.81 | 0 | 0
42 | Windows - Installation |  | 25900 | 0 | 0 | 25900 | 25900 | 0 | 0
43 | Entrances, Storefronts, and Curtain Walls |  | 8755 | 0 | 0 | 8755 | 8755 | 0 | 0
44 | Drywall and metal stud framing |  | 437990 | 0 | 0 | 437990 | 437990 | 0 | 0
45 | Painting and Coating |  | 130000 | 0 | 0 | 130000 | 130000 | 0 | 0
46 | Flooring |  | 118463 | 0 | 0 | 118463 | 118463 | 0 | 0
47 | Cement Plastering - Stucco-Allowance |  | 275000 | 0 | 0 | 275000 | 275000 | 0 | 0
48 | Scaffolding-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | Signages |  | 11972.11 | 0 | 0 | 11972.11 | 11972.11 | 0 | 0
50 | Bathroom Accesories |  | 13056 | 0 | 0 | 13056 | 13056 | 0 | 0
51 | Fire extinguishers-allowance |  | 10840 | 0 | 0 | 10840 | 10840 | 0 | 0
52 | #REF! |  | 3000 | 0 | 0 | 3000 | 3000 | 0 | 0
53 | Mailboxes |  | 14136 | 0 | 0 | 14136 | 14136 | 0 | 0
54 | Appliances - Material & Installation |  | 129875.28 | 0 | 0 | 129875.28 | 129875.28 | 0 | 0
55 | Countertops-AIIowance |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
56 | Cabinetry-Allowance |  | 103000 | 0 | 0 | 103000 | 103000 | 0 | 0
57 | Elevators |  | 150000 | 0 | 0 | 150000 | 150000 | 0 | 0
58 | Trash Chutes |  | 37409 | 0 | 0 | 37409 | 37409 | 0 | 0
59 | Fire Sprinklers |  | 187300 | 0 | 0 | 187300 | 187300 | 0 | 0
60 | Plumbing- Rough-Allowance |  | 800000 | 0 | 0 | 800000 | 800000 | 0 | 0
62 | Water Submeter-aIIowanee |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
63 | HVAC equipment & Ducting |  | 394800 | 0 | 0 | 394800 | 394800 | 0 | 0
64 | Electrical rough and finish-Allowance |  | 575000 | 0 | 0 | 575000 | 575000 | 0 | 0
66 | Low Voltage- Structured Cabling |  | 32000 | 0 | 0 | 32000 | 32000 | 0 | 0
67 | 2-way communication system (AOR) |  | 19000 | 0 | 0 | 19000 | 19000 | 0 | 0
68 | ERRCS / DAS system |  | 51000 | 0 | 0 | 51000 | 51000 | 0 | 0
69 | Access Control/Main Telephone Entry/Door Chimes-Allowance |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
70 | Fire Detection and Alarm |  | 47250 | 0 | 0 | 47250 | 47250 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
71 | Excavation and Fill |  | 57350 | 0 | 0 | 57350 | 57350 | 0 | 0
72 | Fine Grading-Allowance |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
73 | Site concrete, Site walkways Site Stairs |  | 10500 | 0 | 0 | 10500 | 10500 | 0 | 0
74 | Offsite Concrete-Allowance |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
75 | Striping-Allowance |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
76 | Permeable Pavers |  | 28619.55 | 0 | 0 | 28619.55 | 28619.55 | 0 | 0
77 | Irrigation system-Allowance |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
78 | Planting - Landscaping-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
79 | Fiberglass Planters-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 | CSl-33 (Utilities) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
81 | Sanitary Sewerage-Allowance |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
82 | Stormwater Utilities-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
83 | Electrical Utilities-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
84 | GC Fee |  | 806320.04 | 0 | 0 | 806320.04 | 806320.04 | 0 | 0
85 | Contractor's Contingency |  | 689162.43 | 0 | 0 | 689162.43 | 689162.43 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
| TOTAL |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0

## Draw #18
GENESIS CAPITAL DRAW FORM
| CLIENT: | FCM Investments | [5 empty] | TOTAL COMPLETED TO DATE: | 0 | #REF!
| DATE: | 2025-08-19 | [5 empty] | REMAINING $ IN BUDGET: | #REF!
| PROJECT: | 12750 Moorpark Street | [5 empty] | ORIGINAL SCHEDULE OF VALUES: | #REF!
| DRAW REQUEST: | 0 | [5 empty] | CHANGE ORDERS: | 0
[8 empty] | REVISED SCHEDULE OF VALUES: | #REF!
| DESCRIPTION OF WORK |  | SCHEDULED VALUES | PREVIOUS | + / - CHANGES | REVISED VALUES | REMAINING | DRAW | COMPLETED AND
|  |  |  | CHANGES |  |  | BUDGET | 18 | STORED TO DATE
1 | Architect |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
2 | Surveying |  | 25000 | 0 | 0 | 25000 | 25000 | 0 | 0
3 | Soil Engineer |  | 30000 | 0 | 0 | 30000 | 30000 | 0 | 0
4 | Plan Check Fees |  | 30000 | 0 | 0 | 30000 | 30000 | 0 | 0
6 | Utility Setup Fees |  | 75000 | 0 | 0 | 75000 | 75000 | 0 | 0
7 | Deputy Inspections |  | 35 | 0 | 0 | 35 | 35 | 0 | 0
8 | Admin & Legal |  | 25000 | 0 | 0 | 25000 | 25000 | 0 | 0
9 | Structural Engineer |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
10 | Civil Engineer |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
12 | Landscape Architect |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
13 | MEP Engineer |  | 20000 | 0 | 0 | 20000 | 20000 | 0 | 0
14 | Quimby Fee |  | 382500 | 0 | 0 | 382500 | 382500 | 0 | 0
15 | Tenant Buyouts |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Impact Fees |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Insurance (builders risk) |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
18 | Development Fee |  | 7000 | 0 | 0 | 7000 | 7000 | 0 | 0
19 | General Conditions - Manpower (Allowance) |  | 592020.54 | 0 | 0 | 592020.54 | 592020.54 | 0 | 0
20 | Demolition |  | 79500 | 0 | 0 | 79500 | 79500 | 0 | 0
21 | Land Surveyor-Allowance |  | 11000 | 0 | 0 | 11000 | 11000 | 0 | 0
22 | Structural Concrete |  | 327470 | 0 | 0 | 327470 | 327470 | 0 | 0
23 | Spoils removal-Allowance |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
24 | Lightweight Concrete |  | 60042 | 0 | 0 | 60042 | 60042 | 0 | 0
25 | Concrete Masonry Unit (CMU) |  | 143700 | 0 | 0 | 143700 | 143700 | 0 | 0
26 | Stone Facing - Brick Veneer |  | 13055 | 0 | 0 | 13055 | 13055 | 0 | 0
27 | Structural Steel Fabricator Contractor |  | 33988.02 | 0 | 0 | 33988.02 | 33988.02 | 0 | 0
28 | Elevator Steel - Allowance |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
29 | Decorative Metals-Allowance |  | 75000 | 0 | 0 | 75000 | 75000 | 0 | 0
30 | Glass Railing-Allowance |  | 35000 | 0 | 0 | 35000 | 35000 | 0 | 0
31 | Rough Carpentry - Material & Labor |  | 970000 | 0 | 0 | 970000 | 970000 | 0 | 0
32 | EBM System-Allowance |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
33 | Below Grade Water Proofing |  | 7600 | 0 | 0 | 7600 | 7600 | 0 | 0
34 | Above Grade Water Proofing |  | 46600 | 0 | 0 | 46600 | 46600 | 0 | 0
35 | Thermal Insulation |  | 58250 | 0 | 0 | 58250 | 58250 | 0 | 0
36 | Roofing |  | 74200 | 0 | 0 | 74200 | 74200 | 0 | 0
37 | Sheet Metal Contractor-Allowance |  | 70000 | 0 | 0 | 70000 | 70000 | 0 | 0
38 | Firestopping-Allowance |  | 3000 | 0 | 0 | 3000 | 3000 | 0 | 0
39 | Joint Sealants-Allowance |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
40 | Doors and Frames |  | 182256 | 0 | 0 | 182256 | 182256 | 0 | 0
41 | Windows - Material |  | 81726.81 | 0 | 0 | 81726.81 | 81726.81 | 0 | 0
42 | Windows - Installation |  | 25900 | 0 | 0 | 25900 | 25900 | 0 | 0
43 | Entrances, Storefronts, and Curtain Walls |  | 8755 | 0 | 0 | 8755 | 8755 | 0 | 0
44 | Drywall and metal stud framing |  | 437990 | 0 | 0 | 437990 | 437990 | 0 | 0
45 | Painting and Coating |  | 130000 | 0 | 0 | 130000 | 130000 | 0 | 0
46 | Flooring |  | 118463 | 0 | 0 | 118463 | 118463 | 0 | 0
47 | Cement Plastering - Stucco-Allowance |  | 275000 | 0 | 0 | 275000 | 275000 | 0 | 0
48 | Scaffolding-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | Signages |  | 11972.11 | 0 | 0 | 11972.11 | 11972.11 | 0 | 0
50 | Bathroom Accesories |  | 13056 | 0 | 0 | 13056 | 13056 | 0 | 0
51 | Fire extinguishers-allowance |  | 10840 | 0 | 0 | 10840 | 10840 | 0 | 0
52 | #REF! |  | 3000 | 0 | 0 | 3000 | 3000 | 0 | 0
53 | Mailboxes |  | 14136 | 0 | 0 | 14136 | 14136 | 0 | 0
54 | Appliances - Material & Installation |  | 129875.28 | 0 | 0 | 129875.28 | 129875.28 | 0 | 0
55 | Countertops-AIIowance |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
56 | Cabinetry-Allowance |  | 103000 | 0 | 0 | 103000 | 103000 | 0 | 0
57 | Elevators |  | 150000 | 0 | 0 | 150000 | 150000 | 0 | 0
58 | Trash Chutes |  | 37409 | 0 | 0 | 37409 | 37409 | 0 | 0
59 | Fire Sprinklers |  | 187300 | 0 | 0 | 187300 | 187300 | 0 | 0
60 | Plumbing- Rough-Allowance |  | 800000 | 0 | 0 | 800000 | 800000 | 0 | 0
62 | Water Submeter-aIIowanee |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
63 | HVAC equipment & Ducting |  | 394800 | 0 | 0 | 394800 | 394800 | 0 | 0
64 | Electrical rough and finish-Allowance |  | 575000 | 0 | 0 | 575000 | 575000 | 0 | 0
66 | Low Voltage- Structured Cabling |  | 32000 | 0 | 0 | 32000 | 32000 | 0 | 0
67 | 2-way communication system (AOR) |  | 19000 | 0 | 0 | 19000 | 19000 | 0 | 0
68 | ERRCS / DAS system |  | 51000 | 0 | 0 | 51000 | 51000 | 0 | 0
69 | Access Control/Main Telephone Entry/Door Chimes-Allowance |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
70 | Fire Detection and Alarm |  | 47250 | 0 | 0 | 47250 | 47250 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
71 | Excavation and Fill |  | 57350 | 0 | 0 | 57350 | 57350 | 0 | 0
72 | Fine Grading-Allowance |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
73 | Site concrete, Site walkways Site Stairs |  | 10500 | 0 | 0 | 10500 | 10500 | 0 | 0
74 | Offsite Concrete-Allowance |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
75 | Striping-Allowance |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
76 | Permeable Pavers |  | 28619.55 | 0 | 0 | 28619.55 | 28619.55 | 0 | 0
77 | Irrigation system-Allowance |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
78 | Planting - Landscaping-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
79 | Fiberglass Planters-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 | CSl-33 (Utilities) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
81 | Sanitary Sewerage-Allowance |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
82 | Stormwater Utilities-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
83 | Electrical Utilities-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
84 | GC Fee |  | 806320.04 | 0 | 0 | 806320.04 | 806320.04 | 0 | 0
85 | Contractor's Contingency |  | 689162.43 | 0 | 0 | 689162.43 | 689162.43 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
| TOTAL |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0

## Draw #19
GENESIS CAPITAL DRAW FORM
| CLIENT: | FCM Investments | [5 empty] | TOTAL COMPLETED TO DATE: | 0 | #REF!
| DATE: | 2025-08-19 | [5 empty] | REMAINING $ IN BUDGET: | #REF!
| PROJECT: | 12750 Moorpark Street | [5 empty] | ORIGINAL SCHEDULE OF VALUES: | #REF!
| DRAW REQUEST: | 0 | [5 empty] | CHANGE ORDERS: | 0
[8 empty] | REVISED SCHEDULE OF VALUES: | #REF!
| DESCRIPTION OF WORK |  | SCHEDULED VALUES | PREVIOUS | + / - CHANGES | REVISED VALUES | REMAINING | DRAW | COMPLETED AND
|  |  |  | CHANGES |  |  | BUDGET | 19 | STORED TO DATE
1 | Architect |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
2 | Surveying |  | 25000 | 0 | 0 | 25000 | 25000 | 0 | 0
3 | Soil Engineer |  | 30000 | 0 | 0 | 30000 | 30000 | 0 | 0
4 | Plan Check Fees |  | 30000 | 0 | 0 | 30000 | 30000 | 0 | 0
6 | Utility Setup Fees |  | 75000 | 0 | 0 | 75000 | 75000 | 0 | 0
7 | Deputy Inspections |  | 35 | 0 | 0 | 35 | 35 | 0 | 0
8 | Admin & Legal |  | 25000 | 0 | 0 | 25000 | 25000 | 0 | 0
9 | Structural Engineer |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
10 | Civil Engineer |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
12 | Landscape Architect |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
13 | MEP Engineer |  | 20000 | 0 | 0 | 20000 | 20000 | 0 | 0
14 | Quimby Fee |  | 382500 | 0 | 0 | 382500 | 382500 | 0 | 0
15 | Tenant Buyouts |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Impact Fees |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Insurance (builders risk) |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
18 | Development Fee |  | 7000 | 0 | 0 | 7000 | 7000 | 0 | 0
19 | General Conditions - Manpower (Allowance) |  | 592020.54 | 0 | 0 | 592020.54 | 592020.54 | 0 | 0
20 | Demolition |  | 79500 | 0 | 0 | 79500 | 79500 | 0 | 0
21 | Land Surveyor-Allowance |  | 11000 | 0 | 0 | 11000 | 11000 | 0 | 0
22 | Structural Concrete |  | 327470 | 0 | 0 | 327470 | 327470 | 0 | 0
23 | Spoils removal-Allowance |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
24 | Lightweight Concrete |  | 60042 | 0 | 0 | 60042 | 60042 | 0 | 0
25 | Concrete Masonry Unit (CMU) |  | 143700 | 0 | 0 | 143700 | 143700 | 0 | 0
26 | Stone Facing - Brick Veneer |  | 13055 | 0 | 0 | 13055 | 13055 | 0 | 0
27 | Structural Steel Fabricator Contractor |  | 33988.02 | 0 | 0 | 33988.02 | 33988.02 | 0 | 0
28 | Elevator Steel - Allowance |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
29 | Decorative Metals-Allowance |  | 75000 | 0 | 0 | 75000 | 75000 | 0 | 0
30 | Glass Railing-Allowance |  | 35000 | 0 | 0 | 35000 | 35000 | 0 | 0
31 | Rough Carpentry - Material & Labor |  | 970000 | 0 | 0 | 970000 | 970000 | 0 | 0
32 | EBM System-Allowance |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
33 | Below Grade Water Proofing |  | 7600 | 0 | 0 | 7600 | 7600 | 0 | 0
34 | Above Grade Water Proofing |  | 46600 | 0 | 0 | 46600 | 46600 | 0 | 0
35 | Thermal Insulation |  | 58250 | 0 | 0 | 58250 | 58250 | 0 | 0
36 | Roofing |  | 74200 | 0 | 0 | 74200 | 74200 | 0 | 0
37 | Sheet Metal Contractor-Allowance |  | 70000 | 0 | 0 | 70000 | 70000 | 0 | 0
38 | Firestopping-Allowance |  | 3000 | 0 | 0 | 3000 | 3000 | 0 | 0
39 | Joint Sealants-Allowance |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
40 | Doors and Frames |  | 182256 | 0 | 0 | 182256 | 182256 | 0 | 0
41 | Windows - Material |  | 81726.81 | 0 | 0 | 81726.81 | 81726.81 | 0 | 0
42 | Windows - Installation |  | 25900 | 0 | 0 | 25900 | 25900 | 0 | 0
43 | Entrances, Storefronts, and Curtain Walls |  | 8755 | 0 | 0 | 8755 | 8755 | 0 | 0
44 | Drywall and metal stud framing |  | 437990 | 0 | 0 | 437990 | 437990 | 0 | 0
45 | Painting and Coating |  | 130000 | 0 | 0 | 130000 | 130000 | 0 | 0
46 | Flooring |  | 118463 | 0 | 0 | 118463 | 118463 | 0 | 0
47 | Cement Plastering - Stucco-Allowance |  | 275000 | 0 | 0 | 275000 | 275000 | 0 | 0
48 | Scaffolding-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | Signages |  | 11972.11 | 0 | 0 | 11972.11 | 11972.11 | 0 | 0
50 | Bathroom Accesories |  | 13056 | 0 | 0 | 13056 | 13056 | 0 | 0
51 | Fire extinguishers-allowance |  | 10840 | 0 | 0 | 10840 | 10840 | 0 | 0
52 | #REF! |  | 3000 | 0 | 0 | 3000 | 3000 | 0 | 0
53 | Mailboxes |  | 14136 | 0 | 0 | 14136 | 14136 | 0 | 0
54 | Appliances - Material & Installation |  | 129875.28 | 0 | 0 | 129875.28 | 129875.28 | 0 | 0
55 | Countertops-AIIowance |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
56 | Cabinetry-Allowance |  | 103000 | 0 | 0 | 103000 | 103000 | 0 | 0
57 | Elevators |  | 150000 | 0 | 0 | 150000 | 150000 | 0 | 0
58 | Trash Chutes |  | 37409 | 0 | 0 | 37409 | 37409 | 0 | 0
59 | Fire Sprinklers |  | 187300 | 0 | 0 | 187300 | 187300 | 0 | 0
60 | Plumbing- Rough-Allowance |  | 800000 | 0 | 0 | 800000 | 800000 | 0 | 0
62 | Water Submeter-aIIowanee |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
63 | HVAC equipment & Ducting |  | 394800 | 0 | 0 | 394800 | 394800 | 0 | 0
64 | Electrical rough and finish-Allowance |  | 575000 | 0 | 0 | 575000 | 575000 | 0 | 0
66 | Low Voltage- Structured Cabling |  | 32000 | 0 | 0 | 32000 | 32000 | 0 | 0
67 | 2-way communication system (AOR) |  | 19000 | 0 | 0 | 19000 | 19000 | 0 | 0
68 | ERRCS / DAS system |  | 51000 | 0 | 0 | 51000 | 51000 | 0 | 0
69 | Access Control/Main Telephone Entry/Door Chimes-Allowance |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
70 | Fire Detection and Alarm |  | 47250 | 0 | 0 | 47250 | 47250 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
71 | Excavation and Fill |  | 57350 | 0 | 0 | 57350 | 57350 | 0 | 0
72 | Fine Grading-Allowance |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
73 | Site concrete, Site walkways Site Stairs |  | 10500 | 0 | 0 | 10500 | 10500 | 0 | 0
74 | Offsite Concrete-Allowance |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
75 | Striping-Allowance |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
76 | Permeable Pavers |  | 28619.55 | 0 | 0 | 28619.55 | 28619.55 | 0 | 0
77 | Irrigation system-Allowance |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
78 | Planting - Landscaping-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
79 | Fiberglass Planters-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 | CSl-33 (Utilities) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
81 | Sanitary Sewerage-Allowance |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
82 | Stormwater Utilities-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
83 | Electrical Utilities-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
84 | GC Fee |  | 806320.04 | 0 | 0 | 806320.04 | 806320.04 | 0 | 0
85 | Contractor's Contingency |  | 689162.43 | 0 | 0 | 689162.43 | 689162.43 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
| TOTAL |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0

## Draw #20
GENESIS CAPITAL DRAW FORM
| CLIENT: | FCM Investments | [5 empty] | TOTAL COMPLETED TO DATE: |  | #REF!
| DATE: | 2025-08-19
| PROJECT: | 12750 Moorpark Street | [6 empty] | 0
| DRAW REQUEST: | 0 | [5 empty] | REMAINING $ IN BUDGET: | #REF!
[8 empty] | REVISED SCHEDULE OF VALUES: | #REF!
| DESCRIPTION OF WORK |  | SCHEDULED VALUES | PREVIOUS | + / - CHANGES | REVISED VALUES | REMAINING | DRAW | COMPLETED AND
|  |  |  | CHANGES |  |  | BUDGET | 20 | STORED TO DATE
1 | Architect |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
2 | Surveying |  | 25000 | 0 | 0 | 25000 | 25000 | 0 | 0
3 | Soil Engineer |  | 30000 | 0 | 0 | 30000 | 30000 | 0 | 0
4 | Plan Check Fees |  | 30000 | 0 | 0 | 30000 | 30000 | 0 | 0
6 | Utility Setup Fees |  | 75000 | 0 | 0 | 75000 | 75000 | 0 | 0
7 | Deputy Inspections |  | 35 | 0 | 0 | 35 | 35 | 0 | 0
8 | Admin & Legal |  | 25000 | 0 | 0 | 25000 | 25000 | 0 | 0
9 | Structural Engineer |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
10 | Civil Engineer |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
12 | Landscape Architect |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
13 | MEP Engineer |  | 20000 | 0 | 0 | 20000 | 20000 | 0 | 0
14 | Quimby Fee |  | 382500 | 0 | 0 | 382500 | 382500 | 0 | 0
15 | Tenant Buyouts |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Impact Fees |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Insurance (builders risk) |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
18 | Development Fee |  | 7000 | 0 | 0 | 7000 | 7000 | 0 | 0
19 | General Conditions - Manpower (Allowance) |  | 592020.54 | 0 | 0 | 592020.54 | 592020.54 | 0 | 0
20 | Demolition |  | 79500 | 0 | 0 | 79500 | 79500 | 0 | 0
21 | Land Surveyor-Allowance |  | 11000 | 0 | 0 | 11000 | 11000 | 0 | 0
22 | Structural Concrete |  | 327470 | 0 | 0 | 327470 | 327470 | 0 | 0
23 | Spoils removal-Allowance |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
24 | Lightweight Concrete |  | 60042 | 0 | 0 | 60042 | 60042 | 0 | 0
25 | Concrete Masonry Unit (CMU) |  | 143700 | 0 | 0 | 143700 | 143700 | 0 | 0
26 | Stone Facing - Brick Veneer |  | 13055 | 0 | 0 | 13055 | 13055 | 0 | 0
27 | Structural Steel Fabricator Contractor |  | 33988.02 | 0 | 0 | 33988.02 | 33988.02 | 0 | 0
28 | Elevator Steel - Allowance |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
29 | Decorative Metals-Allowance |  | 75000 | 0 | 0 | 75000 | 75000 | 0 | 0
30 | Glass Railing-Allowance |  | 35000 | 0 | 0 | 35000 | 35000 | 0 | 0
31 | Rough Carpentry - Material & Labor |  | 970000 | 0 | 0 | 970000 | 970000 | 0 | 0
32 | EBM System-Allowance |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
33 | Below Grade Water Proofing |  | 7600 | 0 | 0 | 7600 | 7600 | 0 | 0
34 | Above Grade Water Proofing |  | 46600 | 0 | 0 | 46600 | 46600 | 0 | 0
35 | Thermal Insulation |  | 58250 | 0 | 0 | 58250 | 58250 | 0 | 0
36 | Roofing |  | 74200 | 0 | 0 | 74200 | 74200 | 0 | 0
37 | Sheet Metal Contractor-Allowance |  | 70000 | 0 | 0 | 70000 | 70000 | 0 | 0
38 | Firestopping-Allowance |  | 3000 | 0 | 0 | 3000 | 3000 | 0 | 0
39 | Joint Sealants-Allowance |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
40 | Doors and Frames |  | 182256 | 0 | 0 | 182256 | 182256 | 0 | 0
41 | Windows - Material |  | 81726.81 | 0 | 0 | 81726.81 | 81726.81 | 0 | 0
42 | Windows - Installation |  | 25900 | 0 | 0 | 25900 | 25900 | 0 | 0
43 | Entrances, Storefronts, and Curtain Walls |  | 8755 | 0 | 0 | 8755 | 8755 | 0 | 0
44 | Drywall and metal stud framing |  | 437990 | 0 | 0 | 437990 | 437990 | 0 | 0
45 | Painting and Coating |  | 130000 | 0 | 0 | 130000 | 130000 | 0 | 0
46 | Flooring |  | 118463 | 0 | 0 | 118463 | 118463 | 0 | 0
47 | Cement Plastering - Stucco-Allowance |  | 275000 | 0 | 0 | 275000 | 275000 | 0 | 0
48 | Scaffolding-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | Signages |  | 11972.11 | 0 | 0 | 11972.11 | 11972.11 | 0 | 0
50 | Bathroom Accesories |  | 13056 | 0 | 0 | 13056 | 13056 | 0 | 0
51 | Fire extinguishers-allowance |  | 10840 | 0 | 0 | 10840 | 10840 | 0 | 0
52 | #REF! |  | 3000 | 0 | 0 | 3000 | 3000 | 0 | 0
53 | Mailboxes |  | 14136 | 0 | 0 | 14136 | 14136 | 0 | 0
54 | Appliances - Material & Installation |  | 129875.28 | 0 | 0 | 129875.28 | 129875.28 | 0 | 0
55 | Countertops-AIIowance |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
56 | Cabinetry-Allowance |  | 103000 | 0 | 0 | 103000 | 103000 | 0 | 0
57 | Elevators |  | 150000 | 0 | 0 | 150000 | 150000 | 0 | 0
58 | Trash Chutes |  | 37409 | 0 | 0 | 37409 | 37409 | 0 | 0
59 | Fire Sprinklers |  | 187300 | 0 | 0 | 187300 | 187300 | 0 | 0
60 | Plumbing- Rough-Allowance |  | 800000 | 0 | 0 | 800000 | 800000 | 0 | 0
62 | Water Submeter-aIIowanee |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
63 | HVAC equipment & Ducting |  | 394800 | 0 | 0 | 394800 | 394800 | 0 | 0
64 | Electrical rough and finish-Allowance |  | 575000 | 0 | 0 | 575000 | 575000 | 0 | 0
66 | Low Voltage- Structured Cabling |  | 32000 | 0 | 0 | 32000 | 32000 | 0 | 0
67 | 2-way communication system (AOR) |  | 19000 | 0 | 0 | 19000 | 19000 | 0 | 0
68 | ERRCS / DAS system |  | 51000 | 0 | 0 | 51000 | 51000 | 0 | 0
69 | Access Control/Main Telephone Entry/Door Chimes-Allowance |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
70 | Fire Detection and Alarm |  | 47250 | 0 | 0 | 47250 | 47250 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
71 | Excavation and Fill |  | 57350 | 0 | 0 | 57350 | 57350 | 0 | 0
72 | Fine Grading-Allowance |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
73 | Site concrete, Site walkways Site Stairs |  | 10500 | 0 | 0 | 10500 | 10500 | 0 | 0
74 | Offsite Concrete-Allowance |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
75 | Striping-Allowance |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
76 | Permeable Pavers |  | 28619.55 | 0 | 0 | 28619.55 | 28619.55 | 0 | 0
77 | Irrigation system-Allowance |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
78 | Planting - Landscaping-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
79 | Fiberglass Planters-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 | CSl-33 (Utilities) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
81 | Sanitary Sewerage-Allowance |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0
82 | Stormwater Utilities-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
83 | Electrical Utilities-Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
84 | GC Fee |  | 806320.04 | 0 | 0 | 806320.04 | 806320.04 | 0 | 0
85 | Contractor's Contingency |  | 689162.43 | 0 | 0 | 689162.43 | 689162.43 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
| TOTAL |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0