## SCHEDULE OF VALUE WORKSHEET
GENESIS CAPITAL
CLIENT: | Angeleno Investments
DATE: | 11.12.2025
PROJECT: | 10910 Huston Street
| DESCRIPTION OF WORK | REHAB BUDGET | PRE-FUNDING COSTS | SCHEDULED VALUES |  | Full Budget |  | Spent To Date
1 | SOFT COSTS |  |  |  |  | OLD | Delta | OLD | Delta
2 | Site Security | 20000 | 9419.37 | 10580.63 |  | 20000 | 0 | 8669.37 | 750
3 | Soils Inspection | 4800 | 4800 | 0 |  | 4800 | 0 | 4800 | 0
4 | Offsites (Transformer) | 20000 | 0 | 20000 |  | 20000 | 0 | 0 | 0
5 | Plan Check Fees | 15000 | 15000 | 0 |  | 15000 | 0 | 12665.22 | 2334.78
6 | Permits | 183553.73 | 183553.73 | 0 |  | 121785.82 | 61767.91 | 73183.5 | 110370.23
7 | Survey | 3805.23 | 3805.23 | 0 |  | 3805.23 | 0 | 0 | 3805.23
8 | Soils Engineer | 6800 | 6800 | 0 |  | 6800 | 0 | 3400 | 3400
9 | Soils Permit + T24 | 2500 | 0 | 2500 |  | 2500 | 0 | 0 | 0
10 | Special Inspections - Deputy | 15000 | 0 | 15000 |  | 15000 | 0 | 0 | 0
11 | Architect | 122917 | 122917 | 0 |  | 113100 | 9817 | 109989.75 | 12927.25
12 | Structural Engineer | 36600 | 36600 | 0 |  | 31600 | 5000 | 31600 | 5000
13 | Structural Observation | 8000 | 0 | 8000 |  | 8000 | 0 | 0 | 0
14 | Civil Engineering | 20000 | 20000 | 0 |  | 20000 | 0 | 18000 | 2000
15 | Grading Permit | 2313.4 | 2313.4 | 0 |  | 2313.4 | 0 | 2313.4 | 0
16 | Landscape Architect/Designer | 4200 | 4200 | 0 |  | 4200 | 0 | 2700 | 1500
17 | Driveway Apron Permit | 2500 | 0 | 2500 |  | 2500 | 0 | 0 | 0
18 | Punch List - Misc. | 21962.77 | 0 | 21962.77 |  | 21983 | -20.23 | 0 | 0
19 | EBM, Low Voltage, Landscape, Waterproofing CA | 23320.08 | 23320.08 | 0 |  | 23320.08 | 0 | 23320.08 | 0
20 | Project Accounting/Tax Filing | 20000 | 7005.99 | 12994.01 |  | 20000 | 0 | 4205.99 | 2800
21 | Legal & Professional Fees | 20000 | 19126.61 | 873.39 |  | 10000 | 10000 | 9126.61 | 10000
22 | Sewer CCTV and inspection | 325 | 325 | 0 |  | 325 | 0 | 0 | 325
23 | Environmental Phase I | 3000 | 3000 | 0 |  | 3000 | 0 | 0 | 3000
24 | Dry Utility Consultant | 17000 | 17000 | 0 |  | 17000 | 0 | 13000 | 4000
25 | Dry Utility Survey | 5000 | 0 | 5000 |  | 5000 | 0 | 0 | 0
26 | MEP | 51000 | 51000 | 0 |  | 46400 | 4600 | 46400 | 4600
27 | Civil Construction Administration | 5000 | 0 | 5000 |  | 5000 | 0 | 0 | 0
28 | Permit Clearances & Agency Reviews | 40000 | 40000 | 0 |  | 40000 | 0 | 0 | 40000
29 | Demo Permit Fees | 500 | 0 | 500 |  | 500 | 0 | 0 | 0
30 | MEP Fees | 4600 | 4600 | 0 |  | 4600 | 0 | 4600 | 0
31 | Agency Signoffs | 7000 | 7000 | 0 |  | 7000 | 0 | 2500 | 4500
32 | Specifications Writer Consultant | 2000 | 0 | 2000 |  | 2000 | 0 | 0 | 0
33 | Construction Consultant | 3500 | 3500 | 0 |  | 3500 | 0 | 3500 | 0
34 | Low Voltage Consultant | 15524 | 0 | 15524 |  | 15000 | 524 | 0 | 0
35 | Photovoltaic Consultant | 5000 | 0 | 5000 |  | 5000 | 0 | 0 | 0
36 | Construction Management / Observation (OO) | 55000 | 5572.1 | 49427.9 |  | 55000 | 0 | 0 | 5572.1
37 | CMFA Startup Fee | 22800 | 0 | 22800 |  | 22800 | 0 | 0 | 0
38 | Non-Profit Start Up Fee | 25000 | 0 | 25000 |  | 25000 | 0 | 0 | 0
39 | CMFA Construction Fee | 12000 | 0 | 12000 |  | 12000 | 0 | 0 | 0
40 | Non-Profit Construction Fee | 10000 | 0 | 10000 |  | 10000 | 0 | 0 | 0
41 | WTE Legal Costs for CMFA & Non-Profit Partner | 20000 | 0 | 20000 | 857521.21 | 20000 | 0 | 0 | 0
42 | HARD COSTS |  |  | 0
43 | GENERAL CONDITIONS | 565545 | 203429.76 | 362115.24 |  | 565545 | 0 | 197892.71 | 5537.05
44 | GENERAL REQUIREMENT | 135922 | 11264.12 | 124657.88 |  | 135922 | 0 | 11264.12 | 0
45 | SITE WORK | 139049.51 | 0 | 139049.51 |  | 139049.51 | 0 | 0 | 0
46 | CONCRETE | 253182 | 0 | 253182 |  | 253182 | 0 | 0 | 0
47 | MASONRY | 3562.64 | 0 | 3562.64 |  | 3562.64 | 0 | 0 | 0
48 | METALS | 324100 | 0 | 324100 |  | 324100 | 0 | 0 | 0
49 | FRAMING | 818554 | 0 | 818554 |  | 818554 | 0 | 0 | 0
50 | COUNTERTOPS | 56930 | 0 | 56930 |  | 56930 | 0 | 0 | 0
51 | CABINETS | 56930 | 0 | 56930 |  | 56930 | 0 | 0 | 0
52 | THERMAL MOISTURE PROTECTION | 173148 | 0 | 173148 |  | 173148 | 0 | 0 | 0
53 | DOORS | 204087.33 | 0 | 204087.33 |  | 204087.33 | 0 | 0 | 0
54 | WINDOWS | 106274.25 | 0 | 106274.25 |  | 106274.25 | 0 | 0 | 0
55 | STUCCO | 208002 | 0 | 208002 |  | 208002 | 0 | 0 | 0
56 | DRYWALL | 416355 | 0 | 416355 |  | 416355 | 0 | 0 | 0
57 | PAINTING | 120700 | 0 | 120700 |  | 120700 | 0 | 0 | 0
58 | FLOORING - common areas | 45150 | 0 | 45150 |  | 45150 | 0 | 0 | 0
59 | FLOORING - Units with baseboards | 93335 | 0 | 93335 |  | 93335 | 0 | 0 | 0
60 | SPECIALTIES | 25109.21 | 0 | 25109.21 |  | 25109.21 | 0 | 0 | 0
61 | EQUIPMENT | 153636 | 0 | 153636 |  | 153636 | 0 | 0 | 0
62 | FURNISHING |  | 0 | 0
63 | FIRE SPRINKLERS | 108500 | 0 | 108500 |  | 108500 | 0 | 0 | 0
64 | FIRE ALARM | 68401 | 0 | 68401 |  | 68401 | 0 | 0 | 0
65 | SOLAR PANELS | 97000 | 0 | 97000 |  | 97000 | 0 | 0 | 0
66 | SECURITY ACCESS & SURVEILLANCE | 136430 | 0 | 136430 |  | 136430 | 0 | 0 | 0
67 | ELEVATORS & LIFT | 174882 | 0 | 174882 |  | 174882 | 0 | 0 | 0
68 | WATER SUBMETER (material) | 12273 |  | 12273 |  | 12273 | 0
69 | WATER SUBMETER (labor) | 0 | 0 | 0
70 | ROUGH PLUMBING | 751927 | 0 | 751927 |  | 751927 | 0 | 0 | 0
71 | FINISH PLUMBING | 90000 | 0 | 90000 |  | 90000 | 0 | 0 | 0
72 | HVAC | 259000 | 0 | 259000 |  | 259000 | 0 | 0 | 0
73 | ELECTRICAL | 880486.32 | 0 | 880486.32 | 6478471.26 | 880486.32 | 0 | 0 | 0
74 | CONTINGENCY | 546491.43 | 17276.23 | 529215.2 |  | 537822.68 | 8668.75 | 17276.23 | 0
75 | INSURANCE (GL w/auto, workers compl) | 97177.07 | 0 | 97177.07 |  | 97177.07 | 0 | 0 | 0
76 | GROSS RECEIPT TAX | 6543.26 | 0 | 6543.26 |  | 6543.26 | 0 | 0 | 0
77 | GC FEE | 388708.28 | 0 | 388708.28 |  | 388708.28 | 0 | 0 | 0
78 | DEVELOPMENT FEE | 340285 | 159761.5 | 180523.5 |  | 335434 | 4851 | 134536 | 25225.5
79 | CARRYING COSTS | 122215 | 29329.47 | 92885.53 |  | 122215 | 0 | 26862.19 | 2467.28
80 | FINANCING COSTS | 0 |  | 0
82 | Open Item | 0 | 0 | 0
83 | Open Item | 0 | 0 | 0
84 | Open Item | 0 | 0 | 0
85 | Open Item | 0 | 0 | 0
86 | Open Item | 0 | 0 | 0
87 | Open Item | 0 | 0 | 0
88 | Open Item | 0 | 0 | 0
89 | Open Item | 0 | 0 | 0
90 | Open Item | 0 | 0 | 0
91 | Open Item | 0 | 0 | 0
92 | Open Item | 0 | 0 | 0
93 | Open Item | 0 | 0 | 0
94 | Open Item | 0 | 0 | 0
95 | Open Item | 0 | 0 | 0
96 | Open Item | 0 | 0 | 0
97 | Open Item | 0 | 0 | 0
98 | Open Item | 0 | 0 | 0
99 | Open Item | 0 | 0 | 0
| TOTAL | 8837412.51 | 1011919.59 | 7825492.92
CONTINGENCY NOTE: Hard cost $323,923.56 + Soft cost $38,386.06 + Schedule $184181.97 = $546,491.43 / Cost spent $2,444.53 + $14,831 = $17,276.23

## Draw #1
GENESIS CAPITAL DRAW REQUEST FORM
| CLIENT: | Angeleno Investments |  |  |  |  | TOTAL COMPLETED TO DATE: | 0
| PROJECT: | 10910 Huston Street |  |  |  |  | REMAINING $ IN BUDGET: | #REF!
| DATE: | 2025-11-17 |  |  |  |  | ORIGINAL SCHEDULE OF VALUES: | #REF!
| DRAW REQUEST: | 0 |  |  |  |  | CHANGE ORDERS: | 0
[7 empty] | REVISED SCHEDULE OF VALUES: | #REF!
| DESCRIPTION OF WORK |  | SCHEDULED VALUES | + / - CHANGES | REVISED VALUES | REMAINING | DRAW | COMPLETED AND
[6 empty] | $ PER BUDGET | 1 | STORED TO DATE
1 | SOFT COSTS |  | 0 | 0 | 0 | 0 | 0 | 0
2 | Site Security |  | 10580.63 | 0 | 10580.63 | 10580.63 | 0 | 0
3 | Soils Inspection |  | 0 | 0 | 0 | 0 | 0 | 0
4 | Offsites (Transformer) |  | 20000 | 0 | 20000 | 20000 | 0 | 0
5 | Plan Check Fees |  | 0 | 0 | 0 | 0 | 0 | 0
6 | Permits |  | 0 | 0 | 0 | 0 | 0 | 0
7 | Survey |  | 0 | 0 | 0 | 0 | 0 | 0
8 | Soils Engineer |  | 0 | 0 | 0 | 0 | 0 | 0
9 | Soils Permit + T24 |  | 2500 | 0 | 2500 | 2500 | 0 | 0
10 | Special Inspections - Deputy |  | 15000 | 0 | 15000 | 15000 | 0 | 0
11 | Architect |  | 0 | 0 | 0 | 0 | 0 | 0
12 | Structural Engineer |  | 0 | 0 | 0 | 0 | 0 | 0
13 | Structural Observation |  | 8000 | 0 | 8000 | 8000 | 0 | 0
14 | Civil Engineering |  | 0 | 0 | 0 | 0 | 0 | 0
15 | Grading Permit |  | 0 | 0 | 0 | 0 | 0 | 0
16 | Landscape Architect/Designer |  | 0 | 0 | 0 | 0 | 0 | 0
17 | Driveway Apron Permit |  | 2500 | 0 | 2500 | 2500 | 0 | 0
18 | Punch List - Misc. |  | 21962.77 | 0 | 21962.77 | 21962.77 | 0 | 0
19 | EBM, Low Voltage, Landscape, Waterproofing CA |  | 0 | 0 | 0 | 0 | 0 | 0
20 | Project Accounting/Tax Filing |  | 12994.01 | 0 | 12994.01 | 12994.01 | 0 | 0
21 | Legal & Professional Fees |  | 873.39 | 0 | 873.39 | 873.39 | 0 | 0
22 | Sewer CCTV and inspection |  | 0 | 0 | 0 | 0 | 0 | 0
23 | Environmental Phase I |  | 0 | 0 | 0 | 0 | 0 | 0
24 | Dry Utility Consultant |  | 0 | 0 | 0 | 0 | 0 | 0
25 | Dry Utility Survey |  | 5000 | 0 | 5000 | 5000 | 0 | 0
26 | MEP |  | 0 | 0 | 0 | 0 | 0 | 0
27 | Civil Construction Administration |  | 5000 | 0 | 5000 | 5000 | 0 | 0
28 | Permit Clearances & Agency Reviews |  | 0 | 0 | 0 | 0 | 0 | 0
29 | Demo Permit Fees |  | 500 | 0 | 500 | 500 | 0 | 0
30 | MEP Fees |  | 0 | 0 | 0 | 0 | 0 | 0
31 | Agency Signoffs |  | 0 | 0 | 0 | 0 | 0 | 0
32 | Specifications Writer Consultant |  | 2000 | 0 | 2000 | 2000 | 0 | 0
33 | Construction Consultant |  | 0 | 0 | 0 | 0 | 0 | 0
34 | Low Voltage Consultant |  | 15524 | 0 | 15524 | 15524 | 0 | 0
35 | Photovoltaic Consultant |  | 5000 | 0 | 5000 | 5000 | 0 | 0
36 | Construction Management / Observation (OO) |  | 49427.9 | 0 | 49427.9 | 49427.9 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | 0
37 | CMFA Startup Fee |  | 22800 | 0 | 22800 | 22800 | 0 | 0
38 | Non-Profit Start Up Fee |  | 25000 | 0 | 25000 | 25000 | 0 | 0
39 | CMFA Construction Fee |  | 12000 | 0 | 12000 | 12000 | 0 | 0
40 | Non-Profit Construction Fee |  | 10000 | 0 | 10000 | 10000 | 0 | 0
41 | WTE Legal Costs for CMFA & Non-Profit Partner |  | 20000 | 0 | 20000 | 20000 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | 0
43 | GENERAL CONDITIONS |  | 362115.24 | 0 | 362115.24 | 362115.24 | 0 | 0
44 | GENERAL REQUIREMENT |  | 124657.88 | 0 | 124657.88 | 124657.88 | 0 | 0
45 | SITE WORK |  | 139049.51 | 0 | 139049.51 | 139049.51 | 0 | 0
46 | CONCRETE |  | 253182 | 0 | 253182 | 253182 | 0 | 0
47 | MASONRY |  | 3562.64 | 0 | 3562.64 | 3562.64 | 0 | 0
48 | METALS |  | 324100 | 0 | 324100 | 324100 | 0 | 0
49 | FRAMING |  | 818554 | 0 | 818554 | 818554 | 0 | 0
50 | COUNTERTOPS |  | 56930 | 0 | 56930 | 56930 | 0 | 0
51 | CABINETS |  | 56930 | 0 | 56930 | 56930 | 0 | 0
52 | THERMAL MOISTURE PROTECTION |  | 173148 | 0 | 173148 | 173148 | 0 | 0
53 | DOORS |  | 204087.33 | 0 | 204087.33 | 204087.33 | 0 | 0
54 | WINDOWS |  | 106274.25 | 0 | 106274.25 | 106274.25 | 0 | 0
55 | STUCCO |  | 208002 | 0 | 208002 | 208002 | 0 | 0
56 | DRYWALL |  | 416355 | 0 | 416355 | 416355 | 0 | 0
57 | PAINTING |  | 120700 | 0 | 120700 | 120700 | 0 | 0
58 | FLOORING - common areas |  | 45150 | 0 | 45150 | 45150 | 0 | 0
59 | FLOORING - Units with baseboards |  | 93335 | 0 | 93335 | 93335 | 0 | 0
60 | SPECIALTIES |  | 25109.21 | 0 | 25109.21 | 25109.21 | 0 | 0
61 | EQUIPMENT |  | 153636 | 0 | 153636 | 153636 | 0 | 0
62 | FURNISHING |  | 0 | 0 | 0 | 0 | 0 | 0
63 | FIRE SPRINKLERS |  | 108500 | 0 | 108500 | 108500 | 0 | 0
64 | FIRE ALARM |  | 68401 | 0 | 68401 | 68401 | 0 | 0
65 | SOLAR PANELS |  | 97000 | 0 | 97000 | 97000 | 0 | 0
66 | SECURITY ACCESS & SURVEILLANCE |  | 136430 | 0 | 136430 | 136430 | 0 | 0
67 | ELEVATORS & LIFT |  | 174882 | 0 | 174882 | 174882 | 0 | 0
68 | WATER SUBMETER (material) |  | 12273 | 0 | 12273 | 12273 | 0 | 0
69 | WATER SUBMETER (labor) |  | 0 | 0 | 0 | 0 | 0 | 0
70 | ROUGH PLUMBING |  | 751927 | 0 | 751927 | 751927 | 0 | 0
71 | FINISH PLUMBING |  | 90000 | 0 | 90000 | 90000 | 0 | 0
72 | HVAC |  | 259000 | 0 | 259000 | 259000 | 0 | 0
73 | ELECTRICAL |  | 880486.32 | 0 | 880486.32 | 880486.32 | 0 | 0
74 | CONTINGENCY |  | 529215.2 | 0 | 529215.2 | 529215.2 | 0 | 0
75 | INSURANCE (GL w/auto, workers compl) |  | 97177.07 | 0 | 97177.07 | 97177.07 | 0 | 0
76 | GROSS RECEIPT TAX |  | 6543.26 | 0 | 6543.26 | 6543.26 | 0 | 0
77 | GC FEE |  | 388708.28 | 0 | 388708.28 | 388708.28 | 0 | 0
78 | DEVELOPMENT FEE |  | 180523.5 | 0 | 180523.5 | 180523.5 | 0 | 0
79 | CARRYING COSTS |  | 92885.53 | 0 | 92885.53 | 92885.53 | 0 | 0
80 | FINANCING COSTS |  | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | 0
82 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0
83 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0
84 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0
85 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0
86 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0
87 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0
88 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0
89 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0
90 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0
91 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0
92 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0
93 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0
94 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0
95 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0
96 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0
97 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0
98 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0
99 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | 0
| TOTAL |  | #REF! | 0 | #REF! | #REF! | 0 | 0

## Draw #2
GENESIS CAPITAL DRAW FORM
| CLIENT: | Angeleno Investments | [5 empty] | TOTAL COMPLETED TO DATE: | 0 | #REF!
| DATE: | 2025-11-17 | [5 empty] | REMAINING $ IN BUDGET: | #REF!
| PROJECT: | 10910 Huston Street | [5 empty] | ORIGINAL SCHEDULE OF VALUES: | #REF!
| DRAW REQUEST: | 0 | [5 empty] | CHANGE ORDERS: | 0
[8 empty] | REVISED SCHEDULE OF VALUES: | #REF!
| DESCRIPTION OF WORK |  | SCHEDULED VALUES | PREVIOUS | + / - CHANGES | REVISED VALUES | REMAINING | DRAW | COMPLETED AND
|  |  |  | CHANGES |  |  | BUDGET | 2 | STORED TO DATE
1 | SOFT COSTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Site Security |  | 10580.63 | 0 | 0 | 10580.63 | 10580.63 | 0 | 0
3 | Soils Inspection |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Offsites (Transformer) |  | 20000 | 0 | 0 | 20000 | 20000 | 0 | 0
5 | Plan Check Fees |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Permits |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Survey |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Soils Engineer |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Soils Permit + T24 |  | 2500 | 0 | 0 | 2500 | 2500 | 0 | 0
10 | Special Inspections - Deputy |  | 15000 | 0 | 0 | 15000 | 15000 | 0 | 0
11 | Architect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Structural Engineer |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Structural Observation |  | 8000 | 0 | 0 | 8000 | 8000 | 0 | 0
14 | Civil Engineering |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | Grading Permit |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Landscape Architect/Designer |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Driveway Apron Permit |  | 2500 | 0 | 0 | 2500 | 2500 | 0 | 0
18 | Punch List - Misc. |  | 21962.77 | 0 | 0 | 21962.77 | 21962.77 | 0 | 0
19 | EBM, Low Voltage, Landscape, Waterproofing CA |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | Project Accounting/Tax Filing |  | 12994.01 | 0 | 0 | 12994.01 | 12994.01 | 0 | 0
21 | Legal & Professional Fees |  | 873.39 | 0 | 0 | 873.39 | 873.39 | 0 | 0
22 | Sewer CCTV and inspection |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | Environmental Phase I |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | Dry Utility Consultant |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | Dry Utility Survey |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
26 | MEP |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | Civil Construction Administration |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
28 | Permit Clearances & Agency Reviews |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | Demo Permit Fees |  | 500 | 0 | 0 | 500 | 500 | 0 | 0
30 | MEP Fees |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | Agency Signoffs |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | Specifications Writer Consultant |  | 2000 | 0 | 0 | 2000 | 2000 | 0 | 0
33 | Construction Consultant |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | Low Voltage Consultant |  | 15524 | 0 | 0 | 15524 | 15524 | 0 | 0
35 | Photovoltaic Consultant |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
36 | Construction Management / Observation (OO) |  | 49427.9 | 0 | 0 | 49427.9 | 49427.9 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
37 | CMFA Startup Fee |  | 22800 | 0 | 0 | 22800 | 22800 | 0 | 0
38 | Non-Profit Start Up Fee |  | 25000 | 0 | 0 | 25000 | 25000 | 0 | 0
39 | CMFA Construction Fee |  | 12000 | 0 | 0 | 12000 | 12000 | 0 | 0
40 | Non-Profit Construction Fee |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
41 | WTE Legal Costs for CMFA & Non-Profit Partner |  | 20000 | 0 | 0 | 20000 | 20000 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
43 | GENERAL CONDITIONS |  | 362115.24 | 0 | 0 | 362115.24 | 362115.24 | 0 | 0
44 | GENERAL REQUIREMENT |  | 124657.88 | 0 | 0 | 124657.88 | 124657.88 | 0 | 0
45 | SITE WORK |  | 139049.51 | 0 | 0 | 139049.51 | 139049.51 | 0 | 0
46 | CONCRETE |  | 253182 | 0 | 0 | 253182 | 253182 | 0 | 0
47 | MASONRY |  | 3562.64 | 0 | 0 | 3562.64 | 3562.64 | 0 | 0
48 | METALS |  | 324100 | 0 | 0 | 324100 | 324100 | 0 | 0
49 | FRAMING |  | 818554 | 0 | 0 | 818554 | 818554 | 0 | 0
50 | COUNTERTOPS |  | 56930 | 0 | 0 | 56930 | 56930 | 0 | 0
51 | CABINETS |  | 56930 | 0 | 0 | 56930 | 56930 | 0 | 0
52 | THERMAL MOISTURE PROTECTION |  | 173148 | 0 | 0 | 173148 | 173148 | 0 | 0
53 | DOORS |  | 204087.33 | 0 | 0 | 204087.33 | 204087.33 | 0 | 0
54 | WINDOWS |  | 106274.25 | 0 | 0 | 106274.25 | 106274.25 | 0 | 0
55 | STUCCO |  | 208002 | 0 | 0 | 208002 | 208002 | 0 | 0
56 | DRYWALL |  | 416355 | 0 | 0 | 416355 | 416355 | 0 | 0
57 | PAINTING |  | 120700 | 0 | 0 | 120700 | 120700 | 0 | 0
58 | FLOORING - common areas |  | 45150 | 0 | 0 | 45150 | 45150 | 0 | 0
59 | FLOORING - Units with baseboards |  | 93335 | 0 | 0 | 93335 | 93335 | 0 | 0
60 | SPECIALTIES |  | 25109.21 | 0 | 0 | 25109.21 | 25109.21 | 0 | 0
61 | EQUIPMENT |  | 153636 | 0 | 0 | 153636 | 153636 | 0 | 0
62 | FURNISHING |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
63 | FIRE SPRINKLERS |  | 108500 | 0 | 0 | 108500 | 108500 | 0 | 0
64 | FIRE ALARM |  | 68401 | 0 | 0 | 68401 | 68401 | 0 | 0
65 | SOLAR PANELS |  | 97000 | 0 | 0 | 97000 | 97000 | 0 | 0
66 | SECURITY ACCESS & SURVEILLANCE |  | 136430 | 0 | 0 | 136430 | 136430 | 0 | 0
67 | ELEVATORS & LIFT |  | 174882 | 0 | 0 | 174882 | 174882 | 0 | 0
68 | WATER SUBMETER (material) |  | 12273 | 0 | 0 | 12273 | 12273 | 0 | 0
69 | WATER SUBMETER (labor) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
70 | ROUGH PLUMBING |  | 751927 | 0 | 0 | 751927 | 751927 | 0 | 0
71 | FINISH PLUMBING |  | 90000 | 0 | 0 | 90000 | 90000 | 0 | 0
72 | HVAC |  | 259000 | 0 | 0 | 259000 | 259000 | 0 | 0
73 | ELECTRICAL |  | 880486.32 | 0 | 0 | 880486.32 | 880486.32 | 0 | 0
74 | CONTINGENCY |  | 529215.2 | 0 | 0 | 529215.2 | 529215.2 | 0 | 0
75 | INSURANCE (GL w/auto, workers compl) |  | 97177.07 | 0 | 0 | 97177.07 | 97177.07 | 0 | 0
76 | GROSS RECEIPT TAX |  | 6543.26 | 0 | 0 | 6543.26 | 6543.26 | 0 | 0
77 | GC FEE |  | 388708.28 | 0 | 0 | 388708.28 | 388708.28 | 0 | 0
78 | DEVELOPMENT FEE |  | 180523.5 | 0 | 0 | 180523.5 | 180523.5 | 0 | 0
79 | CARRYING COSTS |  | 92885.53 | 0 | 0 | 92885.53 | 92885.53 | 0 | 0
80 | FINANCING COSTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
82 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
83 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
84 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
85 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
86 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
87 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
88 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
89 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
90 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
91 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
92 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
93 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
94 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
95 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
96 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
97 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
98 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
99 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
| TOTAL |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0

## Draw #3
GENESIS CAPITAL DRAW FORM
| CLIENT: | Angeleno Investments | [5 empty] | TOTAL COMPLETED TO DATE: | 0 | #REF!
| DATE: | 2025-11-17 | [5 empty] | REMAINING $ IN BUDGET: | #REF!
| PROJECT: | 10910 Huston Street | [5 empty] | ORIGINAL SCHEDULE OF VALUES: | #REF!
| DRAW REQUEST: | 0 | [5 empty] | CHANGE ORDERS: | 0
[8 empty] | REVISED SCHEDULE OF VALUES: | #REF!
| DESCRIPTION OF WORK |  | SCHEDULED VALUES | PREVIOUS | + / - CHANGES | REVISED VALUES | REMAINING | DRAW | COMPLETED AND
|  |  |  | CHANGES |  |  | BUDGET | 3 | STORED TO DATE
1 | SOFT COSTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Site Security |  | 10580.63 | 0 | 0 | 10580.63 | 10580.63 | 0 | 0
3 | Soils Inspection |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Offsites (Transformer) |  | 20000 | 0 | 0 | 20000 | 20000 | 0 | 0
5 | Plan Check Fees |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Permits |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Survey |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Soils Engineer |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Soils Permit + T24 |  | 2500 | 0 | 0 | 2500 | 2500 | 0 | 0
10 | Special Inspections - Deputy |  | 15000 | 0 | 0 | 15000 | 15000 | 0 | 0
11 | Architect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Structural Engineer |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Structural Observation |  | 8000 | 0 | 0 | 8000 | 8000 | 0 | 0
14 | Civil Engineering |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | Grading Permit |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Landscape Architect/Designer |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Driveway Apron Permit |  | 2500 | 0 | 0 | 2500 | 2500 | 0 | 0
18 | Punch List - Misc. |  | 21962.77 | 0 | 0 | 21962.77 | 21962.77 | 0 | 0
19 | EBM, Low Voltage, Landscape, Waterproofing CA |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | Project Accounting/Tax Filing |  | 12994.01 | 0 | 0 | 12994.01 | 12994.01 | 0 | 0
21 | Legal & Professional Fees |  | 873.39 | 0 | 0 | 873.39 | 873.39 | 0 | 0
22 | Sewer CCTV and inspection |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | Environmental Phase I |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | Dry Utility Consultant |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | Dry Utility Survey |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
26 | MEP |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | Civil Construction Administration |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
28 | Permit Clearances & Agency Reviews |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | Demo Permit Fees |  | 500 | 0 | 0 | 500 | 500 | 0 | 0
30 | MEP Fees |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | Agency Signoffs |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | Specifications Writer Consultant |  | 2000 | 0 | 0 | 2000 | 2000 | 0 | 0
33 | Construction Consultant |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | Low Voltage Consultant |  | 15524 | 0 | 0 | 15524 | 15524 | 0 | 0
35 | Photovoltaic Consultant |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
36 | Construction Management / Observation (OO) |  | 49427.9 | 0 | 0 | 49427.9 | 49427.9 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
37 | CMFA Startup Fee |  | 22800 | 0 | 0 | 22800 | 22800 | 0 | 0
38 | Non-Profit Start Up Fee |  | 25000 | 0 | 0 | 25000 | 25000 | 0 | 0
39 | CMFA Construction Fee |  | 12000 | 0 | 0 | 12000 | 12000 | 0 | 0
40 | Non-Profit Construction Fee |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
41 | WTE Legal Costs for CMFA & Non-Profit Partner |  | 20000 | 0 | 0 | 20000 | 20000 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
43 | GENERAL CONDITIONS |  | 362115.24 | 0 | 0 | 362115.24 | 362115.24 | 0 | 0
44 | GENERAL REQUIREMENT |  | 124657.88 | 0 | 0 | 124657.88 | 124657.88 | 0 | 0
45 | SITE WORK |  | 139049.51 | 0 | 0 | 139049.51 | 139049.51 | 0 | 0
46 | CONCRETE |  | 253182 | 0 | 0 | 253182 | 253182 | 0 | 0
47 | MASONRY |  | 3562.64 | 0 | 0 | 3562.64 | 3562.64 | 0 | 0
48 | METALS |  | 324100 | 0 | 0 | 324100 | 324100 | 0 | 0
49 | FRAMING |  | 818554 | 0 | 0 | 818554 | 818554 | 0 | 0
50 | COUNTERTOPS |  | 56930 | 0 | 0 | 56930 | 56930 | 0 | 0
51 | CABINETS |  | 56930 | 0 | 0 | 56930 | 56930 | 0 | 0
52 | THERMAL MOISTURE PROTECTION |  | 173148 | 0 | 0 | 173148 | 173148 | 0 | 0
53 | DOORS |  | 204087.33 | 0 | 0 | 204087.33 | 204087.33 | 0 | 0
54 | WINDOWS |  | 106274.25 | 0 | 0 | 106274.25 | 106274.25 | 0 | 0
55 | STUCCO |  | 208002 | 0 | 0 | 208002 | 208002 | 0 | 0
56 | DRYWALL |  | 416355 | 0 | 0 | 416355 | 416355 | 0 | 0
57 | PAINTING |  | 120700 | 0 | 0 | 120700 | 120700 | 0 | 0
58 | FLOORING - common areas |  | 45150 | 0 | 0 | 45150 | 45150 | 0 | 0
59 | FLOORING - Units with baseboards |  | 93335 | 0 | 0 | 93335 | 93335 | 0 | 0
60 | SPECIALTIES |  | 25109.21 | 0 | 0 | 25109.21 | 25109.21 | 0 | 0
61 | EQUIPMENT |  | 153636 | 0 | 0 | 153636 | 153636 | 0 | 0
62 | FURNISHING |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
63 | FIRE SPRINKLERS |  | 108500 | 0 | 0 | 108500 | 108500 | 0 | 0
64 | FIRE ALARM |  | 68401 | 0 | 0 | 68401 | 68401 | 0 | 0
65 | SOLAR PANELS |  | 97000 | 0 | 0 | 97000 | 97000 | 0 | 0
66 | SECURITY ACCESS & SURVEILLANCE |  | 136430 | 0 | 0 | 136430 | 136430 | 0 | 0
67 | ELEVATORS & LIFT |  | 174882 | 0 | 0 | 174882 | 174882 | 0 | 0
68 | WATER SUBMETER (material) |  | 12273 | 0 | 0 | 12273 | 12273 | 0 | 0
69 | WATER SUBMETER (labor) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
70 | ROUGH PLUMBING |  | 751927 | 0 | 0 | 751927 | 751927 | 0 | 0
71 | FINISH PLUMBING |  | 90000 | 0 | 0 | 90000 | 90000 | 0 | 0
72 | HVAC |  | 259000 | 0 | 0 | 259000 | 259000 | 0 | 0
73 | ELECTRICAL |  | 880486.32 | 0 | 0 | 880486.32 | 880486.32 | 0 | 0
74 | CONTINGENCY |  | 529215.2 | 0 | 0 | 529215.2 | 529215.2 | 0 | 0
75 | INSURANCE (GL w/auto, workers compl) |  | 97177.07 | 0 | 0 | 97177.07 | 97177.07 | 0 | 0
76 | GROSS RECEIPT TAX |  | 6543.26 | 0 | 0 | 6543.26 | 6543.26 | 0 | 0
77 | GC FEE |  | 388708.28 | 0 | 0 | 388708.28 | 388708.28 | 0 | 0
78 | DEVELOPMENT FEE |  | 180523.5 | 0 | 0 | 180523.5 | 180523.5 | 0 | 0
79 | CARRYING COSTS |  | 92885.53 | 0 | 0 | 92885.53 | 92885.53 | 0 | 0
80 | FINANCING COSTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
82 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
83 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
84 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
85 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
86 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
87 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
88 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
89 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
90 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
91 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
92 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
93 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
94 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
95 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
96 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
97 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
98 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
99 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
| TOTAL |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0

## Draw #4
GENESIS CAPITAL DRAW FORM
| CLIENT: | Angeleno Investments | [5 empty] | TOTAL COMPLETED TO DATE: | 0 | #REF!
| DATE: | 2025-11-17 | [5 empty] | REMAINING $ IN BUDGET: | #REF!
| PROJECT: | 10910 Huston Street | [5 empty] | ORIGINAL SCHEDULE OF VALUES: | #REF!
| DRAW REQUEST: | 0 | [5 empty] | CHANGE ORDERS: | 0
[8 empty] | REVISED SCHEDULE OF VALUES: | #REF!
| DESCRIPTION OF WORK |  | SCHEDULED VALUES | PREVIOUS | + / - CHANGES | REVISED VALUES | REMAINING | DRAW | COMPLETED AND
|  |  |  | CHANGES |  |  | BUDGET | 4 | STORED TO DATE
1 | SOFT COSTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Site Security |  | 10580.63 | 0 | 0 | 10580.63 | 10580.63 | 0 | 0
3 | Soils Inspection |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Offsites (Transformer) |  | 20000 | 0 | 0 | 20000 | 20000 | 0 | 0
5 | Plan Check Fees |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Permits |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Survey |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Soils Engineer |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Soils Permit + T24 |  | 2500 | 0 | 0 | 2500 | 2500 | 0 | 0
10 | Special Inspections - Deputy |  | 15000 | 0 | 0 | 15000 | 15000 | 0 | 0
11 | Architect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Structural Engineer |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Structural Observation |  | 8000 | 0 | 0 | 8000 | 8000 | 0 | 0
14 | Civil Engineering |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | Grading Permit |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Landscape Architect/Designer |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Driveway Apron Permit |  | 2500 | 0 | 0 | 2500 | 2500 | 0 | 0
18 | Punch List - Misc. |  | 21962.77 | 0 | 0 | 21962.77 | 21962.77 | 0 | 0
19 | EBM, Low Voltage, Landscape, Waterproofing CA |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | Project Accounting/Tax Filing |  | 12994.01 | 0 | 0 | 12994.01 | 12994.01 | 0 | 0
21 | Legal & Professional Fees |  | 873.39 | 0 | 0 | 873.39 | 873.39 | 0 | 0
22 | Sewer CCTV and inspection |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | Environmental Phase I |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | Dry Utility Consultant |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | Dry Utility Survey |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
26 | MEP |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | Civil Construction Administration |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
28 | Permit Clearances & Agency Reviews |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | Demo Permit Fees |  | 500 | 0 | 0 | 500 | 500 | 0 | 0
30 | MEP Fees |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | Agency Signoffs |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | Specifications Writer Consultant |  | 2000 | 0 | 0 | 2000 | 2000 | 0 | 0
33 | Construction Consultant |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | Low Voltage Consultant |  | 15524 | 0 | 0 | 15524 | 15524 | 0 | 0
35 | Photovoltaic Consultant |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
36 | Construction Management / Observation (OO) |  | 49427.9 | 0 | 0 | 49427.9 | 49427.9 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
37 | CMFA Startup Fee |  | 22800 | 0 | 0 | 22800 | 22800 | 0 | 0
38 | Non-Profit Start Up Fee |  | 25000 | 0 | 0 | 25000 | 25000 | 0 | 0
39 | CMFA Construction Fee |  | 12000 | 0 | 0 | 12000 | 12000 | 0 | 0
40 | Non-Profit Construction Fee |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
41 | WTE Legal Costs for CMFA & Non-Profit Partner |  | 20000 | 0 | 0 | 20000 | 20000 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
43 | GENERAL CONDITIONS |  | 362115.24 | 0 | 0 | 362115.24 | 362115.24 | 0 | 0
44 | GENERAL REQUIREMENT |  | 124657.88 | 0 | 0 | 124657.88 | 124657.88 | 0 | 0
45 | SITE WORK |  | 139049.51 | 0 | 0 | 139049.51 | 139049.51 | 0 | 0
46 | CONCRETE |  | 253182 | 0 | 0 | 253182 | 253182 | 0 | 0
47 | MASONRY |  | 3562.64 | 0 | 0 | 3562.64 | 3562.64 | 0 | 0
48 | METALS |  | 324100 | 0 | 0 | 324100 | 324100 | 0 | 0
49 | FRAMING |  | 818554 | 0 | 0 | 818554 | 818554 | 0 | 0
50 | COUNTERTOPS |  | 56930 | 0 | 0 | 56930 | 56930 | 0 | 0
51 | CABINETS |  | 56930 | 0 | 0 | 56930 | 56930 | 0 | 0
52 | THERMAL MOISTURE PROTECTION |  | 173148 | 0 | 0 | 173148 | 173148 | 0 | 0
53 | DOORS |  | 204087.33 | 0 | 0 | 204087.33 | 204087.33 | 0 | 0
54 | WINDOWS |  | 106274.25 | 0 | 0 | 106274.25 | 106274.25 | 0 | 0
55 | STUCCO |  | 208002 | 0 | 0 | 208002 | 208002 | 0 | 0
56 | DRYWALL |  | 416355 | 0 | 0 | 416355 | 416355 | 0 | 0
57 | PAINTING |  | 120700 | 0 | 0 | 120700 | 120700 | 0 | 0
58 | FLOORING - common areas |  | 45150 | 0 | 0 | 45150 | 45150 | 0 | 0
59 | FLOORING - Units with baseboards |  | 93335 | 0 | 0 | 93335 | 93335 | 0 | 0
60 | SPECIALTIES |  | 25109.21 | 0 | 0 | 25109.21 | 25109.21 | 0 | 0
61 | EQUIPMENT |  | 153636 | 0 | 0 | 153636 | 153636 | 0 | 0
62 | FURNISHING |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
63 | FIRE SPRINKLERS |  | 108500 | 0 | 0 | 108500 | 108500 | 0 | 0
64 | FIRE ALARM |  | 68401 | 0 | 0 | 68401 | 68401 | 0 | 0
65 | SOLAR PANELS |  | 97000 | 0 | 0 | 97000 | 97000 | 0 | 0
66 | SECURITY ACCESS & SURVEILLANCE |  | 136430 | 0 | 0 | 136430 | 136430 | 0 | 0
67 | ELEVATORS & LIFT |  | 174882 | 0 | 0 | 174882 | 174882 | 0 | 0
68 | WATER SUBMETER (material) |  | 12273 | 0 | 0 | 12273 | 12273 | 0 | 0
69 | WATER SUBMETER (labor) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
70 | ROUGH PLUMBING |  | 751927 | 0 | 0 | 751927 | 751927 | 0 | 0
71 | FINISH PLUMBING |  | 90000 | 0 | 0 | 90000 | 90000 | 0 | 0
72 | HVAC |  | 259000 | 0 | 0 | 259000 | 259000 | 0 | 0
73 | ELECTRICAL |  | 880486.32 | 0 | 0 | 880486.32 | 880486.32 | 0 | 0
74 | CONTINGENCY |  | 529215.2 | 0 | 0 | 529215.2 | 529215.2 | 0 | 0
75 | INSURANCE (GL w/auto, workers compl) |  | 97177.07 | 0 | 0 | 97177.07 | 97177.07 | 0 | 0
76 | GROSS RECEIPT TAX |  | 6543.26 | 0 | 0 | 6543.26 | 6543.26 | 0 | 0
77 | GC FEE |  | 388708.28 | 0 | 0 | 388708.28 | 388708.28 | 0 | 0
78 | DEVELOPMENT FEE |  | 180523.5 | 0 | 0 | 180523.5 | 180523.5 | 0 | 0
79 | CARRYING COSTS |  | 92885.53 | 0 | 0 | 92885.53 | 92885.53 | 0 | 0
80 | FINANCING COSTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
82 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
83 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
84 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
85 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
86 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
87 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
88 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
89 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
90 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
91 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
92 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
93 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
94 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
95 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
96 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
97 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
98 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
99 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
| TOTAL |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0

## Draw #5
GENESIS CAPITAL DRAW FORM
| CLIENT: | Angeleno Investments | [5 empty] | TOTAL COMPLETED TO DATE: | 0 | #REF!
| DATE: | 2025-11-17 | [5 empty] | REMAINING $ IN BUDGET: | #REF!
| PROJECT: | 10910 Huston Street | [5 empty] | ORIGINAL SCHEDULE OF VALUES: | #REF!
| DRAW REQUEST: | 0 | [5 empty] | CHANGE ORDERS: | 0
[8 empty] | REVISED SCHEDULE OF VALUES: | #REF!
| DESCRIPTION OF WORK |  | SCHEDULED VALUES | PREVIOUS | + / - CHANGES | REVISED VALUES | REMAINING | DRAW | COMPLETED AND
|  |  |  | CHANGES |  |  | BUDGET | 5 | STORED TO DATE
1 | SOFT COSTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Site Security |  | 10580.63 | 0 | 0 | 10580.63 | 10580.63 | 0 | 0
3 | Soils Inspection |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Offsites (Transformer) |  | 20000 | 0 | 0 | 20000 | 20000 | 0 | 0
5 | Plan Check Fees |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Permits |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Survey |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Soils Engineer |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Soils Permit + T24 |  | 2500 | 0 | 0 | 2500 | 2500 | 0 | 0
10 | Special Inspections - Deputy |  | 15000 | 0 | 0 | 15000 | 15000 | 0 | 0
11 | Architect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Structural Engineer |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Structural Observation |  | 8000 | 0 | 0 | 8000 | 8000 | 0 | 0
14 | Civil Engineering |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | Grading Permit |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Landscape Architect/Designer |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Driveway Apron Permit |  | 2500 | 0 | 0 | 2500 | 2500 | 0 | 0
18 | Punch List - Misc. |  | 21962.77 | 0 | 0 | 21962.77 | 21962.77 | 0 | 0
19 | EBM, Low Voltage, Landscape, Waterproofing CA |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | Project Accounting/Tax Filing |  | 12994.01 | 0 | 0 | 12994.01 | 12994.01 | 0 | 0
21 | Legal & Professional Fees |  | 873.39 | 0 | 0 | 873.39 | 873.39 | 0 | 0
22 | Sewer CCTV and inspection |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | Environmental Phase I |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | Dry Utility Consultant |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | Dry Utility Survey |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
26 | MEP |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | Civil Construction Administration |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
28 | Permit Clearances & Agency Reviews |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | Demo Permit Fees |  | 500 | 0 | 0 | 500 | 500 | 0 | 0
30 | MEP Fees |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | Agency Signoffs |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | Specifications Writer Consultant |  | 2000 | 0 | 0 | 2000 | 2000 | 0 | 0
33 | Construction Consultant |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | Low Voltage Consultant |  | 15524 | 0 | 0 | 15524 | 15524 | 0 | 0
35 | Photovoltaic Consultant |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
36 | Construction Management / Observation (OO) |  | 49427.9 | 0 | 0 | 49427.9 | 49427.9 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
37 | CMFA Startup Fee |  | 22800 | 0 | 0 | 22800 | 22800 | 0 | 0
38 | Non-Profit Start Up Fee |  | 25000 | 0 | 0 | 25000 | 25000 | 0 | 0
39 | CMFA Construction Fee |  | 12000 | 0 | 0 | 12000 | 12000 | 0 | 0
40 | Non-Profit Construction Fee |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
41 | WTE Legal Costs for CMFA & Non-Profit Partner |  | 20000 | 0 | 0 | 20000 | 20000 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
43 | GENERAL CONDITIONS |  | 362115.24 | 0 | 0 | 362115.24 | 362115.24 | 0 | 0
44 | GENERAL REQUIREMENT |  | 124657.88 | 0 | 0 | 124657.88 | 124657.88 | 0 | 0
45 | SITE WORK |  | 139049.51 | 0 | 0 | 139049.51 | 139049.51 | 0 | 0
46 | CONCRETE |  | 253182 | 0 | 0 | 253182 | 253182 | 0 | 0
47 | MASONRY |  | 3562.64 | 0 | 0 | 3562.64 | 3562.64 | 0 | 0
48 | METALS |  | 324100 | 0 | 0 | 324100 | 324100 | 0 | 0
49 | FRAMING |  | 818554 | 0 | 0 | 818554 | 818554 | 0 | 0
50 | COUNTERTOPS |  | 56930 | 0 | 0 | 56930 | 56930 | 0 | 0
51 | CABINETS |  | 56930 | 0 | 0 | 56930 | 56930 | 0 | 0
52 | THERMAL MOISTURE PROTECTION |  | 173148 | 0 | 0 | 173148 | 173148 | 0 | 0
53 | DOORS |  | 204087.33 | 0 | 0 | 204087.33 | 204087.33 | 0 | 0
54 | WINDOWS |  | 106274.25 | 0 | 0 | 106274.25 | 106274.25 | 0 | 0
55 | STUCCO |  | 208002 | 0 | 0 | 208002 | 208002 | 0 | 0
56 | DRYWALL |  | 416355 | 0 | 0 | 416355 | 416355 | 0 | 0
57 | PAINTING |  | 120700 | 0 | 0 | 120700 | 120700 | 0 | 0
58 | FLOORING - common areas |  | 45150 | 0 | 0 | 45150 | 45150 | 0 | 0
59 | FLOORING - Units with baseboards |  | 93335 | 0 | 0 | 93335 | 93335 | 0 | 0
60 | SPECIALTIES |  | 25109.21 | 0 | 0 | 25109.21 | 25109.21 | 0 | 0
61 | EQUIPMENT |  | 153636 | 0 | 0 | 153636 | 153636 | 0 | 0
62 | FURNISHING |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
63 | FIRE SPRINKLERS |  | 108500 | 0 | 0 | 108500 | 108500 | 0 | 0
64 | FIRE ALARM |  | 68401 | 0 | 0 | 68401 | 68401 | 0 | 0
65 | SOLAR PANELS |  | 97000 | 0 | 0 | 97000 | 97000 | 0 | 0
66 | SECURITY ACCESS & SURVEILLANCE |  | 136430 | 0 | 0 | 136430 | 136430 | 0 | 0
67 | ELEVATORS & LIFT |  | 174882 | 0 | 0 | 174882 | 174882 | 0 | 0
68 | WATER SUBMETER (material) |  | 12273 | 0 | 0 | 12273 | 12273 | 0 | 0
69 | WATER SUBMETER (labor) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
70 | ROUGH PLUMBING |  | 751927 | 0 | 0 | 751927 | 751927 | 0 | 0
71 | FINISH PLUMBING |  | 90000 | 0 | 0 | 90000 | 90000 | 0 | 0
72 | HVAC |  | 259000 | 0 | 0 | 259000 | 259000 | 0 | 0
73 | ELECTRICAL |  | 880486.32 | 0 | 0 | 880486.32 | 880486.32 | 0 | 0
74 | CONTINGENCY |  | 529215.2 | 0 | 0 | 529215.2 | 529215.2 | 0 | 0
75 | INSURANCE (GL w/auto, workers compl) |  | 97177.07 | 0 | 0 | 97177.07 | 97177.07 | 0 | 0
76 | GROSS RECEIPT TAX |  | 6543.26 | 0 | 0 | 6543.26 | 6543.26 | 0 | 0
77 | GC FEE |  | 388708.28 | 0 | 0 | 388708.28 | 388708.28 | 0 | 0
78 | DEVELOPMENT FEE |  | 180523.5 | 0 | 0 | 180523.5 | 180523.5 | 0 | 0
79 | CARRYING COSTS |  | 92885.53 | 0 | 0 | 92885.53 | 92885.53 | 0 | 0
80 | FINANCING COSTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
82 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
83 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
84 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
85 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
86 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
87 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
88 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
89 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
90 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
91 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
92 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
93 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
94 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
95 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
96 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
97 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
98 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
99 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
| TOTAL |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0

## Draw #6
GENESIS CAPITAL DRAW FORM
| CLIENT: | Angeleno Investments | [5 empty] | TOTAL COMPLETED TO DATE: | 0 | #REF!
| DATE: | 2025-11-17 | [5 empty] | REMAINING $ IN BUDGET: | #REF!
| PROJECT: | 10910 Huston Street | [5 empty] | ORIGINAL SCHEDULE OF VALUES: | #REF!
| DRAW REQUEST: | 0 | [5 empty] | CHANGE ORDERS: | 0
[8 empty] | REVISED SCHEDULE OF VALUES: | #REF!
| DESCRIPTION OF WORK |  | SCHEDULED VALUES | PREVIOUS | + / - CHANGES | REVISED VALUES | REMAINING | DRAW | COMPLETED AND
|  |  |  | CHANGES |  |  | BUDGET | 6 | STORED TO DATE
1 | SOFT COSTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Site Security |  | 10580.63 | 0 | 0 | 10580.63 | 10580.63 | 0 | 0
3 | Soils Inspection |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Offsites (Transformer) |  | 20000 | 0 | 0 | 20000 | 20000 | 0 | 0
5 | Plan Check Fees |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Permits |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Survey |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Soils Engineer |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Soils Permit + T24 |  | 2500 | 0 | 0 | 2500 | 2500 | 0 | 0
10 | Special Inspections - Deputy |  | 15000 | 0 | 0 | 15000 | 15000 | 0 | 0
11 | Architect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Structural Engineer |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Structural Observation |  | 8000 | 0 | 0 | 8000 | 8000 | 0 | 0
14 | Civil Engineering |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | Grading Permit |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Landscape Architect/Designer |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Driveway Apron Permit |  | 2500 | 0 | 0 | 2500 | 2500 | 0 | 0
18 | Punch List - Misc. |  | 21962.77 | 0 | 0 | 21962.77 | 21962.77 | 0 | 0
19 | EBM, Low Voltage, Landscape, Waterproofing CA |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | Project Accounting/Tax Filing |  | 12994.01 | 0 | 0 | 12994.01 | 12994.01 | 0 | 0
21 | Legal & Professional Fees |  | 873.39 | 0 | 0 | 873.39 | 873.39 | 0 | 0
22 | Sewer CCTV and inspection |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | Environmental Phase I |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | Dry Utility Consultant |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | Dry Utility Survey |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
26 | MEP |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | Civil Construction Administration |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
28 | Permit Clearances & Agency Reviews |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | Demo Permit Fees |  | 500 | 0 | 0 | 500 | 500 | 0 | 0
30 | MEP Fees |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | Agency Signoffs |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | Specifications Writer Consultant |  | 2000 | 0 | 0 | 2000 | 2000 | 0 | 0
33 | Construction Consultant |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | Low Voltage Consultant |  | 15524 | 0 | 0 | 15524 | 15524 | 0 | 0
35 | Photovoltaic Consultant |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
36 | Construction Management / Observation (OO) |  | 49427.9 | 0 | 0 | 49427.9 | 49427.9 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
37 | CMFA Startup Fee |  | 22800 | 0 | 0 | 22800 | 22800 | 0 | 0
38 | Non-Profit Start Up Fee |  | 25000 | 0 | 0 | 25000 | 25000 | 0 | 0
39 | CMFA Construction Fee |  | 12000 | 0 | 0 | 12000 | 12000 | 0 | 0
40 | Non-Profit Construction Fee |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
41 | WTE Legal Costs for CMFA & Non-Profit Partner |  | 20000 | 0 | 0 | 20000 | 20000 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
43 | GENERAL CONDITIONS |  | 362115.24 | 0 | 0 | 362115.24 | 362115.24 | 0 | 0
44 | GENERAL REQUIREMENT |  | 124657.88 | 0 | 0 | 124657.88 | 124657.88 | 0 | 0
45 | SITE WORK |  | 139049.51 | 0 | 0 | 139049.51 | 139049.51 | 0 | 0
46 | CONCRETE |  | 253182 | 0 | 0 | 253182 | 253182 | 0 | 0
47 | MASONRY |  | 3562.64 | 0 | 0 | 3562.64 | 3562.64 | 0 | 0
48 | METALS |  | 324100 | 0 | 0 | 324100 | 324100 | 0 | 0
49 | FRAMING |  | 818554 | 0 | 0 | 818554 | 818554 | 0 | 0
50 | COUNTERTOPS |  | 56930 | 0 | 0 | 56930 | 56930 | 0 | 0
51 | CABINETS |  | 56930 | 0 | 0 | 56930 | 56930 | 0 | 0
52 | THERMAL MOISTURE PROTECTION |  | 173148 | 0 | 0 | 173148 | 173148 | 0 | 0
53 | DOORS |  | 204087.33 | 0 | 0 | 204087.33 | 204087.33 | 0 | 0
54 | WINDOWS |  | 106274.25 | 0 | 0 | 106274.25 | 106274.25 | 0 | 0
55 | STUCCO |  | 208002 | 0 | 0 | 208002 | 208002 | 0 | 0
56 | DRYWALL |  | 416355 | 0 | 0 | 416355 | 416355 | 0 | 0
57 | PAINTING |  | 120700 | 0 | 0 | 120700 | 120700 | 0 | 0
58 | FLOORING - common areas |  | 45150 | 0 | 0 | 45150 | 45150 | 0 | 0
59 | FLOORING - Units with baseboards |  | 93335 | 0 | 0 | 93335 | 93335 | 0 | 0
60 | SPECIALTIES |  | 25109.21 | 0 | 0 | 25109.21 | 25109.21 | 0 | 0
61 | EQUIPMENT |  | 153636 | 0 | 0 | 153636 | 153636 | 0 | 0
62 | FURNISHING |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
63 | FIRE SPRINKLERS |  | 108500 | 0 | 0 | 108500 | 108500 | 0 | 0
64 | FIRE ALARM |  | 68401 | 0 | 0 | 68401 | 68401 | 0 | 0
65 | SOLAR PANELS |  | 97000 | 0 | 0 | 97000 | 97000 | 0 | 0
66 | SECURITY ACCESS & SURVEILLANCE |  | 136430 | 0 | 0 | 136430 | 136430 | 0 | 0
67 | ELEVATORS & LIFT |  | 174882 | 0 | 0 | 174882 | 174882 | 0 | 0
68 | WATER SUBMETER (material) |  | 12273 | 0 | 0 | 12273 | 12273 | 0 | 0
69 | WATER SUBMETER (labor) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
70 | ROUGH PLUMBING |  | 751927 | 0 | 0 | 751927 | 751927 | 0 | 0
71 | FINISH PLUMBING |  | 90000 | 0 | 0 | 90000 | 90000 | 0 | 0
72 | HVAC |  | 259000 | 0 | 0 | 259000 | 259000 | 0 | 0
73 | ELECTRICAL |  | 880486.32 | 0 | 0 | 880486.32 | 880486.32 | 0 | 0
74 | CONTINGENCY |  | 529215.2 | 0 | 0 | 529215.2 | 529215.2 | 0 | 0
75 | INSURANCE (GL w/auto, workers compl) |  | 97177.07 | 0 | 0 | 97177.07 | 97177.07 | 0 | 0
76 | GROSS RECEIPT TAX |  | 6543.26 | 0 | 0 | 6543.26 | 6543.26 | 0 | 0
77 | GC FEE |  | 388708.28 | 0 | 0 | 388708.28 | 388708.28 | 0 | 0
78 | DEVELOPMENT FEE |  | 180523.5 | 0 | 0 | 180523.5 | 180523.5 | 0 | 0
79 | CARRYING COSTS |  | 92885.53 | 0 | 0 | 92885.53 | 92885.53 | 0 | 0
80 | FINANCING COSTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
82 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
83 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
84 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
85 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
86 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
87 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
88 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
89 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
90 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
91 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
92 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
93 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
94 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
95 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
96 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
97 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
98 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
99 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
| TOTAL |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0

## Draw #7
GENESIS CAPITAL DRAW FORM
| CLIENT: | Angeleno Investments | [5 empty] | TOTAL COMPLETED TO DATE: | 0 | #REF!
| DATE: | 2025-11-17 | [5 empty] | REMAINING $ IN BUDGET: | #REF!
| PROJECT: | 10910 Huston Street | [5 empty] | ORIGINAL SCHEDULE OF VALUES: | #REF!
| DRAW REQUEST: | 0 | [5 empty] | CHANGE ORDERS: | 0
[8 empty] | REVISED SCHEDULE OF VALUES: | #REF!
| DESCRIPTION OF WORK |  | SCHEDULED VALUES | PREVIOUS | + / - CHANGES | REVISED VALUES | REMAINING | DRAW | COMPLETED AND
|  |  |  | CHANGES |  |  | BUDGET | 7 | STORED TO DATE
1 | SOFT COSTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Site Security |  | 10580.63 | 0 | 0 | 10580.63 | 10580.63 | 0 | 0
3 | Soils Inspection |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Offsites (Transformer) |  | 20000 | 0 | 0 | 20000 | 20000 | 0 | 0
5 | Plan Check Fees |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Permits |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Survey |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Soils Engineer |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Soils Permit + T24 |  | 2500 | 0 | 0 | 2500 | 2500 | 0 | 0
10 | Special Inspections - Deputy |  | 15000 | 0 | 0 | 15000 | 15000 | 0 | 0
11 | Architect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Structural Engineer |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Structural Observation |  | 8000 | 0 | 0 | 8000 | 8000 | 0 | 0
14 | Civil Engineering |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | Grading Permit |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Landscape Architect/Designer |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Driveway Apron Permit |  | 2500 | 0 | 0 | 2500 | 2500 | 0 | 0
18 | Punch List - Misc. |  | 21962.77 | 0 | 0 | 21962.77 | 21962.77 | 0 | 0
19 | EBM, Low Voltage, Landscape, Waterproofing CA |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | Project Accounting/Tax Filing |  | 12994.01 | 0 | 0 | 12994.01 | 12994.01 | 0 | 0
21 | Legal & Professional Fees |  | 873.39 | 0 | 0 | 873.39 | 873.39 | 0 | 0
22 | Sewer CCTV and inspection |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | Environmental Phase I |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | Dry Utility Consultant |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | Dry Utility Survey |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
26 | MEP |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | Civil Construction Administration |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
28 | Permit Clearances & Agency Reviews |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | Demo Permit Fees |  | 500 | 0 | 0 | 500 | 500 | 0 | 0
30 | MEP Fees |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | Agency Signoffs |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | Specifications Writer Consultant |  | 2000 | 0 | 0 | 2000 | 2000 | 0 | 0
33 | Construction Consultant |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | Low Voltage Consultant |  | 15524 | 0 | 0 | 15524 | 15524 | 0 | 0
35 | Photovoltaic Consultant |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
36 | Construction Management / Observation (OO) |  | 49427.9 | 0 | 0 | 49427.9 | 49427.9 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
37 | CMFA Startup Fee |  | 22800 | 0 | 0 | 22800 | 22800 | 0 | 0
38 | Non-Profit Start Up Fee |  | 25000 | 0 | 0 | 25000 | 25000 | 0 | 0
39 | CMFA Construction Fee |  | 12000 | 0 | 0 | 12000 | 12000 | 0 | 0
40 | Non-Profit Construction Fee |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
41 | WTE Legal Costs for CMFA & Non-Profit Partner |  | 20000 | 0 | 0 | 20000 | 20000 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
43 | GENERAL CONDITIONS |  | 362115.24 | 0 | 0 | 362115.24 | 362115.24 | 0 | 0
44 | GENERAL REQUIREMENT |  | 124657.88 | 0 | 0 | 124657.88 | 124657.88 | 0 | 0
45 | SITE WORK |  | 139049.51 | 0 | 0 | 139049.51 | 139049.51 | 0 | 0
46 | CONCRETE |  | 253182 | 0 | 0 | 253182 | 253182 | 0 | 0
47 | MASONRY |  | 3562.64 | 0 | 0 | 3562.64 | 3562.64 | 0 | 0
48 | METALS |  | 324100 | 0 | 0 | 324100 | 324100 | 0 | 0
49 | FRAMING |  | 818554 | 0 | 0 | 818554 | 818554 | 0 | 0
50 | COUNTERTOPS |  | 56930 | 0 | 0 | 56930 | 56930 | 0 | 0
51 | CABINETS |  | 56930 | 0 | 0 | 56930 | 56930 | 0 | 0
52 | THERMAL MOISTURE PROTECTION |  | 173148 | 0 | 0 | 173148 | 173148 | 0 | 0
53 | DOORS |  | 204087.33 | 0 | 0 | 204087.33 | 204087.33 | 0 | 0
54 | WINDOWS |  | 106274.25 | 0 | 0 | 106274.25 | 106274.25 | 0 | 0
55 | STUCCO |  | 208002 | 0 | 0 | 208002 | 208002 | 0 | 0
56 | DRYWALL |  | 416355 | 0 | 0 | 416355 | 416355 | 0 | 0
57 | PAINTING |  | 120700 | 0 | 0 | 120700 | 120700 | 0 | 0
58 | FLOORING - common areas |  | 45150 | 0 | 0 | 45150 | 45150 | 0 | 0
59 | FLOORING - Units with baseboards |  | 93335 | 0 | 0 | 93335 | 93335 | 0 | 0
60 | SPECIALTIES |  | 25109.21 | 0 | 0 | 25109.21 | 25109.21 | 0 | 0
61 | EQUIPMENT |  | 153636 | 0 | 0 | 153636 | 153636 | 0 | 0
62 | FURNISHING |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
63 | FIRE SPRINKLERS |  | 108500 | 0 | 0 | 108500 | 108500 | 0 | 0
64 | FIRE ALARM |  | 68401 | 0 | 0 | 68401 | 68401 | 0 | 0
65 | SOLAR PANELS |  | 97000 | 0 | 0 | 97000 | 97000 | 0 | 0
66 | SECURITY ACCESS & SURVEILLANCE |  | 136430 | 0 | 0 | 136430 | 136430 | 0 | 0
67 | ELEVATORS & LIFT |  | 174882 | 0 | 0 | 174882 | 174882 | 0 | 0
68 | WATER SUBMETER (material) |  | 12273 | 0 | 0 | 12273 | 12273 | 0 | 0
69 | WATER SUBMETER (labor) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
70 | ROUGH PLUMBING |  | 751927 | 0 | 0 | 751927 | 751927 | 0 | 0
71 | FINISH PLUMBING |  | 90000 | 0 | 0 | 90000 | 90000 | 0 | 0
72 | HVAC |  | 259000 | 0 | 0 | 259000 | 259000 | 0 | 0
73 | ELECTRICAL |  | 880486.32 | 0 | 0 | 880486.32 | 880486.32 | 0 | 0
74 | CONTINGENCY |  | 529215.2 | 0 | 0 | 529215.2 | 529215.2 | 0 | 0
75 | INSURANCE (GL w/auto, workers compl) |  | 97177.07 | 0 | 0 | 97177.07 | 97177.07 | 0 | 0
76 | GROSS RECEIPT TAX |  | 6543.26 | 0 | 0 | 6543.26 | 6543.26 | 0 | 0
77 | GC FEE |  | 388708.28 | 0 | 0 | 388708.28 | 388708.28 | 0 | 0
78 | DEVELOPMENT FEE |  | 180523.5 | 0 | 0 | 180523.5 | 180523.5 | 0 | 0
79 | CARRYING COSTS |  | 92885.53 | 0 | 0 | 92885.53 | 92885.53 | 0 | 0
80 | FINANCING COSTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
82 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
83 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
84 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
85 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
86 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
87 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
88 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
89 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
90 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
91 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
92 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
93 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
94 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
95 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
96 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
97 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
98 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
99 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
| TOTAL |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0

## Draw #8
GENESIS CAPITAL DRAW FORM
| CLIENT: | Angeleno Investments | [5 empty] | TOTAL COMPLETED TO DATE: | 0 | #REF!
| DATE: | 2025-11-17 | [5 empty] | REMAINING $ IN BUDGET: | #REF!
| PROJECT: | 10910 Huston Street | [5 empty] | ORIGINAL SCHEDULE OF VALUES: | #REF!
| DRAW REQUEST: | 0 | [5 empty] | CHANGE ORDERS: | 0
[8 empty] | REVISED SCHEDULE OF VALUES: | #REF!
| DESCRIPTION OF WORK |  | SCHEDULED VALUES | PREVIOUS | + / - CHANGES | REVISED VALUES | REMAINING | DRAW | COMPLETED AND
|  |  |  | CHANGES |  |  | BUDGET | 8 | STORED TO DATE
1 | SOFT COSTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Site Security |  | 10580.63 | 0 | 0 | 10580.63 | 10580.63 | 0 | 0
3 | Soils Inspection |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Offsites (Transformer) |  | 20000 | 0 | 0 | 20000 | 20000 | 0 | 0
5 | Plan Check Fees |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Permits |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Survey |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Soils Engineer |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Soils Permit + T24 |  | 2500 | 0 | 0 | 2500 | 2500 | 0 | 0
10 | Special Inspections - Deputy |  | 15000 | 0 | 0 | 15000 | 15000 | 0 | 0
11 | Architect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Structural Engineer |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Structural Observation |  | 8000 | 0 | 0 | 8000 | 8000 | 0 | 0
14 | Civil Engineering |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | Grading Permit |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Landscape Architect/Designer |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Driveway Apron Permit |  | 2500 | 0 | 0 | 2500 | 2500 | 0 | 0
18 | Punch List - Misc. |  | 21962.77 | 0 | 0 | 21962.77 | 21962.77 | 0 | 0
19 | EBM, Low Voltage, Landscape, Waterproofing CA |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | Project Accounting/Tax Filing |  | 12994.01 | 0 | 0 | 12994.01 | 12994.01 | 0 | 0
21 | Legal & Professional Fees |  | 873.39 | 0 | 0 | 873.39 | 873.39 | 0 | 0
22 | Sewer CCTV and inspection |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | Environmental Phase I |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | Dry Utility Consultant |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | Dry Utility Survey |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
26 | MEP |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | Civil Construction Administration |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
28 | Permit Clearances & Agency Reviews |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | Demo Permit Fees |  | 500 | 0 | 0 | 500 | 500 | 0 | 0
30 | MEP Fees |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | Agency Signoffs |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | Specifications Writer Consultant |  | 2000 | 0 | 0 | 2000 | 2000 | 0 | 0
33 | Construction Consultant |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | Low Voltage Consultant |  | 15524 | 0 | 0 | 15524 | 15524 | 0 | 0
35 | Photovoltaic Consultant |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
36 | Construction Management / Observation (OO) |  | 49427.9 | 0 | 0 | 49427.9 | 49427.9 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
37 | CMFA Startup Fee |  | 22800 | 0 | 0 | 22800 | 22800 | 0 | 0
38 | Non-Profit Start Up Fee |  | 25000 | 0 | 0 | 25000 | 25000 | 0 | 0
39 | CMFA Construction Fee |  | 12000 | 0 | 0 | 12000 | 12000 | 0 | 0
40 | Non-Profit Construction Fee |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
41 | WTE Legal Costs for CMFA & Non-Profit Partner |  | 20000 | 0 | 0 | 20000 | 20000 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
43 | GENERAL CONDITIONS |  | 362115.24 | 0 | 0 | 362115.24 | 362115.24 | 0 | 0
44 | GENERAL REQUIREMENT |  | 124657.88 | 0 | 0 | 124657.88 | 124657.88 | 0 | 0
45 | SITE WORK |  | 139049.51 | 0 | 0 | 139049.51 | 139049.51 | 0 | 0
46 | CONCRETE |  | 253182 | 0 | 0 | 253182 | 253182 | 0 | 0
47 | MASONRY |  | 3562.64 | 0 | 0 | 3562.64 | 3562.64 | 0 | 0
48 | METALS |  | 324100 | 0 | 0 | 324100 | 324100 | 0 | 0
49 | FRAMING |  | 818554 | 0 | 0 | 818554 | 818554 | 0 | 0
50 | COUNTERTOPS |  | 56930 | 0 | 0 | 56930 | 56930 | 0 | 0
51 | CABINETS |  | 56930 | 0 | 0 | 56930 | 56930 | 0 | 0
52 | THERMAL MOISTURE PROTECTION |  | 173148 | 0 | 0 | 173148 | 173148 | 0 | 0
53 | DOORS |  | 204087.33 | 0 | 0 | 204087.33 | 204087.33 | 0 | 0
54 | WINDOWS |  | 106274.25 | 0 | 0 | 106274.25 | 106274.25 | 0 | 0
55 | STUCCO |  | 208002 | 0 | 0 | 208002 | 208002 | 0 | 0
56 | DRYWALL |  | 416355 | 0 | 0 | 416355 | 416355 | 0 | 0
57 | PAINTING |  | 120700 | 0 | 0 | 120700 | 120700 | 0 | 0
58 | FLOORING - common areas |  | 45150 | 0 | 0 | 45150 | 45150 | 0 | 0
59 | FLOORING - Units with baseboards |  | 93335 | 0 | 0 | 93335 | 93335 | 0 | 0
60 | SPECIALTIES |  | 25109.21 | 0 | 0 | 25109.21 | 25109.21 | 0 | 0
61 | EQUIPMENT |  | 153636 | 0 | 0 | 153636 | 153636 | 0 | 0
62 | FURNISHING |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
63 | FIRE SPRINKLERS |  | 108500 | 0 | 0 | 108500 | 108500 | 0 | 0
64 | FIRE ALARM |  | 68401 | 0 | 0 | 68401 | 68401 | 0 | 0
65 | SOLAR PANELS |  | 97000 | 0 | 0 | 97000 | 97000 | 0 | 0
66 | SECURITY ACCESS & SURVEILLANCE |  | 136430 | 0 | 0 | 136430 | 136430 | 0 | 0
67 | ELEVATORS & LIFT |  | 174882 | 0 | 0 | 174882 | 174882 | 0 | 0
68 | WATER SUBMETER (material) |  | 12273 | 0 | 0 | 12273 | 12273 | 0 | 0
69 | WATER SUBMETER (labor) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
70 | ROUGH PLUMBING |  | 751927 | 0 | 0 | 751927 | 751927 | 0 | 0
71 | FINISH PLUMBING |  | 90000 | 0 | 0 | 90000 | 90000 | 0 | 0
72 | HVAC |  | 259000 | 0 | 0 | 259000 | 259000 | 0 | 0
73 | ELECTRICAL |  | 880486.32 | 0 | 0 | 880486.32 | 880486.32 | 0 | 0
74 | CONTINGENCY |  | 529215.2 | 0 | 0 | 529215.2 | 529215.2 | 0 | 0
75 | INSURANCE (GL w/auto, workers compl) |  | 97177.07 | 0 | 0 | 97177.07 | 97177.07 | 0 | 0
76 | GROSS RECEIPT TAX |  | 6543.26 | 0 | 0 | 6543.26 | 6543.26 | 0 | 0
77 | GC FEE |  | 388708.28 | 0 | 0 | 388708.28 | 388708.28 | 0 | 0
78 | DEVELOPMENT FEE |  | 180523.5 | 0 | 0 | 180523.5 | 180523.5 | 0 | 0
79 | CARRYING COSTS |  | 92885.53 | 0 | 0 | 92885.53 | 92885.53 | 0 | 0
80 | FINANCING COSTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
82 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
83 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
84 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
85 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
86 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
87 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
88 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
89 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
90 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
91 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
92 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
93 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
94 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
95 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
96 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
97 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
98 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
99 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
| TOTAL |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0

## Draw #9
GENESIS CAPITAL DRAW FORM
| CLIENT: | Angeleno Investments | [5 empty] | TOTAL COMPLETED TO DATE: | 0 | #REF!
| DATE: | 2025-11-17 | [5 empty] | REMAINING $ IN BUDGET: | #REF!
| PROJECT: | 10910 Huston Street | [5 empty] | ORIGINAL SCHEDULE OF VALUES: | #REF!
| DRAW REQUEST: | 0 | [5 empty] | CHANGE ORDERS: | 0
[8 empty] | REVISED SCHEDULE OF VALUES: | #REF!
| DESCRIPTION OF WORK |  | SCHEDULED VALUES | PREVIOUS | + / - CHANGES | REVISED VALUES | REMAINING | DRAW | COMPLETED AND
|  |  |  | CHANGES |  |  | BUDGET | 9 | STORED TO DATE
1 | SOFT COSTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Site Security |  | 10580.63 | 0 | 0 | 10580.63 | 10580.63 | 0 | 0
3 | Soils Inspection |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Offsites (Transformer) |  | 20000 | 0 | 0 | 20000 | 20000 | 0 | 0
5 | Plan Check Fees |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Permits |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Survey |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Soils Engineer |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Soils Permit + T24 |  | 2500 | 0 | 0 | 2500 | 2500 | 0 | 0
10 | Special Inspections - Deputy |  | 15000 | 0 | 0 | 15000 | 15000 | 0 | 0
11 | Architect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Structural Engineer |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Structural Observation |  | 8000 | 0 | 0 | 8000 | 8000 | 0 | 0
14 | Civil Engineering |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | Grading Permit |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Landscape Architect/Designer |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Driveway Apron Permit |  | 2500 | 0 | 0 | 2500 | 2500 | 0 | 0
18 | Punch List - Misc. |  | 21962.77 | 0 | 0 | 21962.77 | 21962.77 | 0 | 0
19 | EBM, Low Voltage, Landscape, Waterproofing CA |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | Project Accounting/Tax Filing |  | 12994.01 | 0 | 0 | 12994.01 | 12994.01 | 0 | 0
21 | Legal & Professional Fees |  | 873.39 | 0 | 0 | 873.39 | 873.39 | 0 | 0
22 | Sewer CCTV and inspection |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | Environmental Phase I |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | Dry Utility Consultant |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | Dry Utility Survey |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
26 | MEP |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | Civil Construction Administration |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
28 | Permit Clearances & Agency Reviews |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | Demo Permit Fees |  | 500 | 0 | 0 | 500 | 500 | 0 | 0
30 | MEP Fees |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | Agency Signoffs |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | Specifications Writer Consultant |  | 2000 | 0 | 0 | 2000 | 2000 | 0 | 0
33 | Construction Consultant |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | Low Voltage Consultant |  | 15524 | 0 | 0 | 15524 | 15524 | 0 | 0
35 | Photovoltaic Consultant |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
36 | Construction Management / Observation (OO) |  | 49427.9 | 0 | 0 | 49427.9 | 49427.9 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
37 | CMFA Startup Fee |  | 22800 | 0 | 0 | 22800 | 22800 | 0 | 0
38 | Non-Profit Start Up Fee |  | 25000 | 0 | 0 | 25000 | 25000 | 0 | 0
39 | CMFA Construction Fee |  | 12000 | 0 | 0 | 12000 | 12000 | 0 | 0
40 | Non-Profit Construction Fee |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
41 | WTE Legal Costs for CMFA & Non-Profit Partner |  | 20000 | 0 | 0 | 20000 | 20000 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
43 | GENERAL CONDITIONS |  | 362115.24 | 0 | 0 | 362115.24 | 362115.24 | 0 | 0
44 | GENERAL REQUIREMENT |  | 124657.88 | 0 | 0 | 124657.88 | 124657.88 | 0 | 0
45 | SITE WORK |  | 139049.51 | 0 | 0 | 139049.51 | 139049.51 | 0 | 0
46 | CONCRETE |  | 253182 | 0 | 0 | 253182 | 253182 | 0 | 0
47 | MASONRY |  | 3562.64 | 0 | 0 | 3562.64 | 3562.64 | 0 | 0
48 | METALS |  | 324100 | 0 | 0 | 324100 | 324100 | 0 | 0
49 | FRAMING |  | 818554 | 0 | 0 | 818554 | 818554 | 0 | 0
50 | COUNTERTOPS |  | 56930 | 0 | 0 | 56930 | 56930 | 0 | 0
51 | CABINETS |  | 56930 | 0 | 0 | 56930 | 56930 | 0 | 0
52 | THERMAL MOISTURE PROTECTION |  | 173148 | 0 | 0 | 173148 | 173148 | 0 | 0
53 | DOORS |  | 204087.33 | 0 | 0 | 204087.33 | 204087.33 | 0 | 0
54 | WINDOWS |  | 106274.25 | 0 | 0 | 106274.25 | 106274.25 | 0 | 0
55 | STUCCO |  | 208002 | 0 | 0 | 208002 | 208002 | 0 | 0
56 | DRYWALL |  | 416355 | 0 | 0 | 416355 | 416355 | 0 | 0
57 | PAINTING |  | 120700 | 0 | 0 | 120700 | 120700 | 0 | 0
58 | FLOORING - common areas |  | 45150 | 0 | 0 | 45150 | 45150 | 0 | 0
59 | FLOORING - Units with baseboards |  | 93335 | 0 | 0 | 93335 | 93335 | 0 | 0
60 | SPECIALTIES |  | 25109.21 | 0 | 0 | 25109.21 | 25109.21 | 0 | 0
61 | EQUIPMENT |  | 153636 | 0 | 0 | 153636 | 153636 | 0 | 0
62 | FURNISHING |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
63 | FIRE SPRINKLERS |  | 108500 | 0 | 0 | 108500 | 108500 | 0 | 0
64 | FIRE ALARM |  | 68401 | 0 | 0 | 68401 | 68401 | 0 | 0
65 | SOLAR PANELS |  | 97000 | 0 | 0 | 97000 | 97000 | 0 | 0
66 | SECURITY ACCESS & SURVEILLANCE |  | 136430 | 0 | 0 | 136430 | 136430 | 0 | 0
67 | ELEVATORS & LIFT |  | 174882 | 0 | 0 | 174882 | 174882 | 0 | 0
68 | WATER SUBMETER (material) |  | 12273 | 0 | 0 | 12273 | 12273 | 0 | 0
69 | WATER SUBMETER (labor) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
70 | ROUGH PLUMBING |  | 751927 | 0 | 0 | 751927 | 751927 | 0 | 0
71 | FINISH PLUMBING |  | 90000 | 0 | 0 | 90000 | 90000 | 0 | 0
72 | HVAC |  | 259000 | 0 | 0 | 259000 | 259000 | 0 | 0
73 | ELECTRICAL |  | 880486.32 | 0 | 0 | 880486.32 | 880486.32 | 0 | 0
74 | CONTINGENCY |  | 529215.2 | 0 | 0 | 529215.2 | 529215.2 | 0 | 0
75 | INSURANCE (GL w/auto, workers compl) |  | 97177.07 | 0 | 0 | 97177.07 | 97177.07 | 0 | 0
76 | GROSS RECEIPT TAX |  | 6543.26 | 0 | 0 | 6543.26 | 6543.26 | 0 | 0
77 | GC FEE |  | 388708.28 | 0 | 0 | 388708.28 | 388708.28 | 0 | 0
78 | DEVELOPMENT FEE |  | 180523.5 | 0 | 0 | 180523.5 | 180523.5 | 0 | 0
79 | CARRYING COSTS |  | 92885.53 | 0 | 0 | 92885.53 | 92885.53 | 0 | 0
80 | FINANCING COSTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
82 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
83 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
84 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
85 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
86 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
87 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
88 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
89 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
90 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
91 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
92 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
93 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
94 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
95 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
96 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
97 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
98 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
99 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
| TOTAL |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0

## Draw #10
GENESIS CAPITAL DRAW FORM
| CLIENT: | Angeleno Investments | [5 empty] | TOTAL COMPLETED TO DATE: | 0 | #REF!
| DATE: | 2025-11-17 | [5 empty] | REMAINING $ IN BUDGET: | #REF!
| PROJECT: | 10910 Huston Street | [5 empty] | ORIGINAL SCHEDULE OF VALUES: | #REF!
| DRAW REQUEST: | 0 | [5 empty] | CHANGE ORDERS: | 0
[8 empty] | REVISED SCHEDULE OF VALUES: | #REF!
| DESCRIPTION OF WORK |  | SCHEDULED VALUES | PREVIOUS | + / - CHANGES | REVISED VALUES | REMAINING | DRAW | COMPLETED AND
|  |  |  | CHANGES |  |  | BUDGET | 10 | STORED TO DATE
1 | SOFT COSTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Site Security |  | 10580.63 | 0 | 0 | 10580.63 | 10580.63 | 0 | 0
3 | Soils Inspection |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Offsites (Transformer) |  | 20000 | 0 | 0 | 20000 | 20000 | 0 | 0
5 | Plan Check Fees |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Permits |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Survey |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Soils Engineer |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Soils Permit + T24 |  | 2500 | 0 | 0 | 2500 | 2500 | 0 | 0
10 | Special Inspections - Deputy |  | 15000 | 0 | 0 | 15000 | 15000 | 0 | 0
11 | Architect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Structural Engineer |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Structural Observation |  | 8000 | 0 | 0 | 8000 | 8000 | 0 | 0
14 | Civil Engineering |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | Grading Permit |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Landscape Architect/Designer |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Driveway Apron Permit |  | 2500 | 0 | 0 | 2500 | 2500 | 0 | 0
18 | Punch List - Misc. |  | 21962.77 | 0 | 0 | 21962.77 | 21962.77 | 0 | 0
19 | EBM, Low Voltage, Landscape, Waterproofing CA |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | Project Accounting/Tax Filing |  | 12994.01 | 0 | 0 | 12994.01 | 12994.01 | 0 | 0
21 | Legal & Professional Fees |  | 873.39 | 0 | 0 | 873.39 | 873.39 | 0 | 0
22 | Sewer CCTV and inspection |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | Environmental Phase I |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | Dry Utility Consultant |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | Dry Utility Survey |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
26 | MEP |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | Civil Construction Administration |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
28 | Permit Clearances & Agency Reviews |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | Demo Permit Fees |  | 500 | 0 | 0 | 500 | 500 | 0 | 0
30 | MEP Fees |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | Agency Signoffs |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | Specifications Writer Consultant |  | 2000 | 0 | 0 | 2000 | 2000 | 0 | 0
33 | Construction Consultant |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | Low Voltage Consultant |  | 15524 | 0 | 0 | 15524 | 15524 | 0 | 0
35 | Photovoltaic Consultant |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
36 | Construction Management / Observation (OO) |  | 49427.9 | 0 | 0 | 49427.9 | 49427.9 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
37 | CMFA Startup Fee |  | 22800 | 0 | 0 | 22800 | 22800 | 0 | 0
38 | Non-Profit Start Up Fee |  | 25000 | 0 | 0 | 25000 | 25000 | 0 | 0
39 | CMFA Construction Fee |  | 12000 | 0 | 0 | 12000 | 12000 | 0 | 0
40 | Non-Profit Construction Fee |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
41 | WTE Legal Costs for CMFA & Non-Profit Partner |  | 20000 | 0 | 0 | 20000 | 20000 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
43 | GENERAL CONDITIONS |  | 362115.24 | 0 | 0 | 362115.24 | 362115.24 | 0 | 0
44 | GENERAL REQUIREMENT |  | 124657.88 | 0 | 0 | 124657.88 | 124657.88 | 0 | 0
45 | SITE WORK |  | 139049.51 | 0 | 0 | 139049.51 | 139049.51 | 0 | 0
46 | CONCRETE |  | 253182 | 0 | 0 | 253182 | 253182 | 0 | 0
47 | MASONRY |  | 3562.64 | 0 | 0 | 3562.64 | 3562.64 | 0 | 0
48 | METALS |  | 324100 | 0 | 0 | 324100 | 324100 | 0 | 0
49 | FRAMING |  | 818554 | 0 | 0 | 818554 | 818554 | 0 | 0
50 | COUNTERTOPS |  | 56930 | 0 | 0 | 56930 | 56930 | 0 | 0
51 | CABINETS |  | 56930 | 0 | 0 | 56930 | 56930 | 0 | 0
52 | THERMAL MOISTURE PROTECTION |  | 173148 | 0 | 0 | 173148 | 173148 | 0 | 0
53 | DOORS |  | 204087.33 | 0 | 0 | 204087.33 | 204087.33 | 0 | 0
54 | WINDOWS |  | 106274.25 | 0 | 0 | 106274.25 | 106274.25 | 0 | 0
55 | STUCCO |  | 208002 | 0 | 0 | 208002 | 208002 | 0 | 0
56 | DRYWALL |  | 416355 | 0 | 0 | 416355 | 416355 | 0 | 0
57 | PAINTING |  | 120700 | 0 | 0 | 120700 | 120700 | 0 | 0
58 | FLOORING - common areas |  | 45150 | 0 | 0 | 45150 | 45150 | 0 | 0
59 | FLOORING - Units with baseboards |  | 93335 | 0 | 0 | 93335 | 93335 | 0 | 0
60 | SPECIALTIES |  | 25109.21 | 0 | 0 | 25109.21 | 25109.21 | 0 | 0
61 | EQUIPMENT |  | 153636 | 0 | 0 | 153636 | 153636 | 0 | 0
62 | FURNISHING |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
63 | FIRE SPRINKLERS |  | 108500 | 0 | 0 | 108500 | 108500 | 0 | 0
64 | FIRE ALARM |  | 68401 | 0 | 0 | 68401 | 68401 | 0 | 0
65 | SOLAR PANELS |  | 97000 | 0 | 0 | 97000 | 97000 | 0 | 0
66 | SECURITY ACCESS & SURVEILLANCE |  | 136430 | 0 | 0 | 136430 | 136430 | 0 | 0
67 | ELEVATORS & LIFT |  | 174882 | 0 | 0 | 174882 | 174882 | 0 | 0
68 | WATER SUBMETER (material) |  | 12273 | 0 | 0 | 12273 | 12273 | 0 | 0
69 | WATER SUBMETER (labor) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
70 | ROUGH PLUMBING |  | 751927 | 0 | 0 | 751927 | 751927 | 0 | 0
71 | FINISH PLUMBING |  | 90000 | 0 | 0 | 90000 | 90000 | 0 | 0
72 | HVAC |  | 259000 | 0 | 0 | 259000 | 259000 | 0 | 0
73 | ELECTRICAL |  | 880486.32 | 0 | 0 | 880486.32 | 880486.32 | 0 | 0
74 | CONTINGENCY |  | 529215.2 | 0 | 0 | 529215.2 | 529215.2 | 0 | 0
75 | INSURANCE (GL w/auto, workers compl) |  | 97177.07 | 0 | 0 | 97177.07 | 97177.07 | 0 | 0
76 | GROSS RECEIPT TAX |  | 6543.26 | 0 | 0 | 6543.26 | 6543.26 | 0 | 0
77 | GC FEE |  | 388708.28 | 0 | 0 | 388708.28 | 388708.28 | 0 | 0
78 | DEVELOPMENT FEE |  | 180523.5 | 0 | 0 | 180523.5 | 180523.5 | 0 | 0
79 | CARRYING COSTS |  | 92885.53 | 0 | 0 | 92885.53 | 92885.53 | 0 | 0
80 | FINANCING COSTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
82 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
83 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
84 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
85 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
86 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
87 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
88 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
89 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
90 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
91 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
92 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
93 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
94 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
95 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
96 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
97 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
98 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
99 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
| TOTAL |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0

## Draw #11
GENESIS CAPITAL DRAW FORM
| CLIENT: | Angeleno Investments | [5 empty] | TOTAL COMPLETED TO DATE: | 0 | #REF!
| DATE: | 2025-11-17 | [5 empty] | REMAINING $ IN BUDGET: | #REF!
| PROJECT: | 10910 Huston Street | [5 empty] | ORIGINAL SCHEDULE OF VALUES: | #REF!
| DRAW REQUEST: | 0 | [5 empty] | CHANGE ORDERS: | 0
[8 empty] | REVISED SCHEDULE OF VALUES: | #REF!
| DESCRIPTION OF WORK |  | SCHEDULED VALUES | PREVIOUS | + / - CHANGES | REVISED VALUES | REMAINING | DRAW | COMPLETED AND
|  |  |  | CHANGES |  |  | BUDGET | 11 | STORED TO DATE
1 | SOFT COSTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Site Security |  | 10580.63 | 0 | 0 | 10580.63 | 10580.63 | 0 | 0
3 | Soils Inspection |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Offsites (Transformer) |  | 20000 | 0 | 0 | 20000 | 20000 | 0 | 0
5 | Plan Check Fees |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Permits |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Survey |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Soils Engineer |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Soils Permit + T24 |  | 2500 | 0 | 0 | 2500 | 2500 | 0 | 0
10 | Special Inspections - Deputy |  | 15000 | 0 | 0 | 15000 | 15000 | 0 | 0
11 | Architect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Structural Engineer |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Structural Observation |  | 8000 | 0 | 0 | 8000 | 8000 | 0 | 0
14 | Civil Engineering |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | Grading Permit |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Landscape Architect/Designer |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Driveway Apron Permit |  | 2500 | 0 | 0 | 2500 | 2500 | 0 | 0
18 | Punch List - Misc. |  | 21962.77 | 0 | 0 | 21962.77 | 21962.77 | 0 | 0
19 | EBM, Low Voltage, Landscape, Waterproofing CA |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | Project Accounting/Tax Filing |  | 12994.01 | 0 | 0 | 12994.01 | 12994.01 | 0 | 0
21 | Legal & Professional Fees |  | 873.39 | 0 | 0 | 873.39 | 873.39 | 0 | 0
22 | Sewer CCTV and inspection |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | Environmental Phase I |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | Dry Utility Consultant |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | Dry Utility Survey |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
26 | MEP |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | Civil Construction Administration |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
28 | Permit Clearances & Agency Reviews |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | Demo Permit Fees |  | 500 | 0 | 0 | 500 | 500 | 0 | 0
30 | MEP Fees |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | Agency Signoffs |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | Specifications Writer Consultant |  | 2000 | 0 | 0 | 2000 | 2000 | 0 | 0
33 | Construction Consultant |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | Low Voltage Consultant |  | 15524 | 0 | 0 | 15524 | 15524 | 0 | 0
35 | Photovoltaic Consultant |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
36 | Construction Management / Observation (OO) |  | 49427.9 | 0 | 0 | 49427.9 | 49427.9 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
37 | CMFA Startup Fee |  | 22800 | 0 | 0 | 22800 | 22800 | 0 | 0
38 | Non-Profit Start Up Fee |  | 25000 | 0 | 0 | 25000 | 25000 | 0 | 0
39 | CMFA Construction Fee |  | 12000 | 0 | 0 | 12000 | 12000 | 0 | 0
40 | Non-Profit Construction Fee |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
41 | WTE Legal Costs for CMFA & Non-Profit Partner |  | 20000 | 0 | 0 | 20000 | 20000 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
43 | GENERAL CONDITIONS |  | 362115.24 | 0 | 0 | 362115.24 | 362115.24 | 0 | 0
44 | GENERAL REQUIREMENT |  | 124657.88 | 0 | 0 | 124657.88 | 124657.88 | 0 | 0
45 | SITE WORK |  | 139049.51 | 0 | 0 | 139049.51 | 139049.51 | 0 | 0
46 | CONCRETE |  | 253182 | 0 | 0 | 253182 | 253182 | 0 | 0
47 | MASONRY |  | 3562.64 | 0 | 0 | 3562.64 | 3562.64 | 0 | 0
48 | METALS |  | 324100 | 0 | 0 | 324100 | 324100 | 0 | 0
49 | FRAMING |  | 818554 | 0 | 0 | 818554 | 818554 | 0 | 0
50 | COUNTERTOPS |  | 56930 | 0 | 0 | 56930 | 56930 | 0 | 0
51 | CABINETS |  | 56930 | 0 | 0 | 56930 | 56930 | 0 | 0
52 | THERMAL MOISTURE PROTECTION |  | 173148 | 0 | 0 | 173148 | 173148 | 0 | 0
53 | DOORS |  | 204087.33 | 0 | 0 | 204087.33 | 204087.33 | 0 | 0
54 | WINDOWS |  | 106274.25 | 0 | 0 | 106274.25 | 106274.25 | 0 | 0
55 | STUCCO |  | 208002 | 0 | 0 | 208002 | 208002 | 0 | 0
56 | DRYWALL |  | 416355 | 0 | 0 | 416355 | 416355 | 0 | 0
57 | PAINTING |  | 120700 | 0 | 0 | 120700 | 120700 | 0 | 0
58 | FLOORING - common areas |  | 45150 | 0 | 0 | 45150 | 45150 | 0 | 0
59 | FLOORING - Units with baseboards |  | 93335 | 0 | 0 | 93335 | 93335 | 0 | 0
60 | SPECIALTIES |  | 25109.21 | 0 | 0 | 25109.21 | 25109.21 | 0 | 0
61 | EQUIPMENT |  | 153636 | 0 | 0 | 153636 | 153636 | 0 | 0
62 | FURNISHING |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
63 | FIRE SPRINKLERS |  | 108500 | 0 | 0 | 108500 | 108500 | 0 | 0
64 | FIRE ALARM |  | 68401 | 0 | 0 | 68401 | 68401 | 0 | 0
65 | SOLAR PANELS |  | 97000 | 0 | 0 | 97000 | 97000 | 0 | 0
66 | SECURITY ACCESS & SURVEILLANCE |  | 136430 | 0 | 0 | 136430 | 136430 | 0 | 0
67 | ELEVATORS & LIFT |  | 174882 | 0 | 0 | 174882 | 174882 | 0 | 0
68 | WATER SUBMETER (material) |  | 12273 | 0 | 0 | 12273 | 12273 | 0 | 0
69 | WATER SUBMETER (labor) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
70 | ROUGH PLUMBING |  | 751927 | 0 | 0 | 751927 | 751927 | 0 | 0
71 | FINISH PLUMBING |  | 90000 | 0 | 0 | 90000 | 90000 | 0 | 0
72 | HVAC |  | 259000 | 0 | 0 | 259000 | 259000 | 0 | 0
73 | ELECTRICAL |  | 880486.32 | 0 | 0 | 880486.32 | 880486.32 | 0 | 0
74 | CONTINGENCY |  | 529215.2 | 0 | 0 | 529215.2 | 529215.2 | 0 | 0
75 | INSURANCE (GL w/auto, workers compl) |  | 97177.07 | 0 | 0 | 97177.07 | 97177.07 | 0 | 0
76 | GROSS RECEIPT TAX |  | 6543.26 | 0 | 0 | 6543.26 | 6543.26 | 0 | 0
77 | GC FEE |  | 388708.28 | 0 | 0 | 388708.28 | 388708.28 | 0 | 0
78 | DEVELOPMENT FEE |  | 180523.5 | 0 | 0 | 180523.5 | 180523.5 | 0 | 0
79 | CARRYING COSTS |  | 92885.53 | 0 | 0 | 92885.53 | 92885.53 | 0 | 0
80 | FINANCING COSTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
82 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
83 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
84 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
85 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
86 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
87 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
88 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
89 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
90 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
91 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
92 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
93 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
94 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
95 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
96 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
97 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
98 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
99 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
| TOTAL |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0

## Draw #12
GENESIS CAPITAL DRAW FORM
| CLIENT: | Angeleno Investments | [5 empty] | TOTAL COMPLETED TO DATE: | 0 | #REF!
| DATE: | 2025-11-17 | [5 empty] | REMAINING $ IN BUDGET: | #REF!
| PROJECT: | 10910 Huston Street | [5 empty] | ORIGINAL SCHEDULE OF VALUES: | #REF!
| DRAW REQUEST: | 0 | [5 empty] | CHANGE ORDERS: | 0
[8 empty] | REVISED SCHEDULE OF VALUES: | #REF!
| DESCRIPTION OF WORK |  | SCHEDULED VALUES | PREVIOUS | + / - CHANGES | REVISED VALUES | REMAINING | DRAW | COMPLETED AND
|  |  |  | CHANGES |  |  | BUDGET | 12 | STORED TO DATE
1 | SOFT COSTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Site Security |  | 10580.63 | 0 | 0 | 10580.63 | 10580.63 | 0 | 0
3 | Soils Inspection |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Offsites (Transformer) |  | 20000 | 0 | 0 | 20000 | 20000 | 0 | 0
5 | Plan Check Fees |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Permits |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Survey |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Soils Engineer |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Soils Permit + T24 |  | 2500 | 0 | 0 | 2500 | 2500 | 0 | 0
10 | Special Inspections - Deputy |  | 15000 | 0 | 0 | 15000 | 15000 | 0 | 0
11 | Architect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Structural Engineer |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Structural Observation |  | 8000 | 0 | 0 | 8000 | 8000 | 0 | 0
14 | Civil Engineering |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | Grading Permit |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Landscape Architect/Designer |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Driveway Apron Permit |  | 2500 | 0 | 0 | 2500 | 2500 | 0 | 0
18 | Punch List - Misc. |  | 21962.77 | 0 | 0 | 21962.77 | 21962.77 | 0 | 0
19 | EBM, Low Voltage, Landscape, Waterproofing CA |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | Project Accounting/Tax Filing |  | 12994.01 | 0 | 0 | 12994.01 | 12994.01 | 0 | 0
21 | Legal & Professional Fees |  | 873.39 | 0 | 0 | 873.39 | 873.39 | 0 | 0
22 | Sewer CCTV and inspection |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | Environmental Phase I |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | Dry Utility Consultant |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | Dry Utility Survey |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
26 | MEP |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | Civil Construction Administration |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
28 | Permit Clearances & Agency Reviews |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | Demo Permit Fees |  | 500 | 0 | 0 | 500 | 500 | 0 | 0
30 | MEP Fees |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | Agency Signoffs |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | Specifications Writer Consultant |  | 2000 | 0 | 0 | 2000 | 2000 | 0 | 0
33 | Construction Consultant |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | Low Voltage Consultant |  | 15524 | 0 | 0 | 15524 | 15524 | 0 | 0
35 | Photovoltaic Consultant |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
36 | Construction Management / Observation (OO) |  | 49427.9 | 0 | 0 | 49427.9 | 49427.9 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
37 | CMFA Startup Fee |  | 22800 | 0 | 0 | 22800 | 22800 | 0 | 0
38 | Non-Profit Start Up Fee |  | 25000 | 0 | 0 | 25000 | 25000 | 0 | 0
39 | CMFA Construction Fee |  | 12000 | 0 | 0 | 12000 | 12000 | 0 | 0
40 | Non-Profit Construction Fee |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
41 | WTE Legal Costs for CMFA & Non-Profit Partner |  | 20000 | 0 | 0 | 20000 | 20000 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
43 | GENERAL CONDITIONS |  | 362115.24 | 0 | 0 | 362115.24 | 362115.24 | 0 | 0
44 | GENERAL REQUIREMENT |  | 124657.88 | 0 | 0 | 124657.88 | 124657.88 | 0 | 0
45 | SITE WORK |  | 139049.51 | 0 | 0 | 139049.51 | 139049.51 | 0 | 0
46 | CONCRETE |  | 253182 | 0 | 0 | 253182 | 253182 | 0 | 0
47 | MASONRY |  | 3562.64 | 0 | 0 | 3562.64 | 3562.64 | 0 | 0
48 | METALS |  | 324100 | 0 | 0 | 324100 | 324100 | 0 | 0
49 | FRAMING |  | 818554 | 0 | 0 | 818554 | 818554 | 0 | 0
50 | COUNTERTOPS |  | 56930 | 0 | 0 | 56930 | 56930 | 0 | 0
51 | CABINETS |  | 56930 | 0 | 0 | 56930 | 56930 | 0 | 0
52 | THERMAL MOISTURE PROTECTION |  | 173148 | 0 | 0 | 173148 | 173148 | 0 | 0
53 | DOORS |  | 204087.33 | 0 | 0 | 204087.33 | 204087.33 | 0 | 0
54 | WINDOWS |  | 106274.25 | 0 | 0 | 106274.25 | 106274.25 | 0 | 0
55 | STUCCO |  | 208002 | 0 | 0 | 208002 | 208002 | 0 | 0
56 | DRYWALL |  | 416355 | 0 | 0 | 416355 | 416355 | 0 | 0
57 | PAINTING |  | 120700 | 0 | 0 | 120700 | 120700 | 0 | 0
58 | FLOORING - common areas |  | 45150 | 0 | 0 | 45150 | 45150 | 0 | 0
59 | FLOORING - Units with baseboards |  | 93335 | 0 | 0 | 93335 | 93335 | 0 | 0
60 | SPECIALTIES |  | 25109.21 | 0 | 0 | 25109.21 | 25109.21 | 0 | 0
61 | EQUIPMENT |  | 153636 | 0 | 0 | 153636 | 153636 | 0 | 0
62 | FURNISHING |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
63 | FIRE SPRINKLERS |  | 108500 | 0 | 0 | 108500 | 108500 | 0 | 0
64 | FIRE ALARM |  | 68401 | 0 | 0 | 68401 | 68401 | 0 | 0
65 | SOLAR PANELS |  | 97000 | 0 | 0 | 97000 | 97000 | 0 | 0
66 | SECURITY ACCESS & SURVEILLANCE |  | 136430 | 0 | 0 | 136430 | 136430 | 0 | 0
67 | ELEVATORS & LIFT |  | 174882 | 0 | 0 | 174882 | 174882 | 0 | 0
68 | WATER SUBMETER (material) |  | 12273 | 0 | 0 | 12273 | 12273 | 0 | 0
69 | WATER SUBMETER (labor) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
70 | ROUGH PLUMBING |  | 751927 | 0 | 0 | 751927 | 751927 | 0 | 0
71 | FINISH PLUMBING |  | 90000 | 0 | 0 | 90000 | 90000 | 0 | 0
72 | HVAC |  | 259000 | 0 | 0 | 259000 | 259000 | 0 | 0
73 | ELECTRICAL |  | 880486.32 | 0 | 0 | 880486.32 | 880486.32 | 0 | 0
74 | CONTINGENCY |  | 529215.2 | 0 | 0 | 529215.2 | 529215.2 | 0 | 0
75 | INSURANCE (GL w/auto, workers compl) |  | 97177.07 | 0 | 0 | 97177.07 | 97177.07 | 0 | 0
76 | GROSS RECEIPT TAX |  | 6543.26 | 0 | 0 | 6543.26 | 6543.26 | 0 | 0
77 | GC FEE |  | 388708.28 | 0 | 0 | 388708.28 | 388708.28 | 0 | 0
78 | DEVELOPMENT FEE |  | 180523.5 | 0 | 0 | 180523.5 | 180523.5 | 0 | 0
79 | CARRYING COSTS |  | 92885.53 | 0 | 0 | 92885.53 | 92885.53 | 0 | 0
80 | FINANCING COSTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
82 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
83 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
84 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
85 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
86 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
87 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
88 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
89 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
90 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
91 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
92 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
93 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
94 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
95 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
96 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
97 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
98 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
99 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
| TOTAL |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0

## Draw #13
GENESIS CAPITAL DRAW FORM
| CLIENT: | Angeleno Investments | [5 empty] | TOTAL COMPLETED TO DATE: | 0 | #REF!
| DATE: | 2025-11-17 | [5 empty] | REMAINING $ IN BUDGET: | #REF!
| PROJECT: | 10910 Huston Street | [5 empty] | ORIGINAL SCHEDULE OF VALUES: | #REF!
| DRAW REQUEST: | 0 | [5 empty] | CHANGE ORDERS: | 0
[8 empty] | REVISED SCHEDULE OF VALUES: | #REF!
| DESCRIPTION OF WORK |  | SCHEDULED VALUES | PREVIOUS | + / - CHANGES | REVISED VALUES | REMAINING | DRAW | COMPLETED AND
|  |  |  | CHANGES |  |  | BUDGET | 13 | STORED TO DATE
1 | SOFT COSTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Site Security |  | 10580.63 | 0 | 0 | 10580.63 | 10580.63 | 0 | 0
3 | Soils Inspection |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Offsites (Transformer) |  | 20000 | 0 | 0 | 20000 | 20000 | 0 | 0
5 | Plan Check Fees |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Permits |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Survey |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Soils Engineer |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Soils Permit + T24 |  | 2500 | 0 | 0 | 2500 | 2500 | 0 | 0
10 | Special Inspections - Deputy |  | 15000 | 0 | 0 | 15000 | 15000 | 0 | 0
11 | Architect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Structural Engineer |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Structural Observation |  | 8000 | 0 | 0 | 8000 | 8000 | 0 | 0
14 | Civil Engineering |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | Grading Permit |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Landscape Architect/Designer |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Driveway Apron Permit |  | 2500 | 0 | 0 | 2500 | 2500 | 0 | 0
18 | Punch List - Misc. |  | 21962.77 | 0 | 0 | 21962.77 | 21962.77 | 0 | 0
19 | EBM, Low Voltage, Landscape, Waterproofing CA |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | Project Accounting/Tax Filing |  | 12994.01 | 0 | 0 | 12994.01 | 12994.01 | 0 | 0
21 | Legal & Professional Fees |  | 873.39 | 0 | 0 | 873.39 | 873.39 | 0 | 0
22 | Sewer CCTV and inspection |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | Environmental Phase I |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | Dry Utility Consultant |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | Dry Utility Survey |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
26 | MEP |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | Civil Construction Administration |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
28 | Permit Clearances & Agency Reviews |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | Demo Permit Fees |  | 500 | 0 | 0 | 500 | 500 | 0 | 0
30 | MEP Fees |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | Agency Signoffs |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | Specifications Writer Consultant |  | 2000 | 0 | 0 | 2000 | 2000 | 0 | 0
33 | Construction Consultant |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | Low Voltage Consultant |  | 15524 | 0 | 0 | 15524 | 15524 | 0 | 0
35 | Photovoltaic Consultant |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
36 | Construction Management / Observation (OO) |  | 49427.9 | 0 | 0 | 49427.9 | 49427.9 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
37 | CMFA Startup Fee |  | 22800 | 0 | 0 | 22800 | 22800 | 0 | 0
38 | Non-Profit Start Up Fee |  | 25000 | 0 | 0 | 25000 | 25000 | 0 | 0
39 | CMFA Construction Fee |  | 12000 | 0 | 0 | 12000 | 12000 | 0 | 0
40 | Non-Profit Construction Fee |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
41 | WTE Legal Costs for CMFA & Non-Profit Partner |  | 20000 | 0 | 0 | 20000 | 20000 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
43 | GENERAL CONDITIONS |  | 362115.24 | 0 | 0 | 362115.24 | 362115.24 | 0 | 0
44 | GENERAL REQUIREMENT |  | 124657.88 | 0 | 0 | 124657.88 | 124657.88 | 0 | 0
45 | SITE WORK |  | 139049.51 | 0 | 0 | 139049.51 | 139049.51 | 0 | 0
46 | CONCRETE |  | 253182 | 0 | 0 | 253182 | 253182 | 0 | 0
47 | MASONRY |  | 3562.64 | 0 | 0 | 3562.64 | 3562.64 | 0 | 0
48 | METALS |  | 324100 | 0 | 0 | 324100 | 324100 | 0 | 0
49 | FRAMING |  | 818554 | 0 | 0 | 818554 | 818554 | 0 | 0
50 | COUNTERTOPS |  | 56930 | 0 | 0 | 56930 | 56930 | 0 | 0
51 | CABINETS |  | 56930 | 0 | 0 | 56930 | 56930 | 0 | 0
52 | THERMAL MOISTURE PROTECTION |  | 173148 | 0 | 0 | 173148 | 173148 | 0 | 0
53 | DOORS |  | 204087.33 | 0 | 0 | 204087.33 | 204087.33 | 0 | 0
54 | WINDOWS |  | 106274.25 | 0 | 0 | 106274.25 | 106274.25 | 0 | 0
55 | STUCCO |  | 208002 | 0 | 0 | 208002 | 208002 | 0 | 0
56 | DRYWALL |  | 416355 | 0 | 0 | 416355 | 416355 | 0 | 0
57 | PAINTING |  | 120700 | 0 | 0 | 120700 | 120700 | 0 | 0
58 | FLOORING - common areas |  | 45150 | 0 | 0 | 45150 | 45150 | 0 | 0
59 | FLOORING - Units with baseboards |  | 93335 | 0 | 0 | 93335 | 93335 | 0 | 0
60 | SPECIALTIES |  | 25109.21 | 0 | 0 | 25109.21 | 25109.21 | 0 | 0
61 | EQUIPMENT |  | 153636 | 0 | 0 | 153636 | 153636 | 0 | 0
62 | FURNISHING |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
63 | FIRE SPRINKLERS |  | 108500 | 0 | 0 | 108500 | 108500 | 0 | 0
64 | FIRE ALARM |  | 68401 | 0 | 0 | 68401 | 68401 | 0 | 0
65 | SOLAR PANELS |  | 97000 | 0 | 0 | 97000 | 97000 | 0 | 0
66 | SECURITY ACCESS & SURVEILLANCE |  | 136430 | 0 | 0 | 136430 | 136430 | 0 | 0
67 | ELEVATORS & LIFT |  | 174882 | 0 | 0 | 174882 | 174882 | 0 | 0
68 | WATER SUBMETER (material) |  | 12273 | 0 | 0 | 12273 | 12273 | 0 | 0
69 | WATER SUBMETER (labor) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
70 | ROUGH PLUMBING |  | 751927 | 0 | 0 | 751927 | 751927 | 0 | 0
71 | FINISH PLUMBING |  | 90000 | 0 | 0 | 90000 | 90000 | 0 | 0
72 | HVAC |  | 259000 | 0 | 0 | 259000 | 259000 | 0 | 0
73 | ELECTRICAL |  | 880486.32 | 0 | 0 | 880486.32 | 880486.32 | 0 | 0
74 | CONTINGENCY |  | 529215.2 | 0 | 0 | 529215.2 | 529215.2 | 0 | 0
75 | INSURANCE (GL w/auto, workers compl) |  | 97177.07 | 0 | 0 | 97177.07 | 97177.07 | 0 | 0
76 | GROSS RECEIPT TAX |  | 6543.26 | 0 | 0 | 6543.26 | 6543.26 | 0 | 0
77 | GC FEE |  | 388708.28 | 0 | 0 | 388708.28 | 388708.28 | 0 | 0
78 | DEVELOPMENT FEE |  | 180523.5 | 0 | 0 | 180523.5 | 180523.5 | 0 | 0
79 | CARRYING COSTS |  | 92885.53 | 0 | 0 | 92885.53 | 92885.53 | 0 | 0
80 | FINANCING COSTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
82 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
83 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
84 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
85 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
86 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
87 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
88 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
89 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
90 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
91 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
92 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
93 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
94 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
95 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
96 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
97 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
98 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
99 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
| TOTAL |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0

## Draw #14
GENESIS CAPITAL DRAW FORM
| CLIENT: | Angeleno Investments | [5 empty] | TOTAL COMPLETED TO DATE: | 0 | #REF!
| DATE: | 2025-11-17 | [5 empty] | REMAINING $ IN BUDGET: | #REF!
| PROJECT: | 10910 Huston Street | [5 empty] | ORIGINAL SCHEDULE OF VALUES: | #REF!
| DRAW REQUEST: | 0 | [5 empty] | CHANGE ORDERS: | 0
[8 empty] | REVISED SCHEDULE OF VALUES: | #REF!
| DESCRIPTION OF WORK |  | SCHEDULED VALUES | PREVIOUS | + / - CHANGES | REVISED VALUES | REMAINING | DRAW | COMPLETED AND
|  |  |  | CHANGES |  |  | BUDGET | 14 | STORED TO DATE
1 | SOFT COSTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Site Security |  | 10580.63 | 0 | 0 | 10580.63 | 10580.63 | 0 | 0
3 | Soils Inspection |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Offsites (Transformer) |  | 20000 | 0 | 0 | 20000 | 20000 | 0 | 0
5 | Plan Check Fees |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Permits |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Survey |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Soils Engineer |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Soils Permit + T24 |  | 2500 | 0 | 0 | 2500 | 2500 | 0 | 0
10 | Special Inspections - Deputy |  | 15000 | 0 | 0 | 15000 | 15000 | 0 | 0
11 | Architect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Structural Engineer |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Structural Observation |  | 8000 | 0 | 0 | 8000 | 8000 | 0 | 0
14 | Civil Engineering |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | Grading Permit |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Landscape Architect/Designer |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Driveway Apron Permit |  | 2500 | 0 | 0 | 2500 | 2500 | 0 | 0
18 | Punch List - Misc. |  | 21962.77 | 0 | 0 | 21962.77 | 21962.77 | 0 | 0
19 | EBM, Low Voltage, Landscape, Waterproofing CA |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | Project Accounting/Tax Filing |  | 12994.01 | 0 | 0 | 12994.01 | 12994.01 | 0 | 0
21 | Legal & Professional Fees |  | 873.39 | 0 | 0 | 873.39 | 873.39 | 0 | 0
22 | Sewer CCTV and inspection |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | Environmental Phase I |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | Dry Utility Consultant |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | Dry Utility Survey |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
26 | MEP |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | Civil Construction Administration |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
28 | Permit Clearances & Agency Reviews |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | Demo Permit Fees |  | 500 | 0 | 0 | 500 | 500 | 0 | 0
30 | MEP Fees |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | Agency Signoffs |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | Specifications Writer Consultant |  | 2000 | 0 | 0 | 2000 | 2000 | 0 | 0
33 | Construction Consultant |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | Low Voltage Consultant |  | 15524 | 0 | 0 | 15524 | 15524 | 0 | 0
35 | Photovoltaic Consultant |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
36 | Construction Management / Observation (OO) |  | 49427.9 | 0 | 0 | 49427.9 | 49427.9 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
37 | CMFA Startup Fee |  | 22800 | 0 | 0 | 22800 | 22800 | 0 | 0
38 | Non-Profit Start Up Fee |  | 25000 | 0 | 0 | 25000 | 25000 | 0 | 0
39 | CMFA Construction Fee |  | 12000 | 0 | 0 | 12000 | 12000 | 0 | 0
40 | Non-Profit Construction Fee |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
41 | WTE Legal Costs for CMFA & Non-Profit Partner |  | 20000 | 0 | 0 | 20000 | 20000 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
43 | GENERAL CONDITIONS |  | 362115.24 | 0 | 0 | 362115.24 | 362115.24 | 0 | 0
44 | GENERAL REQUIREMENT |  | 124657.88 | 0 | 0 | 124657.88 | 124657.88 | 0 | 0
45 | SITE WORK |  | 139049.51 | 0 | 0 | 139049.51 | 139049.51 | 0 | 0
46 | CONCRETE |  | 253182 | 0 | 0 | 253182 | 253182 | 0 | 0
47 | MASONRY |  | 3562.64 | 0 | 0 | 3562.64 | 3562.64 | 0 | 0
48 | METALS |  | 324100 | 0 | 0 | 324100 | 324100 | 0 | 0
49 | FRAMING |  | 818554 | 0 | 0 | 818554 | 818554 | 0 | 0
50 | COUNTERTOPS |  | 56930 | 0 | 0 | 56930 | 56930 | 0 | 0
51 | CABINETS |  | 56930 | 0 | 0 | 56930 | 56930 | 0 | 0
52 | THERMAL MOISTURE PROTECTION |  | 173148 | 0 | 0 | 173148 | 173148 | 0 | 0
53 | DOORS |  | 204087.33 | 0 | 0 | 204087.33 | 204087.33 | 0 | 0
54 | WINDOWS |  | 106274.25 | 0 | 0 | 106274.25 | 106274.25 | 0 | 0
55 | STUCCO |  | 208002 | 0 | 0 | 208002 | 208002 | 0 | 0
56 | DRYWALL |  | 416355 | 0 | 0 | 416355 | 416355 | 0 | 0
57 | PAINTING |  | 120700 | 0 | 0 | 120700 | 120700 | 0 | 0
58 | FLOORING - common areas |  | 45150 | 0 | 0 | 45150 | 45150 | 0 | 0
59 | FLOORING - Units with baseboards |  | 93335 | 0 | 0 | 93335 | 93335 | 0 | 0
60 | SPECIALTIES |  | 25109.21 | 0 | 0 | 25109.21 | 25109.21 | 0 | 0
61 | EQUIPMENT |  | 153636 | 0 | 0 | 153636 | 153636 | 0 | 0
62 | FURNISHING |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
63 | FIRE SPRINKLERS |  | 108500 | 0 | 0 | 108500 | 108500 | 0 | 0
64 | FIRE ALARM |  | 68401 | 0 | 0 | 68401 | 68401 | 0 | 0
65 | SOLAR PANELS |  | 97000 | 0 | 0 | 97000 | 97000 | 0 | 0
66 | SECURITY ACCESS & SURVEILLANCE |  | 136430 | 0 | 0 | 136430 | 136430 | 0 | 0
67 | ELEVATORS & LIFT |  | 174882 | 0 | 0 | 174882 | 174882 | 0 | 0
68 | WATER SUBMETER (material) |  | 12273 | 0 | 0 | 12273 | 12273 | 0 | 0
69 | WATER SUBMETER (labor) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
70 | ROUGH PLUMBING |  | 751927 | 0 | 0 | 751927 | 751927 | 0 | 0
71 | FINISH PLUMBING |  | 90000 | 0 | 0 | 90000 | 90000 | 0 | 0
72 | HVAC |  | 259000 | 0 | 0 | 259000 | 259000 | 0 | 0
73 | ELECTRICAL |  | 880486.32 | 0 | 0 | 880486.32 | 880486.32 | 0 | 0
74 | CONTINGENCY |  | 529215.2 | 0 | 0 | 529215.2 | 529215.2 | 0 | 0
75 | INSURANCE (GL w/auto, workers compl) |  | 97177.07 | 0 | 0 | 97177.07 | 97177.07 | 0 | 0
76 | GROSS RECEIPT TAX |  | 6543.26 | 0 | 0 | 6543.26 | 6543.26 | 0 | 0
77 | GC FEE |  | 388708.28 | 0 | 0 | 388708.28 | 388708.28 | 0 | 0
78 | DEVELOPMENT FEE |  | 180523.5 | 0 | 0 | 180523.5 | 180523.5 | 0 | 0
79 | CARRYING COSTS |  | 92885.53 | 0 | 0 | 92885.53 | 92885.53 | 0 | 0
80 | FINANCING COSTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
82 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
83 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
84 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
85 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
86 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
87 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
88 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
89 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
90 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
91 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
92 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
93 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
94 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
95 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
96 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
97 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
98 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
99 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
| TOTAL |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0

## Draw #15
GENESIS CAPITAL DRAW FORM
| CLIENT: | Angeleno Investments | [5 empty] | TOTAL COMPLETED TO DATE: | 0 | #REF!
| DATE: | 2025-11-17 | [5 empty] | REMAINING $ IN BUDGET: | #REF!
| PROJECT: | 10910 Huston Street | [5 empty] | ORIGINAL SCHEDULE OF VALUES: | #REF!
| DRAW REQUEST: | 0 | [5 empty] | CHANGE ORDERS: | 0
[8 empty] | REVISED SCHEDULE OF VALUES: | #REF!
| DESCRIPTION OF WORK |  | SCHEDULED VALUES | PREVIOUS | + / - CHANGES | REVISED VALUES | REMAINING | DRAW | COMPLETED AND
|  |  |  | CHANGES |  |  | BUDGET | 15 | STORED TO DATE
1 | SOFT COSTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Site Security |  | 10580.63 | 0 | 0 | 10580.63 | 10580.63 | 0 | 0
3 | Soils Inspection |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Offsites (Transformer) |  | 20000 | 0 | 0 | 20000 | 20000 | 0 | 0
5 | Plan Check Fees |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Permits |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Survey |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Soils Engineer |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Soils Permit + T24 |  | 2500 | 0 | 0 | 2500 | 2500 | 0 | 0
10 | Special Inspections - Deputy |  | 15000 | 0 | 0 | 15000 | 15000 | 0 | 0
11 | Architect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Structural Engineer |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Structural Observation |  | 8000 | 0 | 0 | 8000 | 8000 | 0 | 0
14 | Civil Engineering |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | Grading Permit |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Landscape Architect/Designer |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Driveway Apron Permit |  | 2500 | 0 | 0 | 2500 | 2500 | 0 | 0
18 | Punch List - Misc. |  | 21962.77 | 0 | 0 | 21962.77 | 21962.77 | 0 | 0
19 | EBM, Low Voltage, Landscape, Waterproofing CA |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | Project Accounting/Tax Filing |  | 12994.01 | 0 | 0 | 12994.01 | 12994.01 | 0 | 0
21 | Legal & Professional Fees |  | 873.39 | 0 | 0 | 873.39 | 873.39 | 0 | 0
22 | Sewer CCTV and inspection |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | Environmental Phase I |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | Dry Utility Consultant |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | Dry Utility Survey |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
26 | MEP |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | Civil Construction Administration |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
28 | Permit Clearances & Agency Reviews |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | Demo Permit Fees |  | 500 | 0 | 0 | 500 | 500 | 0 | 0
30 | MEP Fees |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | Agency Signoffs |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | Specifications Writer Consultant |  | 2000 | 0 | 0 | 2000 | 2000 | 0 | 0
33 | Construction Consultant |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | Low Voltage Consultant |  | 15524 | 0 | 0 | 15524 | 15524 | 0 | 0
35 | Photovoltaic Consultant |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
36 | Construction Management / Observation (OO) |  | 49427.9 | 0 | 0 | 49427.9 | 49427.9 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
37 | CMFA Startup Fee |  | 22800 | 0 | 0 | 22800 | 22800 | 0 | 0
38 | Non-Profit Start Up Fee |  | 25000 | 0 | 0 | 25000 | 25000 | 0 | 0
39 | CMFA Construction Fee |  | 12000 | 0 | 0 | 12000 | 12000 | 0 | 0
40 | Non-Profit Construction Fee |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
41 | WTE Legal Costs for CMFA & Non-Profit Partner |  | 20000 | 0 | 0 | 20000 | 20000 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
43 | GENERAL CONDITIONS |  | 362115.24 | 0 | 0 | 362115.24 | 362115.24 | 0 | 0
44 | GENERAL REQUIREMENT |  | 124657.88 | 0 | 0 | 124657.88 | 124657.88 | 0 | 0
45 | SITE WORK |  | 139049.51 | 0 | 0 | 139049.51 | 139049.51 | 0 | 0
46 | CONCRETE |  | 253182 | 0 | 0 | 253182 | 253182 | 0 | 0
47 | MASONRY |  | 3562.64 | 0 | 0 | 3562.64 | 3562.64 | 0 | 0
48 | METALS |  | 324100 | 0 | 0 | 324100 | 324100 | 0 | 0
49 | FRAMING |  | 818554 | 0 | 0 | 818554 | 818554 | 0 | 0
50 | COUNTERTOPS |  | 56930 | 0 | 0 | 56930 | 56930 | 0 | 0
51 | CABINETS |  | 56930 | 0 | 0 | 56930 | 56930 | 0 | 0
52 | THERMAL MOISTURE PROTECTION |  | 173148 | 0 | 0 | 173148 | 173148 | 0 | 0
53 | DOORS |  | 204087.33 | 0 | 0 | 204087.33 | 204087.33 | 0 | 0
54 | WINDOWS |  | 106274.25 | 0 | 0 | 106274.25 | 106274.25 | 0 | 0
55 | STUCCO |  | 208002 | 0 | 0 | 208002 | 208002 | 0 | 0
56 | DRYWALL |  | 416355 | 0 | 0 | 416355 | 416355 | 0 | 0
57 | PAINTING |  | 120700 | 0 | 0 | 120700 | 120700 | 0 | 0
58 | FLOORING - common areas |  | 45150 | 0 | 0 | 45150 | 45150 | 0 | 0
59 | FLOORING - Units with baseboards |  | 93335 | 0 | 0 | 93335 | 93335 | 0 | 0
60 | SPECIALTIES |  | 25109.21 | 0 | 0 | 25109.21 | 25109.21 | 0 | 0
61 | EQUIPMENT |  | 153636 | 0 | 0 | 153636 | 153636 | 0 | 0
62 | FURNISHING |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
63 | FIRE SPRINKLERS |  | 108500 | 0 | 0 | 108500 | 108500 | 0 | 0
64 | FIRE ALARM |  | 68401 | 0 | 0 | 68401 | 68401 | 0 | 0
65 | SOLAR PANELS |  | 97000 | 0 | 0 | 97000 | 97000 | 0 | 0
66 | SECURITY ACCESS & SURVEILLANCE |  | 136430 | 0 | 0 | 136430 | 136430 | 0 | 0
67 | ELEVATORS & LIFT |  | 174882 | 0 | 0 | 174882 | 174882 | 0 | 0
68 | WATER SUBMETER (material) |  | 12273 | 0 | 0 | 12273 | 12273 | 0 | 0
69 | WATER SUBMETER (labor) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
70 | ROUGH PLUMBING |  | 751927 | 0 | 0 | 751927 | 751927 | 0 | 0
71 | FINISH PLUMBING |  | 90000 | 0 | 0 | 90000 | 90000 | 0 | 0
72 | HVAC |  | 259000 | 0 | 0 | 259000 | 259000 | 0 | 0
73 | ELECTRICAL |  | 880486.32 | 0 | 0 | 880486.32 | 880486.32 | 0 | 0
74 | CONTINGENCY |  | 529215.2 | 0 | 0 | 529215.2 | 529215.2 | 0 | 0
75 | INSURANCE (GL w/auto, workers compl) |  | 97177.07 | 0 | 0 | 97177.07 | 97177.07 | 0 | 0
76 | GROSS RECEIPT TAX |  | 6543.26 | 0 | 0 | 6543.26 | 6543.26 | 0 | 0
77 | GC FEE |  | 388708.28 | 0 | 0 | 388708.28 | 388708.28 | 0 | 0
78 | DEVELOPMENT FEE |  | 180523.5 | 0 | 0 | 180523.5 | 180523.5 | 0 | 0
79 | CARRYING COSTS |  | 92885.53 | 0 | 0 | 92885.53 | 92885.53 | 0 | 0
80 | FINANCING COSTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
82 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
83 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
84 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
85 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
86 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
87 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
88 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
89 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
90 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
91 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
92 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
93 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
94 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
95 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
96 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
97 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
98 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
99 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
| TOTAL |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0

## Draw #16
GENESIS CAPITAL DRAW FORM
| CLIENT: | Angeleno Investments | [5 empty] | TOTAL COMPLETED TO DATE: | 0 | #REF!
| DATE: | 2025-11-17 | [5 empty] | REMAINING $ IN BUDGET: | #REF!
| PROJECT: | 10910 Huston Street | [5 empty] | ORIGINAL SCHEDULE OF VALUES: | #REF!
| DRAW REQUEST: | 0 | [5 empty] | CHANGE ORDERS: | 0
[8 empty] | REVISED SCHEDULE OF VALUES: | #REF!
| DESCRIPTION OF WORK |  | SCHEDULED VALUES | PREVIOUS | + / - CHANGES | REVISED VALUES | REMAINING | DRAW | COMPLETED AND
|  |  |  | CHANGES |  |  | BUDGET | 16 | STORED TO DATE
1 | SOFT COSTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Site Security |  | 10580.63 | 0 | 0 | 10580.63 | 10580.63 | 0 | 0
3 | Soils Inspection |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Offsites (Transformer) |  | 20000 | 0 | 0 | 20000 | 20000 | 0 | 0
5 | Plan Check Fees |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Permits |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Survey |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Soils Engineer |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Soils Permit + T24 |  | 2500 | 0 | 0 | 2500 | 2500 | 0 | 0
10 | Special Inspections - Deputy |  | 15000 | 0 | 0 | 15000 | 15000 | 0 | 0
11 | Architect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Structural Engineer |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Structural Observation |  | 8000 | 0 | 0 | 8000 | 8000 | 0 | 0
14 | Civil Engineering |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | Grading Permit |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Landscape Architect/Designer |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Driveway Apron Permit |  | 2500 | 0 | 0 | 2500 | 2500 | 0 | 0
18 | Punch List - Misc. |  | 21962.77 | 0 | 0 | 21962.77 | 21962.77 | 0 | 0
19 | EBM, Low Voltage, Landscape, Waterproofing CA |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | Project Accounting/Tax Filing |  | 12994.01 | 0 | 0 | 12994.01 | 12994.01 | 0 | 0
21 | Legal & Professional Fees |  | 873.39 | 0 | 0 | 873.39 | 873.39 | 0 | 0
22 | Sewer CCTV and inspection |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | Environmental Phase I |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | Dry Utility Consultant |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | Dry Utility Survey |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
26 | MEP |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | Civil Construction Administration |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
28 | Permit Clearances & Agency Reviews |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | Demo Permit Fees |  | 500 | 0 | 0 | 500 | 500 | 0 | 0
30 | MEP Fees |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | Agency Signoffs |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | Specifications Writer Consultant |  | 2000 | 0 | 0 | 2000 | 2000 | 0 | 0
33 | Construction Consultant |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | Low Voltage Consultant |  | 15524 | 0 | 0 | 15524 | 15524 | 0 | 0
35 | Photovoltaic Consultant |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
36 | Construction Management / Observation (OO) |  | 49427.9 | 0 | 0 | 49427.9 | 49427.9 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
37 | CMFA Startup Fee |  | 22800 | 0 | 0 | 22800 | 22800 | 0 | 0
38 | Non-Profit Start Up Fee |  | 25000 | 0 | 0 | 25000 | 25000 | 0 | 0
39 | CMFA Construction Fee |  | 12000 | 0 | 0 | 12000 | 12000 | 0 | 0
40 | Non-Profit Construction Fee |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
41 | WTE Legal Costs for CMFA & Non-Profit Partner |  | 20000 | 0 | 0 | 20000 | 20000 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
43 | GENERAL CONDITIONS |  | 362115.24 | 0 | 0 | 362115.24 | 362115.24 | 0 | 0
44 | GENERAL REQUIREMENT |  | 124657.88 | 0 | 0 | 124657.88 | 124657.88 | 0 | 0
45 | SITE WORK |  | 139049.51 | 0 | 0 | 139049.51 | 139049.51 | 0 | 0
46 | CONCRETE |  | 253182 | 0 | 0 | 253182 | 253182 | 0 | 0
47 | MASONRY |  | 3562.64 | 0 | 0 | 3562.64 | 3562.64 | 0 | 0
48 | METALS |  | 324100 | 0 | 0 | 324100 | 324100 | 0 | 0
49 | FRAMING |  | 818554 | 0 | 0 | 818554 | 818554 | 0 | 0
50 | COUNTERTOPS |  | 56930 | 0 | 0 | 56930 | 56930 | 0 | 0
51 | CABINETS |  | 56930 | 0 | 0 | 56930 | 56930 | 0 | 0
52 | THERMAL MOISTURE PROTECTION |  | 173148 | 0 | 0 | 173148 | 173148 | 0 | 0
53 | DOORS |  | 204087.33 | 0 | 0 | 204087.33 | 204087.33 | 0 | 0
54 | WINDOWS |  | 106274.25 | 0 | 0 | 106274.25 | 106274.25 | 0 | 0
55 | STUCCO |  | 208002 | 0 | 0 | 208002 | 208002 | 0 | 0
56 | DRYWALL |  | 416355 | 0 | 0 | 416355 | 416355 | 0 | 0
57 | PAINTING |  | 120700 | 0 | 0 | 120700 | 120700 | 0 | 0
58 | FLOORING - common areas |  | 45150 | 0 | 0 | 45150 | 45150 | 0 | 0
59 | FLOORING - Units with baseboards |  | 93335 | 0 | 0 | 93335 | 93335 | 0 | 0
60 | SPECIALTIES |  | 25109.21 | 0 | 0 | 25109.21 | 25109.21 | 0 | 0
61 | EQUIPMENT |  | 153636 | 0 | 0 | 153636 | 153636 | 0 | 0
62 | FURNISHING |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
63 | FIRE SPRINKLERS |  | 108500 | 0 | 0 | 108500 | 108500 | 0 | 0
64 | FIRE ALARM |  | 68401 | 0 | 0 | 68401 | 68401 | 0 | 0
65 | SOLAR PANELS |  | 97000 | 0 | 0 | 97000 | 97000 | 0 | 0
66 | SECURITY ACCESS & SURVEILLANCE |  | 136430 | 0 | 0 | 136430 | 136430 | 0 | 0
67 | ELEVATORS & LIFT |  | 174882 | 0 | 0 | 174882 | 174882 | 0 | 0
68 | WATER SUBMETER (material) |  | 12273 | 0 | 0 | 12273 | 12273 | 0 | 0
69 | WATER SUBMETER (labor) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
70 | ROUGH PLUMBING |  | 751927 | 0 | 0 | 751927 | 751927 | 0 | 0
71 | FINISH PLUMBING |  | 90000 | 0 | 0 | 90000 | 90000 | 0 | 0
72 | HVAC |  | 259000 | 0 | 0 | 259000 | 259000 | 0 | 0
73 | ELECTRICAL |  | 880486.32 | 0 | 0 | 880486.32 | 880486.32 | 0 | 0
74 | CONTINGENCY |  | 529215.2 | 0 | 0 | 529215.2 | 529215.2 | 0 | 0
75 | INSURANCE (GL w/auto, workers compl) |  | 97177.07 | 0 | 0 | 97177.07 | 97177.07 | 0 | 0
76 | GROSS RECEIPT TAX |  | 6543.26 | 0 | 0 | 6543.26 | 6543.26 | 0 | 0
77 | GC FEE |  | 388708.28 | 0 | 0 | 388708.28 | 388708.28 | 0 | 0
78 | DEVELOPMENT FEE |  | 180523.5 | 0 | 0 | 180523.5 | 180523.5 | 0 | 0
79 | CARRYING COSTS |  | 92885.53 | 0 | 0 | 92885.53 | 92885.53 | 0 | 0
80 | FINANCING COSTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
82 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
83 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
84 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
85 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
86 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
87 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
88 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
89 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
90 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
91 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
92 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
93 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
94 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
95 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
96 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
97 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
98 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
99 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
| TOTAL |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0

## Draw #17
GENESIS CAPITAL DRAW FORM
| CLIENT: | Angeleno Investments | [5 empty] | TOTAL COMPLETED TO DATE: | 0 | #REF!
| DATE: | 2025-11-17 | [5 empty] | REMAINING $ IN BUDGET: | #REF!
| PROJECT: | 10910 Huston Street | [5 empty] | ORIGINAL SCHEDULE OF VALUES: | #REF!
| DRAW REQUEST: | 0 | [5 empty] | CHANGE ORDERS: | 0
[8 empty] | REVISED SCHEDULE OF VALUES: | #REF!
| DESCRIPTION OF WORK |  | SCHEDULED VALUES | PREVIOUS | + / - CHANGES | REVISED VALUES | REMAINING | DRAW | COMPLETED AND
|  |  |  | CHANGES |  |  | BUDGET | 17 | STORED TO DATE
1 | SOFT COSTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Site Security |  | 10580.63 | 0 | 0 | 10580.63 | 10580.63 | 0 | 0
3 | Soils Inspection |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Offsites (Transformer) |  | 20000 | 0 | 0 | 20000 | 20000 | 0 | 0
5 | Plan Check Fees |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Permits |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Survey |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Soils Engineer |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Soils Permit + T24 |  | 2500 | 0 | 0 | 2500 | 2500 | 0 | 0
10 | Special Inspections - Deputy |  | 15000 | 0 | 0 | 15000 | 15000 | 0 | 0
11 | Architect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Structural Engineer |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Structural Observation |  | 8000 | 0 | 0 | 8000 | 8000 | 0 | 0
14 | Civil Engineering |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | Grading Permit |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Landscape Architect/Designer |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Driveway Apron Permit |  | 2500 | 0 | 0 | 2500 | 2500 | 0 | 0
18 | Punch List - Misc. |  | 21962.77 | 0 | 0 | 21962.77 | 21962.77 | 0 | 0
19 | EBM, Low Voltage, Landscape, Waterproofing CA |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | Project Accounting/Tax Filing |  | 12994.01 | 0 | 0 | 12994.01 | 12994.01 | 0 | 0
21 | Legal & Professional Fees |  | 873.39 | 0 | 0 | 873.39 | 873.39 | 0 | 0
22 | Sewer CCTV and inspection |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | Environmental Phase I |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | Dry Utility Consultant |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | Dry Utility Survey |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
26 | MEP |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | Civil Construction Administration |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
28 | Permit Clearances & Agency Reviews |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | Demo Permit Fees |  | 500 | 0 | 0 | 500 | 500 | 0 | 0
30 | MEP Fees |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | Agency Signoffs |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | Specifications Writer Consultant |  | 2000 | 0 | 0 | 2000 | 2000 | 0 | 0
33 | Construction Consultant |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | Low Voltage Consultant |  | 15524 | 0 | 0 | 15524 | 15524 | 0 | 0
35 | Photovoltaic Consultant |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
36 | Construction Management / Observation (OO) |  | 49427.9 | 0 | 0 | 49427.9 | 49427.9 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
37 | CMFA Startup Fee |  | 22800 | 0 | 0 | 22800 | 22800 | 0 | 0
38 | Non-Profit Start Up Fee |  | 25000 | 0 | 0 | 25000 | 25000 | 0 | 0
39 | CMFA Construction Fee |  | 12000 | 0 | 0 | 12000 | 12000 | 0 | 0
40 | Non-Profit Construction Fee |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
41 | WTE Legal Costs for CMFA & Non-Profit Partner |  | 20000 | 0 | 0 | 20000 | 20000 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
43 | GENERAL CONDITIONS |  | 362115.24 | 0 | 0 | 362115.24 | 362115.24 | 0 | 0
44 | GENERAL REQUIREMENT |  | 124657.88 | 0 | 0 | 124657.88 | 124657.88 | 0 | 0
45 | SITE WORK |  | 139049.51 | 0 | 0 | 139049.51 | 139049.51 | 0 | 0
46 | CONCRETE |  | 253182 | 0 | 0 | 253182 | 253182 | 0 | 0
47 | MASONRY |  | 3562.64 | 0 | 0 | 3562.64 | 3562.64 | 0 | 0
48 | METALS |  | 324100 | 0 | 0 | 324100 | 324100 | 0 | 0
49 | FRAMING |  | 818554 | 0 | 0 | 818554 | 818554 | 0 | 0
50 | COUNTERTOPS |  | 56930 | 0 | 0 | 56930 | 56930 | 0 | 0
51 | CABINETS |  | 56930 | 0 | 0 | 56930 | 56930 | 0 | 0
52 | THERMAL MOISTURE PROTECTION |  | 173148 | 0 | 0 | 173148 | 173148 | 0 | 0
53 | DOORS |  | 204087.33 | 0 | 0 | 204087.33 | 204087.33 | 0 | 0
54 | WINDOWS |  | 106274.25 | 0 | 0 | 106274.25 | 106274.25 | 0 | 0
55 | STUCCO |  | 208002 | 0 | 0 | 208002 | 208002 | 0 | 0
56 | DRYWALL |  | 416355 | 0 | 0 | 416355 | 416355 | 0 | 0
57 | PAINTING |  | 120700 | 0 | 0 | 120700 | 120700 | 0 | 0
58 | FLOORING - common areas |  | 45150 | 0 | 0 | 45150 | 45150 | 0 | 0
59 | FLOORING - Units with baseboards |  | 93335 | 0 | 0 | 93335 | 93335 | 0 | 0
60 | SPECIALTIES |  | 25109.21 | 0 | 0 | 25109.21 | 25109.21 | 0 | 0
61 | EQUIPMENT |  | 153636 | 0 | 0 | 153636 | 153636 | 0 | 0
62 | FURNISHING |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
63 | FIRE SPRINKLERS |  | 108500 | 0 | 0 | 108500 | 108500 | 0 | 0
64 | FIRE ALARM |  | 68401 | 0 | 0 | 68401 | 68401 | 0 | 0
65 | SOLAR PANELS |  | 97000 | 0 | 0 | 97000 | 97000 | 0 | 0
66 | SECURITY ACCESS & SURVEILLANCE |  | 136430 | 0 | 0 | 136430 | 136430 | 0 | 0
67 | ELEVATORS & LIFT |  | 174882 | 0 | 0 | 174882 | 174882 | 0 | 0
68 | WATER SUBMETER (material) |  | 12273 | 0 | 0 | 12273 | 12273 | 0 | 0
69 | WATER SUBMETER (labor) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
70 | ROUGH PLUMBING |  | 751927 | 0 | 0 | 751927 | 751927 | 0 | 0
71 | FINISH PLUMBING |  | 90000 | 0 | 0 | 90000 | 90000 | 0 | 0
72 | HVAC |  | 259000 | 0 | 0 | 259000 | 259000 | 0 | 0
73 | ELECTRICAL |  | 880486.32 | 0 | 0 | 880486.32 | 880486.32 | 0 | 0
74 | CONTINGENCY |  | 529215.2 | 0 | 0 | 529215.2 | 529215.2 | 0 | 0
75 | INSURANCE (GL w/auto, workers compl) |  | 97177.07 | 0 | 0 | 97177.07 | 97177.07 | 0 | 0
76 | GROSS RECEIPT TAX |  | 6543.26 | 0 | 0 | 6543.26 | 6543.26 | 0 | 0
77 | GC FEE |  | 388708.28 | 0 | 0 | 388708.28 | 388708.28 | 0 | 0
78 | DEVELOPMENT FEE |  | 180523.5 | 0 | 0 | 180523.5 | 180523.5 | 0 | 0
79 | CARRYING COSTS |  | 92885.53 | 0 | 0 | 92885.53 | 92885.53 | 0 | 0
80 | FINANCING COSTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
82 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
83 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
84 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
85 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
86 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
87 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
88 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
89 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
90 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
91 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
92 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
93 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
94 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
95 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
96 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
97 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
98 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
99 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
| TOTAL |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0

## Draw #18
GENESIS CAPITAL DRAW FORM
| CLIENT: | Angeleno Investments | [5 empty] | TOTAL COMPLETED TO DATE: | 0 | #REF!
| DATE: | 2025-11-17 | [5 empty] | REMAINING $ IN BUDGET: | #REF!
| PROJECT: | 10910 Huston Street | [5 empty] | ORIGINAL SCHEDULE OF VALUES: | #REF!
| DRAW REQUEST: | 0 | [5 empty] | CHANGE ORDERS: | 0
[8 empty] | REVISED SCHEDULE OF VALUES: | #REF!
| DESCRIPTION OF WORK |  | SCHEDULED VALUES | PREVIOUS | + / - CHANGES | REVISED VALUES | REMAINING | DRAW | COMPLETED AND
|  |  |  | CHANGES |  |  | BUDGET | 18 | STORED TO DATE
1 | SOFT COSTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Site Security |  | 10580.63 | 0 | 0 | 10580.63 | 10580.63 | 0 | 0
3 | Soils Inspection |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Offsites (Transformer) |  | 20000 | 0 | 0 | 20000 | 20000 | 0 | 0
5 | Plan Check Fees |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Permits |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Survey |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Soils Engineer |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Soils Permit + T24 |  | 2500 | 0 | 0 | 2500 | 2500 | 0 | 0
10 | Special Inspections - Deputy |  | 15000 | 0 | 0 | 15000 | 15000 | 0 | 0
11 | Architect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Structural Engineer |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Structural Observation |  | 8000 | 0 | 0 | 8000 | 8000 | 0 | 0
14 | Civil Engineering |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | Grading Permit |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Landscape Architect/Designer |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Driveway Apron Permit |  | 2500 | 0 | 0 | 2500 | 2500 | 0 | 0
18 | Punch List - Misc. |  | 21962.77 | 0 | 0 | 21962.77 | 21962.77 | 0 | 0
19 | EBM, Low Voltage, Landscape, Waterproofing CA |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | Project Accounting/Tax Filing |  | 12994.01 | 0 | 0 | 12994.01 | 12994.01 | 0 | 0
21 | Legal & Professional Fees |  | 873.39 | 0 | 0 | 873.39 | 873.39 | 0 | 0
22 | Sewer CCTV and inspection |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | Environmental Phase I |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | Dry Utility Consultant |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | Dry Utility Survey |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
26 | MEP |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | Civil Construction Administration |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
28 | Permit Clearances & Agency Reviews |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | Demo Permit Fees |  | 500 | 0 | 0 | 500 | 500 | 0 | 0
30 | MEP Fees |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | Agency Signoffs |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | Specifications Writer Consultant |  | 2000 | 0 | 0 | 2000 | 2000 | 0 | 0
33 | Construction Consultant |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | Low Voltage Consultant |  | 15524 | 0 | 0 | 15524 | 15524 | 0 | 0
35 | Photovoltaic Consultant |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
36 | Construction Management / Observation (OO) |  | 49427.9 | 0 | 0 | 49427.9 | 49427.9 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
37 | CMFA Startup Fee |  | 22800 | 0 | 0 | 22800 | 22800 | 0 | 0
38 | Non-Profit Start Up Fee |  | 25000 | 0 | 0 | 25000 | 25000 | 0 | 0
39 | CMFA Construction Fee |  | 12000 | 0 | 0 | 12000 | 12000 | 0 | 0
40 | Non-Profit Construction Fee |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
41 | WTE Legal Costs for CMFA & Non-Profit Partner |  | 20000 | 0 | 0 | 20000 | 20000 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
43 | GENERAL CONDITIONS |  | 362115.24 | 0 | 0 | 362115.24 | 362115.24 | 0 | 0
44 | GENERAL REQUIREMENT |  | 124657.88 | 0 | 0 | 124657.88 | 124657.88 | 0 | 0
45 | SITE WORK |  | 139049.51 | 0 | 0 | 139049.51 | 139049.51 | 0 | 0
46 | CONCRETE |  | 253182 | 0 | 0 | 253182 | 253182 | 0 | 0
47 | MASONRY |  | 3562.64 | 0 | 0 | 3562.64 | 3562.64 | 0 | 0
48 | METALS |  | 324100 | 0 | 0 | 324100 | 324100 | 0 | 0
49 | FRAMING |  | 818554 | 0 | 0 | 818554 | 818554 | 0 | 0
50 | COUNTERTOPS |  | 56930 | 0 | 0 | 56930 | 56930 | 0 | 0
51 | CABINETS |  | 56930 | 0 | 0 | 56930 | 56930 | 0 | 0
52 | THERMAL MOISTURE PROTECTION |  | 173148 | 0 | 0 | 173148 | 173148 | 0 | 0
53 | DOORS |  | 204087.33 | 0 | 0 | 204087.33 | 204087.33 | 0 | 0
54 | WINDOWS |  | 106274.25 | 0 | 0 | 106274.25 | 106274.25 | 0 | 0
55 | STUCCO |  | 208002 | 0 | 0 | 208002 | 208002 | 0 | 0
56 | DRYWALL |  | 416355 | 0 | 0 | 416355 | 416355 | 0 | 0
57 | PAINTING |  | 120700 | 0 | 0 | 120700 | 120700 | 0 | 0
58 | FLOORING - common areas |  | 45150 | 0 | 0 | 45150 | 45150 | 0 | 0
59 | FLOORING - Units with baseboards |  | 93335 | 0 | 0 | 93335 | 93335 | 0 | 0
60 | SPECIALTIES |  | 25109.21 | 0 | 0 | 25109.21 | 25109.21 | 0 | 0
61 | EQUIPMENT |  | 153636 | 0 | 0 | 153636 | 153636 | 0 | 0
62 | FURNISHING |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
63 | FIRE SPRINKLERS |  | 108500 | 0 | 0 | 108500 | 108500 | 0 | 0
64 | FIRE ALARM |  | 68401 | 0 | 0 | 68401 | 68401 | 0 | 0
65 | SOLAR PANELS |  | 97000 | 0 | 0 | 97000 | 97000 | 0 | 0
66 | SECURITY ACCESS & SURVEILLANCE |  | 136430 | 0 | 0 | 136430 | 136430 | 0 | 0
67 | ELEVATORS & LIFT |  | 174882 | 0 | 0 | 174882 | 174882 | 0 | 0
68 | WATER SUBMETER (material) |  | 12273 | 0 | 0 | 12273 | 12273 | 0 | 0
69 | WATER SUBMETER (labor) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
70 | ROUGH PLUMBING |  | 751927 | 0 | 0 | 751927 | 751927 | 0 | 0
71 | FINISH PLUMBING |  | 90000 | 0 | 0 | 90000 | 90000 | 0 | 0
72 | HVAC |  | 259000 | 0 | 0 | 259000 | 259000 | 0 | 0
73 | ELECTRICAL |  | 880486.32 | 0 | 0 | 880486.32 | 880486.32 | 0 | 0
74 | CONTINGENCY |  | 529215.2 | 0 | 0 | 529215.2 | 529215.2 | 0 | 0
75 | INSURANCE (GL w/auto, workers compl) |  | 97177.07 | 0 | 0 | 97177.07 | 97177.07 | 0 | 0
76 | GROSS RECEIPT TAX |  | 6543.26 | 0 | 0 | 6543.26 | 6543.26 | 0 | 0
77 | GC FEE |  | 388708.28 | 0 | 0 | 388708.28 | 388708.28 | 0 | 0
78 | DEVELOPMENT FEE |  | 180523.5 | 0 | 0 | 180523.5 | 180523.5 | 0 | 0
79 | CARRYING COSTS |  | 92885.53 | 0 | 0 | 92885.53 | 92885.53 | 0 | 0
80 | FINANCING COSTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
82 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
83 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
84 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
85 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
86 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
87 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
88 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
89 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
90 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
91 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
92 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
93 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
94 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
95 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
96 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
97 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
98 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
99 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
| TOTAL |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0

## Draw #19
GENESIS CAPITAL DRAW FORM
| CLIENT: | Angeleno Investments | [5 empty] | TOTAL COMPLETED TO DATE: | 0 | #REF!
| DATE: | 2025-11-17 | [5 empty] | REMAINING $ IN BUDGET: | #REF!
| PROJECT: | 10910 Huston Street | [5 empty] | ORIGINAL SCHEDULE OF VALUES: | #REF!
| DRAW REQUEST: | 0 | [5 empty] | CHANGE ORDERS: | 0
[8 empty] | REVISED SCHEDULE OF VALUES: | #REF!
| DESCRIPTION OF WORK |  | SCHEDULED VALUES | PREVIOUS | + / - CHANGES | REVISED VALUES | REMAINING | DRAW | COMPLETED AND
|  |  |  | CHANGES |  |  | BUDGET | 19 | STORED TO DATE
1 | SOFT COSTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Site Security |  | 10580.63 | 0 | 0 | 10580.63 | 10580.63 | 0 | 0
3 | Soils Inspection |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Offsites (Transformer) |  | 20000 | 0 | 0 | 20000 | 20000 | 0 | 0
5 | Plan Check Fees |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Permits |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Survey |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Soils Engineer |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Soils Permit + T24 |  | 2500 | 0 | 0 | 2500 | 2500 | 0 | 0
10 | Special Inspections - Deputy |  | 15000 | 0 | 0 | 15000 | 15000 | 0 | 0
11 | Architect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Structural Engineer |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Structural Observation |  | 8000 | 0 | 0 | 8000 | 8000 | 0 | 0
14 | Civil Engineering |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | Grading Permit |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Landscape Architect/Designer |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Driveway Apron Permit |  | 2500 | 0 | 0 | 2500 | 2500 | 0 | 0
18 | Punch List - Misc. |  | 21962.77 | 0 | 0 | 21962.77 | 21962.77 | 0 | 0
19 | EBM, Low Voltage, Landscape, Waterproofing CA |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | Project Accounting/Tax Filing |  | 12994.01 | 0 | 0 | 12994.01 | 12994.01 | 0 | 0
21 | Legal & Professional Fees |  | 873.39 | 0 | 0 | 873.39 | 873.39 | 0 | 0
22 | Sewer CCTV and inspection |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | Environmental Phase I |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | Dry Utility Consultant |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | Dry Utility Survey |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
26 | MEP |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | Civil Construction Administration |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
28 | Permit Clearances & Agency Reviews |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | Demo Permit Fees |  | 500 | 0 | 0 | 500 | 500 | 0 | 0
30 | MEP Fees |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | Agency Signoffs |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | Specifications Writer Consultant |  | 2000 | 0 | 0 | 2000 | 2000 | 0 | 0
33 | Construction Consultant |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | Low Voltage Consultant |  | 15524 | 0 | 0 | 15524 | 15524 | 0 | 0
35 | Photovoltaic Consultant |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
36 | Construction Management / Observation (OO) |  | 49427.9 | 0 | 0 | 49427.9 | 49427.9 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
37 | CMFA Startup Fee |  | 22800 | 0 | 0 | 22800 | 22800 | 0 | 0
38 | Non-Profit Start Up Fee |  | 25000 | 0 | 0 | 25000 | 25000 | 0 | 0
39 | CMFA Construction Fee |  | 12000 | 0 | 0 | 12000 | 12000 | 0 | 0
40 | Non-Profit Construction Fee |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
41 | WTE Legal Costs for CMFA & Non-Profit Partner |  | 20000 | 0 | 0 | 20000 | 20000 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
43 | GENERAL CONDITIONS |  | 362115.24 | 0 | 0 | 362115.24 | 362115.24 | 0 | 0
44 | GENERAL REQUIREMENT |  | 124657.88 | 0 | 0 | 124657.88 | 124657.88 | 0 | 0
45 | SITE WORK |  | 139049.51 | 0 | 0 | 139049.51 | 139049.51 | 0 | 0
46 | CONCRETE |  | 253182 | 0 | 0 | 253182 | 253182 | 0 | 0
47 | MASONRY |  | 3562.64 | 0 | 0 | 3562.64 | 3562.64 | 0 | 0
48 | METALS |  | 324100 | 0 | 0 | 324100 | 324100 | 0 | 0
49 | FRAMING |  | 818554 | 0 | 0 | 818554 | 818554 | 0 | 0
50 | COUNTERTOPS |  | 56930 | 0 | 0 | 56930 | 56930 | 0 | 0
51 | CABINETS |  | 56930 | 0 | 0 | 56930 | 56930 | 0 | 0
52 | THERMAL MOISTURE PROTECTION |  | 173148 | 0 | 0 | 173148 | 173148 | 0 | 0
53 | DOORS |  | 204087.33 | 0 | 0 | 204087.33 | 204087.33 | 0 | 0
54 | WINDOWS |  | 106274.25 | 0 | 0 | 106274.25 | 106274.25 | 0 | 0
55 | STUCCO |  | 208002 | 0 | 0 | 208002 | 208002 | 0 | 0
56 | DRYWALL |  | 416355 | 0 | 0 | 416355 | 416355 | 0 | 0
57 | PAINTING |  | 120700 | 0 | 0 | 120700 | 120700 | 0 | 0
58 | FLOORING - common areas |  | 45150 | 0 | 0 | 45150 | 45150 | 0 | 0
59 | FLOORING - Units with baseboards |  | 93335 | 0 | 0 | 93335 | 93335 | 0 | 0
60 | SPECIALTIES |  | 25109.21 | 0 | 0 | 25109.21 | 25109.21 | 0 | 0
61 | EQUIPMENT |  | 153636 | 0 | 0 | 153636 | 153636 | 0 | 0
62 | FURNISHING |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
63 | FIRE SPRINKLERS |  | 108500 | 0 | 0 | 108500 | 108500 | 0 | 0
64 | FIRE ALARM |  | 68401 | 0 | 0 | 68401 | 68401 | 0 | 0
65 | SOLAR PANELS |  | 97000 | 0 | 0 | 97000 | 97000 | 0 | 0
66 | SECURITY ACCESS & SURVEILLANCE |  | 136430 | 0 | 0 | 136430 | 136430 | 0 | 0
67 | ELEVATORS & LIFT |  | 174882 | 0 | 0 | 174882 | 174882 | 0 | 0
68 | WATER SUBMETER (material) |  | 12273 | 0 | 0 | 12273 | 12273 | 0 | 0
69 | WATER SUBMETER (labor) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
70 | ROUGH PLUMBING |  | 751927 | 0 | 0 | 751927 | 751927 | 0 | 0
71 | FINISH PLUMBING |  | 90000 | 0 | 0 | 90000 | 90000 | 0 | 0
72 | HVAC |  | 259000 | 0 | 0 | 259000 | 259000 | 0 | 0
73 | ELECTRICAL |  | 880486.32 | 0 | 0 | 880486.32 | 880486.32 | 0 | 0
74 | CONTINGENCY |  | 529215.2 | 0 | 0 | 529215.2 | 529215.2 | 0 | 0
75 | INSURANCE (GL w/auto, workers compl) |  | 97177.07 | 0 | 0 | 97177.07 | 97177.07 | 0 | 0
76 | GROSS RECEIPT TAX |  | 6543.26 | 0 | 0 | 6543.26 | 6543.26 | 0 | 0
77 | GC FEE |  | 388708.28 | 0 | 0 | 388708.28 | 388708.28 | 0 | 0
78 | DEVELOPMENT FEE |  | 180523.5 | 0 | 0 | 180523.5 | 180523.5 | 0 | 0
79 | CARRYING COSTS |  | 92885.53 | 0 | 0 | 92885.53 | 92885.53 | 0 | 0
80 | FINANCING COSTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
82 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
83 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
84 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
85 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
86 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
87 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
88 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
89 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
90 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
91 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
92 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
93 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
94 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
95 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
96 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
97 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
98 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
99 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
| TOTAL |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0

## Draw #20
GENESIS CAPITAL DRAW FORM
| CLIENT: | Angeleno Investments | [5 empty] | TOTAL COMPLETED TO DATE: |  | #REF!
| DATE: | 2025-11-17
| PROJECT: | 10910 Huston Street | [6 empty] | 0
| DRAW REQUEST: | 0 | [5 empty] | REMAINING $ IN BUDGET: | #REF!
[8 empty] | REVISED SCHEDULE OF VALUES: | #REF!
| DESCRIPTION OF WORK |  | SCHEDULED VALUES | PREVIOUS | + / - CHANGES | REVISED VALUES | REMAINING | DRAW | COMPLETED AND
|  |  |  | CHANGES |  |  | BUDGET | 20 | STORED TO DATE
1 | SOFT COSTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Site Security |  | 10580.63 | 0 | 0 | 10580.63 | 10580.63 | 0 | 0
3 | Soils Inspection |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Offsites (Transformer) |  | 20000 | 0 | 0 | 20000 | 20000 | 0 | 0
5 | Plan Check Fees |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Permits |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Survey |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Soils Engineer |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Soils Permit + T24 |  | 2500 | 0 | 0 | 2500 | 2500 | 0 | 0
10 | Special Inspections - Deputy |  | 15000 | 0 | 0 | 15000 | 15000 | 0 | 0
11 | Architect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Structural Engineer |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Structural Observation |  | 8000 | 0 | 0 | 8000 | 8000 | 0 | 0
14 | Civil Engineering |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | Grading Permit |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Landscape Architect/Designer |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Driveway Apron Permit |  | 2500 | 0 | 0 | 2500 | 2500 | 0 | 0
18 | Punch List - Misc. |  | 21962.77 | 0 | 0 | 21962.77 | 21962.77 | 0 | 0
19 | EBM, Low Voltage, Landscape, Waterproofing CA |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | Project Accounting/Tax Filing |  | 12994.01 | 0 | 0 | 12994.01 | 12994.01 | 0 | 0
21 | Legal & Professional Fees |  | 873.39 | 0 | 0 | 873.39 | 873.39 | 0 | 0
22 | Sewer CCTV and inspection |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | Environmental Phase I |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | Dry Utility Consultant |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | Dry Utility Survey |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
26 | MEP |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | Civil Construction Administration |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
28 | Permit Clearances & Agency Reviews |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | Demo Permit Fees |  | 500 | 0 | 0 | 500 | 500 | 0 | 0
30 | MEP Fees |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | Agency Signoffs |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | Specifications Writer Consultant |  | 2000 | 0 | 0 | 2000 | 2000 | 0 | 0
33 | Construction Consultant |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | Low Voltage Consultant |  | 15524 | 0 | 0 | 15524 | 15524 | 0 | 0
35 | Photovoltaic Consultant |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | 0
36 | Construction Management / Observation (OO) |  | 49427.9 | 0 | 0 | 49427.9 | 49427.9 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
37 | CMFA Startup Fee |  | 22800 | 0 | 0 | 22800 | 22800 | 0 | 0
38 | Non-Profit Start Up Fee |  | 25000 | 0 | 0 | 25000 | 25000 | 0 | 0
39 | CMFA Construction Fee |  | 12000 | 0 | 0 | 12000 | 12000 | 0 | 0
40 | Non-Profit Construction Fee |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | 0
41 | WTE Legal Costs for CMFA & Non-Profit Partner |  | 20000 | 0 | 0 | 20000 | 20000 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
43 | GENERAL CONDITIONS |  | 362115.24 | 0 | 0 | 362115.24 | 362115.24 | 0 | 0
44 | GENERAL REQUIREMENT |  | 124657.88 | 0 | 0 | 124657.88 | 124657.88 | 0 | 0
45 | SITE WORK |  | 139049.51 | 0 | 0 | 139049.51 | 139049.51 | 0 | 0
46 | CONCRETE |  | 253182 | 0 | 0 | 253182 | 253182 | 0 | 0
47 | MASONRY |  | 3562.64 | 0 | 0 | 3562.64 | 3562.64 | 0 | 0
48 | METALS |  | 324100 | 0 | 0 | 324100 | 324100 | 0 | 0
49 | FRAMING |  | 818554 | 0 | 0 | 818554 | 818554 | 0 | 0
50 | COUNTERTOPS |  | 56930 | 0 | 0 | 56930 | 56930 | 0 | 0
51 | CABINETS |  | 56930 | 0 | 0 | 56930 | 56930 | 0 | 0
52 | THERMAL MOISTURE PROTECTION |  | 173148 | 0 | 0 | 173148 | 173148 | 0 | 0
53 | DOORS |  | 204087.33 | 0 | 0 | 204087.33 | 204087.33 | 0 | 0
54 | WINDOWS |  | 106274.25 | 0 | 0 | 106274.25 | 106274.25 | 0 | 0
55 | STUCCO |  | 208002 | 0 | 0 | 208002 | 208002 | 0 | 0
56 | DRYWALL |  | 416355 | 0 | 0 | 416355 | 416355 | 0 | 0
57 | PAINTING |  | 120700 | 0 | 0 | 120700 | 120700 | 0 | 0
58 | FLOORING - common areas |  | 45150 | 0 | 0 | 45150 | 45150 | 0 | 0
59 | FLOORING - Units with baseboards |  | 93335 | 0 | 0 | 93335 | 93335 | 0 | 0
60 | SPECIALTIES |  | 25109.21 | 0 | 0 | 25109.21 | 25109.21 | 0 | 0
61 | EQUIPMENT |  | 153636 | 0 | 0 | 153636 | 153636 | 0 | 0
62 | FURNISHING |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
63 | FIRE SPRINKLERS |  | 108500 | 0 | 0 | 108500 | 108500 | 0 | 0
64 | FIRE ALARM |  | 68401 | 0 | 0 | 68401 | 68401 | 0 | 0
65 | SOLAR PANELS |  | 97000 | 0 | 0 | 97000 | 97000 | 0 | 0
66 | SECURITY ACCESS & SURVEILLANCE |  | 136430 | 0 | 0 | 136430 | 136430 | 0 | 0
67 | ELEVATORS & LIFT |  | 174882 | 0 | 0 | 174882 | 174882 | 0 | 0
68 | WATER SUBMETER (material) |  | 12273 | 0 | 0 | 12273 | 12273 | 0 | 0
69 | WATER SUBMETER (labor) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
70 | ROUGH PLUMBING |  | 751927 | 0 | 0 | 751927 | 751927 | 0 | 0
71 | FINISH PLUMBING |  | 90000 | 0 | 0 | 90000 | 90000 | 0 | 0
72 | HVAC |  | 259000 | 0 | 0 | 259000 | 259000 | 0 | 0
73 | ELECTRICAL |  | 880486.32 | 0 | 0 | 880486.32 | 880486.32 | 0 | 0
74 | CONTINGENCY |  | 529215.2 | 0 | 0 | 529215.2 | 529215.2 | 0 | 0
75 | INSURANCE (GL w/auto, workers compl) |  | 97177.07 | 0 | 0 | 97177.07 | 97177.07 | 0 | 0
76 | GROSS RECEIPT TAX |  | 6543.26 | 0 | 0 | 6543.26 | 6543.26 | 0 | 0
77 | GC FEE |  | 388708.28 | 0 | 0 | 388708.28 | 388708.28 | 0 | 0
78 | DEVELOPMENT FEE |  | 180523.5 | 0 | 0 | 180523.5 | 180523.5 | 0 | 0
79 | CARRYING COSTS |  | 92885.53 | 0 | 0 | 92885.53 | 92885.53 | 0 | 0
80 | FINANCING COSTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
82 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
83 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
84 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
85 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
86 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
87 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
88 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
89 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
90 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
91 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
92 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
93 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
94 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
95 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
96 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
97 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
98 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
99 | Open Item |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0
| TOTAL |  | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0